## PP
PROCUREMENT PLAN
TRADE PROMOTION AND QUALITY INFRASTRUCTURE PROJECT
Package No. | Description of Contract Packages | No. of Packages | Procurement Method | Review By Bank (PRIOR / Post) | TOR/TS Submision to WB | Tender documents (Bidding document, RFP, ITQ) Submision to WB | Contract Signing | Contract Completion | Contract price | Contractor/Consultant | Disbursed total (Loan proceeds)
A | B | C | E | F | G | H | I | J | K | L | M
Component 1 - Improving the effectiveness of the trade promotion and quality system of the country |  |  | RBF
Component 2 - Promoting Investment & Export
Subcomponent 2.1 Services to Investors & Exporters
CONSULTANT'S SERVICES
2.1.1 | International consultants for representative offices | 6 | IC | Prior
2.1.2 | Local consultants for representative offices | 6 | IC | Prior
2.1.3 | Export Programs & Market Research
2.1.3a | Develop "How to Export Manual" and staff training | 1 | IC | Post
2.1.3b | Exporters workshop | 1 | CQ | Post
2.1.3c | Export Readiness Assessment | 1 | IC | Prior
2.13d | Export Development Program | 1 | CQ | Post
2.1.3e | Market analysis for foreign export promotion offices | 1 | CQ | Prior
2.1.4 | Online platform of export manual, CRM programming, and on-site assessment of exporters | 1 | CQ | Prior
2.1.5 | Resident Advisor | 1 | IC | Prior
2.1.6 | Training for Staff | 1 | CQ | Post
2.1.7 | Promotion Materials (Investment & Export) | 1 | QCBS | Prior
2.1.8 | Customer Relations Management (CRM) System Design | 1 | IC | Post
2.1.9 | Image Building and Investment Outreach | 1 | QCBS | Prior
2.1.10 | Investment Aftercare | 1 | IC | Prior
Sub-Component 2.2. Export Promotion Grants
2.2.1 | Grants (70/30) | multi | per OM
CONSULTING SERVICES
2.2.2 | Grant Manager | 2 | IC | Prior
2.2.3 | Selection Committee Members | 5 | IC | Prior
2.2.4 | Marketing and Communication |  | CQ | Prior
Sub-Component 2.3. PPPs to increase export & investment
2.3(a) | Cluster Development | multi
WORKS
2.3.1 | Works
GOODS
2.3.2 | Goods
CONSULTING SERVICES
2.3.3 | Grant Manager | 1 | IC | Prior
2.3(b) | Research skills development PPP with Multinationals
2.3.4 | Investments | multi | per OM
CONSULTING SERVICES
2.3.5 | R&D PPP manager | 1 | IC | Prior
2.3.6 | R&D PPP Expert | 1 | IC | Prior
2.3.7 | Selection Committee Members for sub-component 2.3 (a) and (b) | 5 | IC | Prior
2.3.8 | Marketing and Communication | 1 | CQ | Post
Component 3 - Modernizing the national quality infrastructure
Subcomponent 3.1. Refurbishment of industrial metrology building
WORKS
3.1.1 | Renovation of industrial metrology building and laboratories | 1 | NCB | Prior
GOODS
3.1.2 | Procurement of Equipment for industrial metrology building and laboratories | 1 | ICB | Prior
3.1.3 | Procurement of Furniture for industrial metrology building and laboratories | 1 | ICB | Prior
CONSULTING SERVICES
3.1.4 | International firm to support design and renovation of metrology building and laboratories | 1 | QCBS | Prior
3.1.5 | Preparation of design-cost estimate document&Author’s Supervision for Renovation of industrial metrology building and laboratories | 1 | CQ | Post
3.1.6 | Implementation of technical supervision of Renovation of industrial metrology building and laboratories | 1 | CQ | Post
3.1.7 | Renovation Manager (industrial metrology building ) | 1 | IC | Post
3.1.8 | International Resident Advisor | 1 | IC | Prior
3.1.9 | Consulting firm for the implementation of the quality system for metrological laboratories | 1 | CQ | Post
TRAINING
3.2.11 | Workshops and Training Programs | 5 | SOE | Prior
Sub-component 3.2: Refurbishment of NAB offices and capacity building of NAB staff
WORKS
3.2.1 | Refurbishment of NAB offices | 1 | NCB | Post
GOODS
3.2.2 | Procurement of IT Equipment for NAB offices | 1 | SH | Post
3.2.3 | Procurement of Furniture for NAB offices | 1 | SH | Post
CONSULTANT'S SERVICES
3.2.5 | Preparation of design-cost estimate document&Author’s Supervision for Refurbishment of NAB offices | 1 | CQ | Post
3.2.6 | Implementation of technical supervision of Refurbishment of NAB offices | 1 | CQ | Post
3.2.7 | Development of IT management system including on-line application system (e-accreditation) and NAB database&Development of CRM and monitoring | 1 | QCBS | Prior
3.2.8 | Renovation Manager (NAB offices) | 1 | IC | Post
3.2.9 | Resident Advisor (with international work experience) to implement NAB quality control system | 1 | IC | Prior
Sub-Component 3.3. Development of Database of Catalogue of Standards for SARM
GOODS
3.3.1 | Procurement of International standards documents (ISO-IEC, CEN/CENELC) |  | SH | Post
3.3.2 | Procurement of IT Equipment for SARM |  | SH | Post
CONSULTANT'S SERVICES
3.3.3 | Implementation of IT system |  | CQ | Prior
Component 4: Project Management, Monitoring and Evaluation
4.1.1 | Operating Costs |  | SOE
CONSULTANT'S SERVICES
4.1.2 | Project Manager | 1 | IC | Prior
4.1.3 | Translator | 1 | IC | Post
4.1.4 | IT expert | 1 | IC | Post
4.1.5 | Engineer | 1 | IC | Post
4.1.6 | Procurement Consultant | 1 | IC | Post
4.1.7 | Financial Management Consultant | 1 | IC | Post
4.1.8 | Project Monitoring and Evaluation Consultant | 1 | IC | Prior
4.1.9 | Project Audit | 1 | LCS | Prior
4.1.10 | Performance Evaluation of Agencies | 1 | CQ | Prior
4.1.11 | Safeguards Consultant | 1 | IC | Post
GRAND TOTAL