## General Aspects
Procurement Plan |  | Credit No xx-XK | Project ID: P143055
Project Name: | Kosovo Energy Efficiency and Renewable Energy Project
I. General
Agreed date of procurement Plan
Original: | xxxx, 2014
Date of General Procurement Notice: Published on UNDB online on xxxx, 2014
II. Goods and Works
1. Prior Review Threshold: Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement - January 2011
| Procurement Method | Procurement Method Threshold (Euro) | Prior Review Threshold (in Euro)
1 | ICB (Goods) | ≥ 730,000 | All
2 | NCB (Goods) Packages | ≤ 730,000 | First 2
3 | ICB (Works) Packages | ≥ 3,600,000 | All
4 | NCB (Works) Packages | ≤ 3,600,000 | First 2
5 | Shopping (Goods) | ≤ 73,000 in accordance with 3.5 of the Procurement Guidelines | First Contract
6 | Shopping (Works) | ≤145,000 in accordance with 3.5 of the Procurement Guidelines | First Contract
7 | Direct Contracting (Goods and Works) | In accordance with paragraph 3.7 of the Procurement Guidelines | All (with justification)
III. Selection of Consultants
1. Prior Review Threshold: Selection Decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants - January 2011
| Selection Method | Selection Method Threshold (Euro) | Prior Review Threshold (in Euro)
1 | Quality and Cost Based Selection (QCBS)* | ≥ 220,000 | All
2 | Fixed Budget Selection (FBS) | In accordance with paragraph 3.5 of the Consultants Guidelines | ≥ 146,000
3 | Least Cost Selection (LCS) | In accordance with paragraph 3.6 of the Consultants Guidelines | ≥ 146,000
4 | Consultants' Qualification Selection (CQS) | In accordance with paragraph 3.7 of the Consultant's Guidelines | First Contract
5 | Single Source Selection (SSS) (Firms) | In accordance with paragraphs 3.8 thru.3.11 of the Consultants Guidelines | All (with justification)
6 | Individual Consultants (IC) | In accordance with Section V of the Consultants Guidelines | ≥ 73,000
7 | Single Source Selection (SSS) (Individuals) | In accordance with paragraph 5.6 of the Consultants Guidelines | All (with justification)
*All ToRs for Consulting Contracts will be reviewed
2. Short list comprising entirely of national consultant: Short list of consultants for services, estimated to cost less thant Euro 215,000 equivalent per contract,
may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultants Guidelines.
Detailed Procurement Plan for goods, works, and consulting services contracts are in the next excel spread sheet
The Borrower will prepare a draft Project Operations Manual which should include a section of Procurement Arrangements to be followed under the project.

## OC (hidden)
Sub Total (Works)
Package Nr. | Description of Contract Package | Procurement Type | Estimated cost of the Project, Euro | Estimated cost of the Project, USD | Status | Comments/Explanations | Additional information
Component 1: Building institutional capacity to improve financial proctection and quality care
Sub-component 1.1: Improving financial protection
OC.1 | Training from international experts to design and implement policies, systems design and operational documents for HIF (Staff Secondments) | OC | 72992.7007 | 100000 | Planned | Secondments of staff from another HIF to Kosovo
Revised
Actual
OC.2 | DRG license | OC | 145985.4015 | 200000 | Planned
Revised
Actual
OC.3 | Translation of DRGs | OC | 36496.3504 | 50000 | Planned
Revised
Actual
Sub-component 1.2: Improving Quality of Care
OC.4 | In country travel for central level staff staff MoH and HIF | OC | 10000 | 13700 | Planned
Revised
Actual
Monitoring and Evaluation
OC.5 | Production of Studies and Surveys | OC | 36496.3504 | 50000 | Planned | Studies for M&E undertaken by IPH
Revised
Actual
Component 2: Strengthening primary care
OC.6 | Capitation based performance payments (No procurement required, since capitation payments) |  | 9160017.7355 | 12549224.2977 | Planned
Revised
Actual
Component 3: Project Management
OC.7 | PCU Office Running Cost | OC | 97810.219 | 134000 | Planned | Includes operating costs for PCU. Based on MoH communication, premises will be provided by the MoH, so rent is not included here. Vehicle to be provided by MoH.
Revised
Actual
OC.8 | PCU Staff Travel | OC | 10000 | 13700 | Planned | PCU travel to support the Project
Revised
Actual
OC.9 | Loan Audits for first 18 months | OC | 175000 | 239750 | Planned | 5 year contract with auditor. No re-advertisement needed.
Revised
Actual

## Training (hidden)
Sub Total (Works)
Package Nr. | Description of Contract Package | Procurement Type | Estimated cost of the Project, Euro | Estimated cost of the Project, USD | Status | Comments/Explanations | Additional information
Component 1: Building institutional capacity to improve financial proctection and quality care
Sub-component 1.1: Improving financial protection
Tr.1 | 1. Trainings for HIF/HFA staff on mandatory health insurance. 2. Media training for Ministry and HIF staff 3. Within Internal Communications Campaign of MoH: Trainings for facility staff | TR | 364963.5036 | 500000 | Planned | Includes training for HIF staff on health insurance implementation and media training for key functionaries in Ministry and HIF to improve media interaction skills. For internal communications: 'Townhalls' or workshops on health insurance for facility staff
Revised
Actual
Tr.2 | Training and study tours for DRG Implementation | TR | 364963.5036 | 500000 | Planned | To confirm number of participants for training and study tours for HFA/HIF staff, hospital staff
Revised
Actual
Sub-component 1.2: Improving Quality of Care
Tr.3 | Development of eHealth Development Capacity Building, Study tours, training, and workshops | TR | 43795.6204 | 60000 | Planned
Revised
Actual
Tr.4 | Training for MoH, Municipality and PHC facility staff on the capitation payments manual and implementation | TR | 72992.7007 | 100000 | Planned | Training of Municipality, HIF and facility staff to implement capitation payments, scheme, reporting, quality standard and quality improvement mechanism. The number to be trained should also depend on plans to scale up.
Revised
Actual
Monitoring and Evaluation
-
Component 2: Strengthening primary care
-
Component 3: Project Management
Tr.5 | Training /seminars/workshops (launch) | TR | 56000 | 76720 | Planned | Project launch workshop; Trainings on POM for PCU staff and key MoH staff; FM training for PCU FM consultant; Procurement training for Procurement consultant, and IT procurement training for Procurement and IT consultant
Revised
Actual

## Disbursements 2014-2016 (hidden)
Tentative Disbursements in EUR
FY | 2014 | 2015 | 2016
In PP | 542296.3504 | 2244917.0693 | 3096760.1934
Capitation Payments | - | 274985.2 | 2406185.0355
Total | 542296.3504 | 2519902.2693 | 5502945.229
Retroactive Financing | 258507 | - | -

## PP
1.37
Project Name: Kosovo Energy Efficiency & Renewable Energy Project
|  | Project ID Number: P143055 |  |  | Credit No: IDA- 55080-XK. | [8 empty] | Closing date: June 31, 2020
| Original: | May, 2014 |  |  |  | `
Update date:
No. | Package Nr. | Description of Contract Package | Procurement Type | Procurement method | Bank's review (Prior/Post) | Actual Contract Amount | Disbursed Amount | Physical Progress (%) | Payment to Vendor (%) | Retroactive Financing Euro | Procurement Status | Bid Document/RFP/TOR and SPN/EOI sent to the Bank | Bank's NO objection to Bid Document/RFP | Issue date of the Bid Document/RFP | Bid opening/Proposal Submission | Bid evaluation report sent to the Bank | Bank's NO to the Bid Evaluation Report/ Technical Evaluation Report | Draft Contract sent to the Bank | Bank's no objection to Contract award | Contract signing date | Contract completion date | Supplier/ Contractor name | Name of the Bidder/Supplier/Consultant
Component 1: Energy Efficiency and Renewable Energy Investments in Public Buildings - Pilot EE Investment Program for Municipalities
Sub-component 1A: EE Investments in Central Government Buildings & Renewable Energy
1 | 1A.1 | Renovation of Building - 1 (EE & RE) (Year 2014) | W | NCB | Prior | [5 empty] | Planned | 2014-08-20 | 2014-08-25 | 2014-08-28 | 2014-09-27 | 2014-10-04 | 2014-10-08 | - | - | 2014-11-20 | 2015-01-20
Revised
Actual
2 | 1A.2 | Renovation of Building - 2 (EE & RE) (Year 2015) | W | NCB | Prior | [5 empty] | Planned | 2015-08-20 | 2015-08-25 | 2015-08-28 | 2015-09-28 | 2015-10-05 | 2015-10-09 | - | - | 2015-10-14 | 2015-12-20
Revised
Actual
3 | 1A.3 | Renovation of Building - 3 (EE & RE) (Year 2016) | W | NCB | Post | [5 empty] | Planned | 2016-08-10 | 2016-08-15 | 2016-08-18 | 2016-09-18 | 2016-09-25 | 2016-09-29 | - | - | 2016-10-05 | 2016-12-20
Revised
Actual
4 | 1A.4 | Renovation of Building - 4 (EE & RE) (Year 2016) | W | NCB | Post | [5 empty] | Planned | 2016-08-10 | 2016-08-15 | 2016-08-18 | 2016-09-18 | 2016-09-25 | 2016-09-29 | - | - | 2016-10-04 | 2017-01-15
Revised
Actual
5 | 1A.5 | Renovation of Building - 5 (EE & RE) (Year 2017) | W | NCB | Post | [5 empty] | Planned | 2017-10-01 | 2017-10-06 | 2017-10-10 | 2017-11-10 | 2017-11-16 | 2017-11-20 | - | - | 2017-11-25 | 2018-01-31
Revised
Actual
6 | 1A.6 | Renovation of Building - 6 (EE & RE) (Year 2017) | W | NCB | Post | [5 empty] | Planned | 2017-10-01 | 2017-10-06 | 2017-10-10 | 2017-11-07 | 2017-11-13 | 2017-11-17 | - | - | 2017-11-24 | 2018-01-31
Revised
Actual
7 | 1A.7 | Renovation of Building - 7 (EE & RE) (Year 2018) | W | NCB | Post | [5 empty] | Planned | 2018-08-10 | 2018-08-15 | 2018-08-19 | 2018-09-19 | 2018-09-25 | 2018-09-29 | - | - | 2018-10-04 | 2018-12-20
Revised
Actual
8 | 1A.8 | Renovation of Building - 8 (EE & RE) (Year 2018) | W | NCB | Post | [5 empty] | Planned | 2018-08-10 | 2018-08-15 | 2018-08-19 | 2018-09-19 | 2018-09-25 | 2018-09-29 | - | - | 2018-10-04 | 2018-12-20
Revised
Actual
9 | 1A.9 | Renovation of Building - 9 (EE & RE) (Year 2019) | W | NCB | Post | [5 empty] | Planned | 2019-01-15 | 2019-01-20 | 2019-01-24 | 2019-02-24 | 2019-03-02 | 2019-03-06 | - | - | 2019-03-11 | 2019-05-31
Revised
9 | [10 empty] | Actual
10 | 1A.10 | Renovation of Building - 10 (EE & RE) (Year 2020) | W | NCB | Post | [5 empty] | Planned | 2019-06-15 | 2019-06-20 | 2019-06-24 | 2019-07-25 | 2019-07-31 | 2019-08-04 | - | - | 2019-08-09 | 2020-05-31
Revised
10 | [10 empty] | Actual
Sub-component B: Pilot Investment Program for Municpalities
11 | 1B.1 | Municipal Building 1 (Year 2019) | W | NCB | Post | [5 empty] | Planned | 2019-02-05 | 2019-02-10 | 2019-02-14 | 2019-03-14 | 2019-03-20 | 2019-03-24 | - | - | 2019-03-31 | 2019-08-30
Revised
Actual
12 | 1B.2 | Municipal Building 2 (Year 2020) | W | NCB | Post | [5 empty] | Planned | 2020-02-05 | 2020-02-10 | 2020-02-14 | 2020-03-13 | 2020-03-19 | 2020-03-23 | - | - | 2020-03-30 | 2020-05-31
Revised
Actual
Sub-component C :Technical Studies and Supervision
13 | 1C.1 | Detailed design/bidding Documents/Supervision/Commissioning for first 5 EE audits (2014) | CS | CQS | Prior | [5 empty] | Planned | 2014-04-15 | 2014-04-19 | 2014-05-02 | 2014-05-30 | 2014-06-13 | 2014-06-17 | 2014-07-08 | 2014-07-12 | 2014-10-11 | 2015-02-19
Revised
[6 empty] | 21999 |  |  |  | 21999 | Actual | 2014-04-11 | 2014-04-26 | 2014-05-02 | 2014-06-10 | 2014-06-16 | 2014-06-16 | 2014-07-17 | 2014-07-21 |  |  | Arch&Design
14 | 1C.2 | Detailed Designs/Bidding Documents/Supervision/Commissioning/Passports (2015) | CS | CQS | Post | [5 empty] | Planned | 2015-01-15 | 2015-01-19 | 2015-01-22 | 2015-02-19 | 2015-03-05 | 2015-03-09 | 2015-03-30 | 2015-04-03 | 2015-04-17 | 2016-01-19
Revised
Actual
15 | 1C.3 | Detailed Designs/Bidding Documents/Supervision/Commissioning/Passports (2016) | CS | CQS | Post | [5 empty] | Planned | 2016-01-07 | 2016-01-11 | 2016-01-14 | 2016-02-11 | 2016-02-25 | 2016-02-29 | 2016-03-21 | 2016-03-25 | 2016-04-08 | 2017-02-14
Revised
Actual
16 | 1C.4 | Detailed Designs/Bidding Documents/Supervision/Commissioning/Passports (2017) | CS | CQS | Post | [5 empty] | Planned | 2017-01-07 | 2017-01-11 | 2017-01-14 | 2017-02-11 | 2017-02-25 | 2017-03-01 | 2017-03-22 | 2017-03-26 | 2017-04-09 | 2018-03-02
| 3.0167 | [9 empty] | Revised
| 2.9 | [9 empty] | Actual
17 | 1C.5 | Detailed Designs/Bidding Documents/Supervision/Commissioning/Passports (2018) | CS | CQS | Post | [5 empty] | Planned | 2018-01-07 | 2018-01-11 | 2018-01-14 | 2018-02-11 | 2018-02-25 | 2018-03-01 | 2018-03-22 | 2018-03-26 | 2018-04-09 | 2019-01-19
| 2.6667 | [9 empty] | Revised
| 2.55 | [9 empty] | Actual
18 | 1C.6 | Detailed Designs/Bidding Documents/Supervision/Commissioning/Passports (2019) | CS | CQS | Post | [5 empty] | Planned | 2018-06-14 | 2018-06-18 | 2018-06-21 | 2018-07-19 | 2018-08-02 | 2018-08-06 | 2018-08-27 | 2018-08-31 | 2018-09-14 | 2019-06-20
Revised
Actual
19 | 1C.7 | Detailed Designs/Bidding Documents/Supervision/Commissioning/Passports (2020) | CS | CQS | Post | [5 empty] | Planned | 2019-06-14 | 2019-06-18 | 2019-06-21 | 2019-07-19 | 2019-08-02 | 2019-08-06 | 2019-08-27 | 2019-08-31 | 2019-09-14 | 2020-06-20
Revised
Actual
20 | 1C.8 | Landfill EA/Light Disposal | CS | CQS | Post | [5 empty] | Planned | 2014-10-01 | 2014-10-05 | 2014-10-18 | 2014-11-15 | 2014-11-29 | 2014-12-03 | 2014-12-24 | 2014-12-28 | 2015-01-11 | 2016-12-15
Revised
Actual
21 | 1C.9 | Social Survey | CS | CQS | Post | [5 empty] | Planned | 2014-10-01 | 2014-10-05 | 2014-10-18 | 2014-11-15 | 2014-11-29 | 2014-12-03 | 2014-12-24 | 2014-12-28 | 2015-01-11 | 2015-12-15
| 0.56667 | [9 empty] | Revised
| 0.45 | [9 empty] | Actual
| Total: |  |  |  |  | 21999 |  |  |  | 21999
Component 2: Policy and Regulatory Support for RE/EE
Sub-component 2A: Support to ERO for RE and EE Development
22 | 2A.1 | Regulatory Support for Renewal Energy Regulatory Framework and Grid Integration | CS | QCBS | Prior | [5 empty] | Planned | 2014-07-31 | 2014-08-04 | 2014-08-07 | 2014-09-10 | 2014-09-24 | 2014-09-28 | 2014-10-21 | 2014-10-25 | 2014-11-01 | 2016-06-30
[11 empty] | Revised | 2014-11-17 | 2014-11-21 | 2014-11-24 | 2014-12-28 | 2015-01-11 | 2015-01-15 | 2015-02-07 | 2015-02-11 | 2014-11-01 | 2016-06-30
Actual
23 | 2A.2 | Streamline Procedures and Tariff | CS | QCBS | Prior | [5 empty] | Planned | 2016-06-30 | 2016-07-04 | 2016-07-07 | 2016-08-10 | 2016-08-24 | 2016-08-28 | 2016-09-20 | 2016-09-24 | 2016-09-26 | 2017-03-31
Revised
Actual
24 | 2A.3 | Renewable Energy Assessment | CS | QCBS | Prior | [5 empty] | Planned | 2015-09-30 | 2015-10-04 | 2015-10-07 | 2015-11-10 | 2015-11-24 | 2015-11-28 | 2015-12-21 | 2015-12-25 | 2015-12-30 | 2017-03-30
Revised
Actual
|  | Total: |  |  |  | 0 |  |  |  | 0
Sub-component 2B: Support to MED for EE Secondary Legislation
25 | 2B.1 | Development of Energy Efficiency Fund | CS | QCBS | Prior | [5 empty] | Planned | 2015-12-15 | 2015-12-19 | 2015-12-22 | 2016-01-25 | 2016-02-08 | 2016-02-12 | 2016-03-06 | 2016-03-10 | 2016-04-01 | 2017-01-31
Revised
Actual
26 | 2B.2 | Review of Public Procurement for Energy Service Companies | CS | CQS | Post | [5 empty] | Planned | 2017-03-10 | 2017-03-14 | 2017-03-17 | 2017-04-20 | 2017-05-04 | 2017-05-08 | 2017-05-31 | 2017-06-04 | 2017-06-15 | 2018-12-31
Revised
Actual
27 | 2B.4 | Home Owners Association (HOA) Implementation | CS | QCBS | Prior | [5 empty] | Planned | 2016-04-10 | 2016-04-14 | 2016-04-17 | 2016-05-21 | 2016-06-04 | 2016-06-08 | 2016-07-01 | 2016-07-05 | 2016-07-20 | 2017-12-31
Revised
Actual
|  | Total: |  |  |  | 0 |  |  |  | 0
Component 3: Project Implementation Support
28 | 3.1 | Project Manager | CS | IC | Prior | [5 empty] | Planned | 2014-02-10 | - | - | 2014-03-01 | 2014-03-08 | - | 2014-03-12 | - | 2014-03-19 | 2020-08-31 | Naim Bujupi
Revised
[6 empty] | 7200 |  |  |  | 7200 | Actual | 2014-02-18 |  |  | 2014-03-04 | 2014-03-11 | - | 2014-03-16 | - | 2014-03-01 | 2014-09-01
29 | 1131/013/037/221 | Project Manager - Contract Extension |  |  |  | 7200 |  |  |  | 7200 | Actual | NA |  |  | NA | NA |  | 2014-08-29 | 2014-09-08 | 2014-09-01 | 2015-02-28
30 | 3.2 | Procurement Specialist | CS | IC | Prior | [5 empty] | Planned | 2014-02-10 | - | - | 2014-03-01 | 2014-03-08 |  | 2014-03-12 |  | 2014-03-19 | 2020-08-31 | Luan Asllani
Revised
[6 empty] | 2880 |  |  |  | 2880 | Actual | 2014-02-18 |  |  | 2011-03-04 | 2014-03-11 | - | 2014-03-16 | - | 2014-04-01 | 2014-09-30
31 | 3.3 | Environmental Specialist | CS | IC | Prior | [5 empty] | Planned | 2014-02-10 | - | - | 2014-03-01 | 2014-03-08 |  | 2014-03-12 |  | 2014-03-18 | 2016-06-30 | Fahrush Azemi
Revised
[6 empty] | 2880 |  |  |  | 2880 | Actual | 2014-02-17 |  |  | 2014-03-03 | 2014-03-10 | - | 2014-03-15 | - | 2014-04-07 | 2014-09-07
32 | 11313/13/37/221 | Environmental Specialist - Contract Extension |  |  |  | 2880 |  |  |  | 2880 | Actual | NA |  |  | NA | NA |  | 2014-08-29 | 2014-09-08 | 2014-09-07 | 2015-03-07
33 | 3.4 | Financial Management Specialist | CS | IC | Prior | [5 empty] | Planned | 2014-09-03 | - | - | 2014-09-17 | 2014-09-24 | - | 2014-09-28 | - | 2014-10-01 | 2020-08-31
[11 empty] | Revised | 2015-03-02 |  |  | 2015-03-16 | 2015-03-21 |  | 2015-03-25 |  | 2015-03-31 | 2020-08-31
Actual
34 | 3.5 | Construction Engineer | CS | IC | Prior | [5 empty] | Planned | 2014-06-06 | - | - | 2014-06-20 | 2014-06-27 | - | 2014-07-01 | - | 2014-07-05 | 2020-08-31
Revised
[11 empty] | Actual | 2014-06-24 | 2014-07-17 | 2014-07-21 | 2014-08-04
35 | 3.6 | International Technical Advisor | CS | IC | Prior | [5 empty] | Planned | 2014-07-06 | - | - | 2014-07-20 | 2014-07-27 | - | 2014-08-01 | - | 2014-08-05 | 2020-08-31
[11 empty] | Revised | 2015-03-02 |  |  | 2015-04-02 | 2015-04-09 |  | 2015-04-19 |  | 2015-04-21 | 2020-08-31
Actual
36 | 3.7 | Financial Audit | CS | LCS | Post | [5 empty] | Planned | 2014-06-01 | - | - | 2014-06-20 | 2014-06-30 | - | 2014-07-10 | - | 2014-07-15 | 2020-08-31
[11 empty] | Revised | 2015-06-01 |  |  | 2015-06-20 | 2015-06-30 |  | 2015-07-10 |  | 2015-07-15 | 2020-08-31
Actual
|  | Total: |  |  |  | 23040 |  |  |  | 23040
|  | TOTAL PROJECT COST |  |  |  | 45039 |  |  |  | 45039
Formulas:
Closing date: June 31, 2020 = [Bank's NO objection to Bid Document/RFP]+3
Bid opening/Proposal Submission = [Closing date: June 31, 2020]+30
Bid evaluation report sent to the Bank = [Bid opening/Proposal Submission]+7
Contract signing date = [Bank's no objection to Contract award]+91
Bank's no objection to Contract award = [Draft Contract sent to the Bank]+4