|  |
| --- |
| 75749 v2  **Restructuring** **Status:** **Archived** |
| **Restructuring Type:** **Level two** |
| Last modified on date : 04/16/2013 |

|  |  |
| --- | --- |
| **1. Basic Information** | |
| Project ID & Name | P084437: CN-Rural Health |
| Country | China |
| Task Team Leader | Shuo Zhang |
| Sector Manager/Director | Toomas Palu |
| Country Director | Klaus Rohland |
| Original Board Approval Date | 06/24/2008 |
| Original Closing Date: | 12/31/2013 |
| Current Closing Date | 12/31/2013 |
| Proposed Closing Date [if applicable] | 12/31/2014 |
| EA Category | B-Partial Assessment |
| Revised EA Category | B-Partial Assessment-Partial Assessment |
| EA Completion Date | 10/10/2005 |
| Revised EA Completion Date | 04/22/2008 |

|  |  |  |
| --- | --- | --- |
| **2. Revised Financing Plan (US$m)** | | |
| **Source** | **Original** | **Revised** |
| BORR | 50.00 | 50.00 |
| DFID | 10.00 | 10.00 |
| IBRD | 50.00 | 50.00 |
| **Total** | 110.00 | 110.00 |

|  |  |  |
| --- | --- | --- |
| **3. Borrower** | | |
| **Organization** | **Department** | **Location** |
| People's Republic of China |  | China |

|  |  |  |
| --- | --- | --- |
| **4. Implementing Agency** | | |
| **Organization** | **Department** | **Location** |
| National Health and Family Planning Commission (NHFPC) | Center for Project Supervision and Management (CPSM) | China |

|  |  |  |
| --- | --- | --- |
| **5. Disbursement Estimates (US$m)** | | |
| **Actual amount disbursed as of 04/30/2013** **38.63** | | |
| **Fiscal Year** | **Annual** | **Cumulative** |
| 2013 | 3.00 | 41.63 |
| 2014 | 6.37 | 48.00 |
| 2015 | 2.00 | 50.00 |
|  | **Total** | **50.00** |

|  |  |
| --- | --- |
| **6. Policy Exceptions and Safeguard Policies** | |
| **Does the restructured project require any exceptions to Bank policies?** | N |
|  |  |
|  |  |
| **Does the restructured projects trigger any new safeguard policies? If yes, please select from the checklist below and update ISDS accordingly before submitting the package.** | N |

|  |
| --- |
| **7a. Project Development Objectives/Outcomes**  **Original/Current Project Development Objectives/Outcomes** |
| The main project objective is increased and more equitable access to quality health services, improved financial protection, and better management of public health threats in pilot provinces and counties, with lessons to support reforms in non-project areas. |

|  |
| --- |
| **7b. Revised Project Development Objectives/Outcomes** [if applicable] |
|  |