BRICKS Joint Procurement Plan

Version of April 2015

## General

1. 	Project information:

- Project Name: Building Resilience through Innovation, C

- ommunication and Knowledge Services (BRICKS) Project

- Country: Regional

- Recipients (3): Interstate Committee for Drought Control in the Sahel (CILSS), Sahel and Sahara Observatory (OSS), and West and Central Africa Office of the International Union for Conservation of Nature (IUCN)

- Grant Numbers:TF014804, TF014805, TF014806

2.	Bank’s approval Date of the procurement Plan: Original March 2015; Revisions (to be filled in upon receipt of No Objection form the World Bank]

- Date of General Procurement Notice: ……in the Development Business No____

- Period covered by this procurement plan: March 2015 to December 2015

##### II. Goods, Works and Non-consulting services

- Prior Review Threshold: Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement:

| Description | Procurement Methods | Threshold $EU | Prior review |
| --- | --- | --- | --- |
| 1. Works | No works will be financed | No works will be financed | No works will be financed |
| 2. Goods and Non-Consultant services | ICB | ≥ 1 000.000 | All |
|  | NCB | < 1.000.000 | None |
|  | Shopping | < 100.000 | None |
|  | Shopping for vehicles | <150.000 | None |
|  | SSS | No threshold | Contract estimated to about $100,000 and above |

ICB: International Competitive Bidding

NCB: National Competitive Bidding

SSS: Single Source

2.	Pre-qualification. Not applicable

3.	Proposed Procedures for CDD Components (as per paragraph. 3.17 of the Guidelines: Not Applicable

Reference to (if any) Project Operational/Procurement Manual: Not Applicable

Any Other Special Procurement Arrangements: Not Applicable

- Procurement Packages with Methods and Time Schedule

| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Ref. No. | Contract (Description) | Estimated Cost [$] (000) | Procurement Method | Prequalification (yes/no) | Domestic Preference (yes/no) | Review by Bank (Prior / Post) | Expected Bid-Opening Date | Comments |
| CILSS |
| 1 | Decision support portal hosting (servers and data storage) | 10 000 | Shopping | No | No | Post | June 2015 |  |
| 2 | Acquisition of laptops and printers | 35 000 | Shopping | No | No | Post | June 2015 |  |
| 3 | Acquisition of on line information monitoring software and email marketing software | 1 100 | Shopping | No | No | Post | July 2015 |  |
| IUCN |
| 1 | Translation of various documents | 4 000 | Shopping | Post | No | Post | April 2015 |  |
| 2 | Digital camcorder | 4 000 | Shopping | No | No | Post | May 2015 |  |
| OSS |
| 1 | Acquisition of 3 desktop and 2 laptops + GIS tools and software + peripherals (GPS, printer, scanner, etc.) | 30 000 | Shopping | No | No | Post | May 2015 |  |
| 2 | Geospatial /RS data purchase and acquisition | 50 000 | Shopping | No | No | Post | September 2015 |  |
| 3 | Total travel fees for : | 138000 | Shopping | No | No | Post | March 2015 |  |
|  | Participation to international events | 3000 |  |  |
|  | Regional level M&E Framework for the SAWAP portfolio | 10000 |  |  |
|  | EXACT regional training | 30000 |  |  |
|  | Support to SAWAP project M&E and GIS | 20000 |  |  |
|  | Regional workshop on harmonization of indicators | 25000 |  |  |
|  | Regional GIS and RS training | 30 000 |  |  |  |  |  |  |
|  | Validation maps with the national teams | 20 000 |  |  |  |  |  |  |
| 4 | Documents Translation | 20000 | Shopping | No | No | Post | May 2015 | 30% of the organization fees |
| 5 | Renting a dedicated server | 5 000 | Shopping | No | No | Post | May 2015 | Cost to renting a broad band server for storage and access to spatial data |

##### III. Selection of Consultants

- Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:

| Description | Procurement methods | Threshold | Prior review |
| --- | --- | --- | --- |
|  |  | $EU |  |
| Consultant Firms | QCBS; QBS; LCS; LBS | ≥ 200.000 | All |
|  | CQ | <200.000 | None |
|  | SSS | No threshold | All |
| Individual Consultants | IC(Advertisement) | ≥ 100.000 | All |
|  | IC(Three CVs) | < 100.000 | None |
|  | SSS | No threshold | Contract estimated to about $100,000 and above |
| All TORs are submitted for prior review |

QCBS: Quality and Cost Based Selection

QBS: Quality Based Selection

LCS: Least Cost Selection

LBS: Limited Budget Selection

CQ: Consultant Qualifications

IC: Individual Consultant

SSS: Single-source

2. Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than $200,000.00 equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.

- Any Other Special Selection Arrangements: Not applicable

2.	Consultancy Assignments with Selection Methods and Time Schedule:

| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| --- | --- | --- | --- | --- | --- | --- |
| Ref. No. | Description of Assignment | Estimated | Selection | Review | Expected | Comments |
|  |  | Cost (US$ 000) | Method | by Bank | Proposals Submission |  |
|  |  |  |  | (Prior / Post) | Date |  |
| CILSS |
| 1 | Inventory of impact studies already conducted in the area to identify the best approaches and identify available expertise | 30 000 | IC | Post | September 2015 |  |
| 2 | Best practice gathering and review | 80 000 | QC | Post | April 2015 | Ongoing process |
| 3 | Annual Financial Audit | 12 000 | LCS | Post | March 2015 | Ongoing process |
| 4 | Creation and maintenance of project web support portal | 60 000 | QC | Post | March 2015 | Ongoing process |
| 5 | Translation of the various documents | 20 000 | IC (3CV) | Post | May 2015 |  |
| 6 | Consultant to support BRICKS CILSS coordination team (Consultant recruited for 4 years: 60 000 per year) | 240 000 | IC (EOI) | Prior | March 2015 | Ongoing process |
| IUCN |
| 1 | ToRs for the establishment of an operations support pool | 9 000 | IC (3CV) | Post | April 2015 |  |
|  | assist in the implementation of the strategic communication plan | 9000 | IC ( 3 CV) |  | June 2015 |  |
| 3 | Annual Financial Audit | 7 500 | QC | Post | April 2015 |  |
| OSS |
| 1 | Consultancy to develop indicators and method of calculation | 15 000 | IC (3CV) | Post | July 2015 |  |
| 2 | Consultancy to develop a Kit for GIS and RS training | 20 000 | IC (3CV) | Post | May 2015 |  |
| 3 | Consultancy for a thematic and monographic atlas (Component 2; activity c) | 50 000 | IC (3CV) | Post | July 2015 |  |
| 4 | Support services for the development of maps of other SAWAP countries | 90 000 | IC (3CV) | Post | August 2015 |  |
| 5 | Consultancy for IT development to strengthening the Geoportal | 15 000 | IC (3CV) | Post | May 2015 |  |
| 6 | Consultancy to setting up of the data base for geospatial and no spatial data | 10 000 | IC (3CV) | Post | July 2015 |  |
| 7 | Consultancy to support M&E and GIS activities, indicator processing and reporting | 50 000 | SSS | Prior | January 2015 | Ongoing process |
| 8 | Annual Financial Audit | 5 000 | SSS | Post | December 2015 | SSS with the listener all OSS programs |

##### IV. Implementing Agency Capacity Building Activities with Time Schedule

1.	In this section the agreed Capacity Building Activities (some items could be from CPAR recommendation) are listed with time schedule:

| No. | Expected outcome / Activity Description | Estimated Cost (US$ 000) | Estimated Duration | Start Date | Comments |
| --- | --- | --- | --- | --- | --- |
| 1 | Training of Procurement Management Specialists on World Bank procurement procedures | 10 000 | Three weeks | October 2015 |  |
| 2 | Training of Financial Management Specialists on World Bank financial management procedures | 10 000 | Three weeks | October 2015 |  |

# Text boxes

98045