## Threshold
Solomon Islands
Community Governance and Grievance Management Project
Grant No. (TF#): 18206
| Prepared: 7 August 2014 | Updated: 3 August 2016 (version 4 of 2016)
By: Project Management Unit
I. Procurement thresholds and Prior Review Thresholds:
I. Procurement Methods | Procurement Thresholds | Prior Review Thresholds
Goods:
International Competitive Bidding | ≥US$500,000 | All contracts subject to prior review
Shopping | <US$500,000 | First two contracts
Direct Contracting | Meet the criteria set out in para. 3.7 of Procurement Guidelines | All contracts subject to prior review
II. Selection of Consultants:
Selection Methods | Procurement Thresholds | Prior Review Thresholds
Firms (QCBS, QBS, LCS, CQS and SSS) | In accordance with the Bank’s Consultants Guidelines | ≥US$100,000, and all SSS contracts
Individual Consultants |  | ≥US$50,000(exception made to SSS contracts, legal and procurement related assignments, where all contracts are subject to prior review)

## Goods and Consultants
Community Governance and Grievance Management Project
Revised Procurement Plan 2016 and 2017
II. Procurement Plan for Goods and Selection of Consultants:
1 | 2 | 3 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 9 | 10 | 11
Contract Ref. No. | Brief Description of Contracts | Estimate Cost | Estimate Cost | Type of Procurement | Procurement/Selection Method | Review by Bank (Prior /Post) | Contract Signing Date | Contract Completion Date (planned) | Contract amount | Contract amount | Contract Signing Date | Contract Execution Infor
|  | USD | SBD |  |  |  | (Planned) | mm/dd/yy | USD | SBD | (Actual)
|  | 1 | 7.13 |  |  |  | mm/dd/yy |  | 1 | 7.13 | mm/dd/yy
Procurement of Goods
1 | Office equipment (Lap-top, Printer/Copier/Fax Combination) | 16790 | 119712.7 | Goods | Shopping | Prior | 2015-01-01 | 2015-07-14 | 8555.3997 | 61000 | 2015-06-19 | ICT Services Ltd
1a | Provincial Equipment | 9744 | 80000 | Goods | Shopping | Post
1b | Office equipment (Lap-top, Printer/Copier/Fax Combination) | 14581 | 119713 | Goods | Shopping | Prior
2 | Office furniture (desk, chair, filing cabinet, including shipping) | 32760 | 233578.8 | Goods | Shopping | Post | 2015-02-01 | 2015-09-24 | 8016.129 | 57155 | 2015-09-16 | Universal Traders Ltd
2a | Provincial Office Furniture | 9744 | 80000 | Goods | Shopping | Post | 2017-04-01
3 | Provincial Support - Provincial Project Coordinators Activity, Communication, printing etc. | 73080 | 600000 | Goods | Shopping | Prior | 2017-03-01
3 | Communications Equipment - mobiles for PMU, Provincial govt counterparts | 18290 | 130407.7 | Goods | Shopping | Post | 2015-03-01 | 2015-10-30 | 1654.979 | 11800 | 2015-10-30 | Solomon Telekom Co Ltd
3a | Communications equipment (replacements due to damage/wear) | 6090 | 50000 | Goods | Shopping | Post | 2016-05-26 | 2016-05-26 | 729 | 5200 | 2016-05-26 | Sol Tronic
4 | Radio | 194510 | 1386856.3 | Goods | Shopping | Post | 2016-07-01 | 2016-08-31
6 | Storage unit | 65520 | 467157.6 | Goods | Shopping | Post | 2015-02-01 | 2015-10-28 | 2391.3043 | 17050 | 2015-10-28 | Universal Traders Ltd
7 | Safety equipment | 9744 | 80000 | Goods | Shopping | Post | 2017-03-01
8 | Training equipment | 5460 | 38929.8 | Goods | Shopping | Post | 2015-04-01 | 2015-10-30 | 904.6283 | 6450 | 2015-10-30 | Advanced Techologies Ltd
9 | Accounting Software | 1230 | 8769.9 | Goods | Direct Contracting | Prior | 2015-03-01 | 2015-07-14 | 720.1964 | 5135 | 2015-06-19 | Eddie Piturara
10 | Staff Development - Short trainings and workshops | 42075 | 300000 | Goods | Shopping | Post | 2017-06-01
12 | Communication/Media - Curriculum Development and printing | 24360 | 200000 | Goods | shopping | Post | 2017-04-01
| Total Procurement of Goods | 523978 | 3895125.8 | [5 empty] | 22971.6367 | 163790
Selection of Consultants
Individual Consultant
1 | Training and Curriculum Specialist (international) | 163800 | 1167894 | Consultants | IC | Prior | 2015-01-01 | 2015-10-30 | 51458 | 366895.54 | 2015-08-26 | Kate Higgins
1a | Training and Curriculum Specialist (international) - new | 163800 | 1167894 | Consultants | IC | Prior | 2017-04-01
2 | Community Outreach & Training Specialist (national) | 81900 | 583947 | Consultants | IC | Prior | 2016-12-01 | 2016-06-05 | 33884.993 | 241600 | 2015-06-05 | Koreta Kadi
| Contract extension 1 | 67769.986 | 483200 | Consultants | IC | Prior | 2016-06-05 | 2017-06-05 | 67769.986 | 483200 | 2016-05-31
3 | Project Coordinator | 196560 | 1401472.8 | Consultants | IC | Prior | 2015-01-01 | 2016-02-08 | 37183.871 | 265121 | 2015-05-04 | Joe Rausi
| Contract extension 1 | 46220.7 | 363942 | Consultants | IC | Prior | 2015-05-04 | 2016-04-04 | 46221 | 363942 | 2016-02-09
| Contract extension 2 | 47793 | 376325 | Consultants | IC | Prior | 2016-04-04 | 2016-04-18 | 47793 | 376325 | 2016-04-04
4 | Finance Specialist | 170350 | 1214595.5 | Consultants | IC | Prior | 2015-05-01 | 2016-05-16 | 28004.9088 | 199675 | 2015-05-15
4a | Finance and Procurement Specialist | 26476.1571 | 188775 | Consultants | IC | Prior | 2016-09-15 | 2016-05-23 | 26476.1571 | 188775 | 2015-09-24
5 | M&E Consultant (international) | 110570 | 788364.1 | Consultants | IC | Post | 2017-09-16 | 2016-11-21 | 22660 | 161565.8 | 2016-09-28 | Georgina Clark
5a | M&E Consultant (international) - New | 5000 | 41052 | Consultants | SS | Post | 2017-01-01 | 30-Feb-2017
6 | M&E Specialist (Local) | 72000 | 513360 | Consultants | IC | Prior | 2016-10-01 | 2017-10-10 | 29964.9369 | 213650 | 2016-10-17 | Clinton Kiko
7 | Short Term Finance and Procurement Specialist | 7200 | 51336 | Consultants | IC - SS | Prior | 2016-05-01 | 2016-08-09 | 7200 | 51336 | 2016-05-09 | Margaret Kisi
| Contract extension 1 | 4752 | 33881.76 | Consultants | IC | Prior | 2016-08-09 | 2016-10-09 | 12996.5753 | 94875 | 2016-05-09
8 | Finance and Procurement Specialist (new) | 170350 | 1214595.5 | Consultants | IC | Prior | 2016-10-01 | 2017-10-10 | 37805.0491 | 269550 | 2016-10-10 | Margaret Kisi
9 | Beneficiary Survey (6 enumerators) | 49350 | 351865.5 | Consultants | IC | Post | 2016-08-01 | 2016-11-01 | 14197.1831 | 100800 | 2016-10-10 | Enumerators
10 | Project Coordinator (replacement) | 196560 | 1401472.8 | Consultants | IC | Prior | 2017-10-16 | 2017-10-10 | 53278.6816 | 379877 | 2016-10-10 | Ravin Dhari
11 | Provincial Coordinator 1 | 8000 | 62671.87 | Consultants |  | Post | 2017-03-01
12 | Provincial Coordinator 2 | 8000 | 62671.87 | Consultants |  | Post | 2017-03-01
13 | Finance Assistance - Short Term | 5000 | 35650 | Consultants |  | Post | 2017-03-01
Total Selection of Individual Consultants
Consultant Firm
12 | External Audit | 20480 | 146022.4 | Consultants | CQS | Prior | 2016-04-01 | 2016-04-29 | 6171.108 | 44000 | 2016-04-18 | Baoro and Associates
12a | External Audit - 2016/17 | 20480 | 146022.4 | Consultants | SS | Prior | 2017-04-01 | 2017-04-01
13a | Mid-Term Sustainability - Institutional/Political | 24675 | 175932.75 | Consultants | SS | Post | 2016-08-01 | 2016-11-30 | 36036 | 255856 | 2016-11-21 | Melanie Phillips
| Extension 1 | 20000 | 142600 | Consultants | SS | Post | 2017-02-01 | 2017-03-31 | 13764 | 98137.32 | 2017-02-02
13b | Mid-Term Sustainability - Fiscal | 24675 | 175932.75 | Consultants | SS | Post | 2016-08-01 | 2016-11-30 | 19770 | 140367 | 2016-11-15 | Ben Schultz
14 | Mid Term Review | 24675 | 175932.75 | Consultants | SS | Post | 2017-06-01 | 2017-08-01
15 | Decentralisation/Analytical Work | 63824.49 | 500000 | Consultants | SS | Post | 2017-04-01 | 2017-06-01
Total Selection of Consultants
| Total Selection of Consultants (IC and Firm) |  | 1462443.05 | [5 empty] | 592635.4499 | 4295547.66
| Total Procurement | [7 empty] | 615607.0866 | 4459337.66

## Sheet3
COMMUNITY GOVERNANCE AND GRIEVANCE MANAGEMENT PROJECT
MINISTRY OF PROVINCIAL GOVERNMENT AND INSTITUTIONAL STRENGTHENING
2015 CONTRACT REGISTER
A. | PROCUREMENT OF GOODS
No | Description | Contractor Name | Contract No. | Value
SBD
Procurment of Goods
1 | Office Equipment - Laptops, Copier 3 in-one | ICT Services Ltd | 42005 | 61000
2 | MYOB Accounting Software | Eddie Piturara | 42278 | 5135
3 | Office Furniture - Desks, Chairs & Filing Cabinets | Universal Traders Ltd | 42036 | 57155
4 | Uniform – Polo Shirts | Global Digital Press | 42156 | 5328
5 | Uniform – Pants, Shoes and Socks | BOC | 42156 | 25304
6 | Storage Unit – Filing Cabinets - 2 Drawers | Universal Traders | 42186 | 17050
7 | Mobile Phones – BLU Studio G | Solomon Telekom | 42125 | 11800
8 | Training Equipment - Camera | Advanced Technology | 42248 | 6450
|  |  | Total | 189222
B. | SELECTION OF CONSULTANTS
No. | Description | Contractor Name | Contract No. | Value | Duration | Starts Date
SBD
Selection of Consultant
1 | Project Coordinator | Joe Rausi | 1 | 339258.3 | One Year | 2015-01-20
2 | Finance Officer | George Tasra | 2 | 199675 | One Year | 2015-05-18
3 | Community Outreach & Training Specialist | Koreta Kadi | 3 | 241600 | One Year | 2015-06-08
3 | Training Curriculum Specialist | Kate Higgins | 4 | 422827 | 60 Days | 2015-08-26
4 | Finance & Procurement Specialist | George Tasra | 5 | 188775 | One Year | 2015-09-24
|  |  | Total | 1392135.3