## Settings (hidden)
Prior | Version: | 1
Post | Last changed: | 2009-04-13
| Revised by: | Andrew Alexander Jacobs
Firm
Individual
Yes
No
Goods
Works
Non-Consulting Services

## General
Sample Procurement Plan
I. General
1. | Project Information
| Project Name: | Greater Beirut Water Supply Project
| Country: | Lebanon
| Project ID: | IBRD 7010
| Loan/Credit Numbers: | 7967-LE/
2. | Bank's approval date of Procurement Plan | Original:
Revision 1:
Add new revisions
3. | Date of General Procurement Notice | 2011-01-24
II. Goods, Work and Non-Consulting Services Thresholds
1. | Prior Review Threshold. Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement: [Thresholds for applicable procurement methods (not limited to the list below) will be determined by the Procurement Specialist /Procurement Accredited Staff based on the assessment of the implementing agency’s capacity.]
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Goods | 250000
| Works | 500000
| Operational Cost | 2000
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
| ICB and LIB (Goods) | ≥200,000.00
| NCB (Goods) | <200,000.00
| Shopping (Goods) | < 50,000.00
| ICB (Works) | ≥5,000,000.00
| NCB (Works) | <5,000,000.00
| Shopping (Works) | <50,000.00
2. | Prequalification. Bidders for __WTP_______ shall be prequlified in accordance with the provisions of paragraphs 2.9 and 2.10 of the Guidelines.
3. | Proposed Procedures for CDD Components (as per paragraph 3.17 of the Guidelines): Refer to the relevant CDD project implementation document approved by the Bank
4. | Reference to (if any) Project Operational/Procurement Manual:
5. | Any Other Special Procurement Arrangements:Retroactive financing between Oct 1, 2010 and Loan Signing Date (≤12 months). Expenditures will not exceed a total of USD 12 million
6. | Procurement Packages with Methods and Time Schedule: See attached "Goods and Works" sheet
III. Selection of Consultants
1. | Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Consulting Firms (Competitive) | 100000
| Individual Consultants (Competitive) | 50000
| SSS | All
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
| QCBS | Default
| QBS | TBD
| SSS | TBD
| LCS | TBD
| CQS | TBD
2. | Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than $_200,000_equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.
| Note: OPCPR list of ceilings can be found here: | http://go.worldbank.org/MKXO98RY40
3. | Any Other Special Selection Arrangements: Retroactive financing between Oct 1, 2010 and Loan Signing Date (≤12 months). Expenditures will not exceed a total of USD 12 million
4. | Consultancy Assignments with Selection Methods and Time Schedule: See attached "Consulting Services" sheet
IV. Implementing Agency Capacity Building Activities with Time Schedule: See attached "Capacity Building" sheet

## Goods and Works
Procurement Plan for Goods/Works/Non-Consulting Services
Lebanon IBRD 7010: Greater Beirut Water Supply Project 7967-LE/
** Applicable in case of Bank's prior review | [9 empty] | Prequalification
| SL No. | Package/ Reference No. | Description of Goods/ Works | Goods/ Works/ NCS | World Bank part | BMLWE part | Review by Bank (Prior/ Post) | Method of Selection | Domestic Preference (yes/no) | Prequalification (yes/no) | No Objection from Bank for Draft Prequalification documents (Date)** | No Objection from Bank for Evaluation of Prequalification Application (Date)** | Preparation of Bid Document (Date) | Bank’s No Objection to Bidding Document (Date)** | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | Contract Award Decision (Date) | Bank’s No Objection to Bid Evaulation Report and Contract Award (Date)** | Contract Signed (Date) | Contract No. | Name, City, and Country of Contractor (incl. Zip Code if US) | Completion of Contract (Date) | Remarks
Planned | 1 | BWW2-1 | Distribution Networks, Pumping Stations & Reservoirs – Zone A | Works | 2.5% | 97.5% | Prior | ICB | NO | NO |  |  | 2012-03-01 | 2012-03-22 | 2012-04-06 | 2012-05-17 | 2012-05-17 | 2012-07-10 | 2012-07-17 | 2012-08-21 |  | Cooperativa Edile Appennino scarl | 2015-11-30
Revised | [22 empty] | 2017-02-01
Actual | [12 empty] | 2013-09-02 | 2014-02-03 | 2014-02-20 | 2014-04-10 | 2014-04-10 | 2014-05-19 | 2014-06-04 | 2014-08-06
Planned | 2 | BWW2-2 | Distribution Networks, Pumping Stations & Reservoirs – Zone B | Works | 2.5% | 97.5% | Prior | ICB | NO | NO |  |  | 2012-02-13 | 2012-02-27 | 2012-03-13 | 2012-04-23 | 2012-04-23 | 2012-06-04 | 2012-06-18 | 2012-07-23 | 7018/2014 | JCC/WARD | 2015-12-30
Revised | [22 empty] | 2016-08-05
Actual | [12 empty] | 2013-09-02 | 2014-02-03 | 2014-03-13 | 2014-05-06 | 2014-05-06 | 2014-06-02 | 2014-07-09 | 2014-08-06
Planned | 3 | BWW2-3 | Distribution Networks, Pumping Stations & Reservoirs – Zone C | Works | 2.5% | 97.5% | Prior | ICB | NO | NO |  |  | 2012-02-13 | 2012-02-27 | 2012-03-20 | 2012-04-30 | 2012-04-30 | 2012-06-14 | 2012-06-28 | 2012-08-02 | 605/2014 | VODOKANALPROEKT – METALPROEKT INGENEERING AD, Bulgaria | 2015-05-21
Revised | [22 empty] | 2016-07-04
Actual | [12 empty] | 2013-02-13 | 2013-07-02 | 2013-07-25 | 2013-09-24 | 2013-09-24 | 2013-12-24 | 2014-01-10 | 2014-01-28
Planned | 4 | BWW2-4 | Distribution Networks, Pumping Stations & Reservoirs – Zone D | Works | 2.5% | 97.5% | Prior | ICB | NO | NO |  |  | 2012-03-01 | 2012-03-22 | 2012-06-13 | 2012-05-24 | 2012-05-24 | 2012-07-17 | 2012-07-24 | 2012-08-28 |  |  | 2015-02-27
Revised | [13 empty] | 2014-10-03 | 2014-10-17 | 2014-12-10 | 2014-12-10 | 2015-01-15 | 2015-01-27 | 2015-02-24 |  |  | 2017-02-23
Actual | [12 empty] | 2013-02-13: 2013-12-20
Planned | 5 | BWW1-A | Tunnel & Transfer lines | Works | 100% | 0% | Prior | ICB | NO | YES | 2011-01-28 | 2011-05-13 | 2011-06-03 | 2011-06-10 | 2011-06-07 | 2011-08-01 | 2011-08-01 | 2011-12-05 | 2011-12-12 | 2012-01-09 |  |  | 2014-12-24
Revised | [12 empty] | 2013-12-24: 2014-10-02; 2014-01-10: 2014-10-09; 2014-01-28: 2014-11-09 |  |  | 2018-09-09
Actual | [10 empty] | 2011-11-21 | 2013-01-17 | 2013-02-28 | 2013-07-17 | 2013-09-24 | 2014-05-12 | 2014-05-12
Planned | 6 | BWW1-C | Reservoirs & Transmission lines | Works | 100% | 0% | Prior | ICB | NO | No |  |  | 2011-08-03 | 2011-08-10 | 2011-08-11 | 2011-09-08 | 2011-09-08 | 2011-12-07 | 2011-12-14 | 2011-12-29 |  |  | 2014-12-24
Revised | [13 empty] | 2015-02-13 | 2015-02-16 | 2015-03-16 | 2015-03-16 | 2015-06-12 | 2015-06-19 | 2015-07-06 |  |  | 2017-07-04
Actual | [12 empty] | 2011-08-03: 2014-08-01
Planned | 7 | BWW1-B | Wardanieh Water Treatment Plant | Works | 5% | 95% | Prior | ICB | NO | YES | 2011-05-31 | 2011-08-09 | 2011-08-30 | 2011-09-27 | 2011-09-28 | 2011-11-08 | 2011-11-08 | 2012-01-31 | 2012-02-07 | 2012-02-22 |  |  | 2014-02-18
Revised | [11 empty] | 2014-12-23 | 2014-12-23 | 2015-01-26 | 2015-02-23 | 2015-07-24 | 2015-07-24 | 2016-01-22 | 2016-01-29 | 2016-02-15 |  |  | 2019-02-08
Actual | [10 empty] | 2014-04-28
Planned | 8 | BWW2-5 | Meters | Works | 5% | 95% | Prior | ICB | NO | No
Revised
Actual
Planned | 9 | BWW3-2-4 | Fax machine Shopping | Goods | 66% | 34% | Post | Shopping | NO | No |  | 2016-01-22: 2014-03-03; 2016-02-15: 2014-03-18 | 128A | Sacotel (Badaro - Lebanon) | 2014-03-25 | 1 fax machine
Revised
Actual | [11 empty] | 2016-01-22: 2014-04-02; 2016-02-15: 2014-04-02 |  |  | 2014-04-02
Planned | 10 | BWW3-2-5 | Computers Shopping | Goods | 66% | 34% | Post | Shopping | NO | No |  | 2016-01-22: 2014-03-03; 2016-02-15: 2014-03-18 |  |  | 2014-03-25 | 6 computers/Laptops, printer
Revised | [11 empty] | 2016-01-22: 2014-08-01; 2016-02-15: 2014-10-01 |  |  | 2014-10-08
Actual | [11 empty] | 2016-01-22: 2014-09-11
Planned | 10 | BWW3-2-14 | Photocopy machine Multi feeder | Goods | 66% | 34% | Post | Shopping | NO | No |  | 2016-01-22: 2015-02-12; 2016-02-15: 2015-02-26 |  |  | 2015-03-26 | 6 computers/Laptops, printer
Revised
Actual

## Consulting Services
Procurement Plan for Consultant Services
Lebanon IBRD 7010: Greater Beirut Water Supply Project 7967-LE/
** Applicable in case of Bank's prior review | [9 empty] | In some contracts, one or more of these approvals may be contained in one Bank communication.
| SL No. | Package/ Reference No. | Description of Services | Review by Bank (Prior/ Post) | Type of Consultant (Firm/ Individual) | Method of Selection | Advertising for Short listing (Date) | TOR/Shortlist to be Finalised (Date) | RFP Final Draft to be forwarded to the Bank (Date) | No Objection from Bank for TOR (Date)** | No Objection from Bank for Shortlist (Date)** | No Objection from Bank for Final RFP (Date)** | RFP Issued (Date) | Proposal Submission Deadline (Date) | No Objection by the Bank to the Technical Evaluation Report (Date)** | No Objection by the Bank (Technical/ #Combined/ Draft Contract/ Final Contract) (Date)** | Contract Signed (Date) | Name, City, and Country of Contractor (incl. Zip Code if US) | Services Completion (Date) | Remarks
Planned | 01 | BWC1-A | Supervision of Tunnel & Transfer lines |  |  |  | 2011-04-03 | 2011-05-05 | 2011-05-05 | 2011-06-08 | 2011-05-12 | 2011-06-08 | 2011-06-09 | 2011-07-06 | 2011-08-03 | 2011-08-24 |  |  | 2015-01-23
Revised |  |  |  | Prior | Firm | QCBS | [9 empty] | 2014-10-01 |  |  | 2018-10-09
Actual | [6 empty] | 2011-09-09 | 2011-12-27 | 2012-07-12 | 2013-03-15 | 2012-01-22 | 2013-03-15 | 2013-05-29 | 2013-07-05 | 2014-04-15
Planned | 02 | BWC1-B | Supervision of Wardanieh Water Treatment Plant |  |  |  | 2011-08-30 | 2011-10-04 | 2011-10-05 | 2011-10-19 | 2011-10-18 | 2011-10-19 | 2011-10-20 | 2011-11-15 | 2011-12-13 | 2012-01-10 |  |  | 2014-03-18
Revised |  |  |  | Prior | Firm | QCBS | 2014-11-17 | 2014-12-30 | 2014-12-16 | 2015-01-06 | 2015-01-06 | 2015-01-06 | 2015-01-07 | 2015-03-11 | 2015-05-02 | 2015-07-01 |  |  | 2019-03-10
Actual
Planned | 03 | BWC1-C | Supervision of Reservoirs & Transmission lines |  |  |  | 2011-05-17 | 2011-07-14 | 2011-08-04 | 2011-08-10 | 2011-08-01 | 2011-08-10 | 2011-08-11 | 2011-09-07 | 2011-10-05 | 2011-10-26 |  |  | 2015-01-23
Revised |  |  |  | Prior | Firm | QCBS | [9 empty] | 2014-10-01 |  |  | 2017-08-03
Actual | [6 empty] | 2011-09-09 | 2011-12-27 | 2012-07-12 | 2013-03-15 | 2012-01-22 | 2013-03-15 | 2013-05-29 | 2013-07-05 | 2014-04-15
Planned | 04 | BWC2-1 | Water Distribution Networks Design & Supervision | [13 empty] | 2012-03-28 | DAR AL HANDASAH NAZIH TALEB & PARTNERS SAFEGE JV | 2016-01-29
Revised |  |  |  | Prior | Firm | QCBS | [12 empty] | 2017-03-05
Actual | [6 empty] | 2011-02-10 | 2011-08-04 | 2011-08-12 | 2011-09-07 | 2011-08-19 | 2011-09-07 | 2011-09-08 | 2011-10-12 | 2011-11-04 | 2011-12-08
Planned | 05 | BWC2-2 | Supervision of Meters
Revised |  |  |  | Prior | Firm | QCBS
Actual
Planned | 06 | BWC3-2 | BMLWE External Audit | [13 empty] | 2011-11-12 | USAMAH TABBARAH & CO Auditors & Consultants - NEXIA INTERNATIONAL, Beirut, Lebanon | 2011-11-18
Revised |  |  |  | Prior | Firm | LC | [9 empty] | retroactive
Actual | [6 empty] | 2011-05-31 | 2011-03-14 | 2011-04-14 | 2011-04-16 | 2011-04-16 | 2011-04-16 | 2011-09-05 | 2011-09-26 | 2011-10-05 | 2014-02-04 |  |  | 2012-02-12
Planned | 07 | BWC3-2-1 | PROJECT External Audit 2014 |  |  |  | 2014-03-06 | 2014-02-10 | 2014-02-10 | 2014-02-20 | 2014-03-25 | 2014-02-20 | 2014-04-03 | 2014-04-22 | 2014-05-02 | 2014-05-09 | 2014-06-03 |  | 2014-06-14
Revised |  |  |  | Prior | Firm | LC | [12 empty] | 2014-06-30
Actual | [7 empty] | 2014-02-10 | 2014-02-10 | 2014-05-02 | 2014-05-02 | 2014-05-02 | 2014-05-19 | 2014-06-02 | 2014-06-03 | 2014-06-11
Planned | 08 | BWC1-1 | Other Consultancies
Revised |  |  |  | Prior | Firm | QCBS-IC
Actual
Planned | 07 | BWC3-2-2 | PROJECT External Audit (4 years) |  |  |  |  | 2015-01-15 | 2015-01-15 | 2015-01-22 | 2015-01-15 | 2015-01-22 | 2015-02-05 | 2015-02-26 | 2015-03-05 | 2015-03-19 |  |  | 2015-04-30
Revised |  |  |  | Prior | Firm | LC
Actual

## Operational Cost
Procurement Plan for Goods/Works/Non-Consulting Services
Lebanon IBRD 7010: Greater Beirut Water Supply Project 7967-LE/
** Applicable in case of Bank's prior review | [7 empty] | Prequalification
| SL No. | Package/ Reference No. | Description of Goods/ Works | Goods/ Works/ NCS | Review by Bank (Prior/ Post) | Method of Selection | Domestic Preference (yes/no) | Prequalification (yes/no) | No Objection from Bank for Draft Prequalification documents (Date)** | No Objection from Bank for Evaluation of Prequalification Application (Date)** | Preparation of Bid Document (Date) | Bank’s No Objection to Bidding Document (Date)** | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | Contract Award Decision (Date) | Bank’s No Objection to Bid Evaulation Report and Contract Award (Date)** | Contract Signed (Date) | Contract No. | Name, City, and Country of Contractor (incl. Zip Code if US) | Completion of Contract (Date) | Remarks
Planned | 01 | BWW3-2-6 | Stationary Shopping (2014) | Goods | Post | Shopping | NO | No | [7 empty] | 2014-03-03 |  | 2014-03-18 | 191A | Librairie Halim (Dora - Lebanon) | 2014-03-25
Revised | [15 empty] | 2014-05-03
Actual | [15 empty] | 2014-05-15 |  | 2014-04-15 |  |  | 2014-05-23
Planned | 02 | BWW3-2-7 | Consumables Shopping (2014) | Goods | Post | Single Source | NO | No | [7 empty] | 2014-03-03 |  | 2014-03-18 |  |  | 2014-12-31 | Office daily consumables
Revised | [15 empty] | 2014-08-01 |  | 2014-08-15 |  |  | 2014-08-22
Actual
Planned | 03 | BWW3-2-8 | Paper Shredder Shopping | Goods | Post | Shopping | NO | No | [7 empty] | 2014-03-03 |  | 2014-03-18 |  |  | 2014-03-25
Revised | [15 empty] | 2014-08-01 |  | 2014-08-15 |  |  | 2014-08-22
Actual
Planned | 04 | BWW3-2-9 | Insurance for 2 vehicules (2014) | Goods | Post | Shopping | NO | No | [7 empty] | 2014-03-03 |  | 2014-03-18 |  |  | 2014-03-25
Revised | [15 empty] | 2014-08-01 |  | 2014-08-15 |  |  | 2014-08-22
Actual
Planned | 05 | BWW3-2-10 | Fuel oil for 2 vehicules (2014) | Goods | Post | Single Source | NO | No | [7 empty] | 2014-03-03 |  | 2014-03-18 |  |  | 2014-12-31
Revised | [15 empty] | 2014-08-01 |  | 2014-08-15 |  |  | 2014-08-22
Actual
Planned | 06 | BWW3-2-11 | Stationary Shopping (2015) | Goods | Post | Shopping | NO | No | [7 empty] | 2015-01-30 |  | 2015-02-13
Revised
Actual
Planned | 07 | BWW3-2-12 | Fuel oil for 2 vehicules (2015) | Goods | Post | Single Source | NO | No | [7 empty] | 2014-03-03 |  | 2014-03-18 |  |  | 2014-12-31
Revised | [15 empty] | 2014-08-01 |  | 2014-08-15 |  |  | 2014-08-22
Actual
Planned | 08 | BWW3-2-13 | Consumables Shopping (2015) | Goods | Post | Single Source | NO | No | [7 empty] | 2014-03-03 |  | 2014-03-18 |  |  | 2014-12-31 | Office daily consumables
Revised | [15 empty] | 2014-08-01 |  | 2014-08-15 |  |  | 2014-08-22
Actual
Planned | 09 | BWW3-2-14 | Maintenance for office equipments | Goods | Post | Single Source | NO | No | [13 empty] | Photocopy, coffee, fax, …
Revised
Actual
Formulas:
Contract Signed (Date) = [Contract Award Decision (Date)]+14
Completion of Contract (Date) = [Contract Signed (Date)]+7

## PMU
Procurement Plan for Consultant Services
Lebanon IBRD 7010: Greater Beirut Water Supply Project 7967-LE/
** Applicable in case of Bank's prior review
2014-09-30 | SL No. | Package/ Reference No. | Description of Services | Estimated Cost | Review by Bank (Prior/ Post) | Type of Consultant (Firm/ Individual) | Method of Selection | Contract Signed (Date) | Contract Start (Date) | Name of Consultant | Services Completion (Date) | Remarks
Actual | 1-1 | BWC3-1-1-1 | Project Coordinator |  | Prior | Individual | IC | 2010-12-24 | 2010-12-01 | Randa Daher | 2011-11-30
Actual | 1-2 | BWC3-1-1-2 | [5 empty] | 2012-01-01 | 2011-12-01 |  | 2012-11-30 | Extension in new contract form
Actual | 1-3 | BWC3-1-1-3 | [5 empty] | 2013-01-01 | 2012-12-01 |  | 2013-11-30 | Extension in new contract form
Planned |  | BWC3-1-1-3-1 | [5 empty] | 2013-12-01 | 2013-12-01 |  | 2013-12-31 | Addendum
Actual | 1-4 | BWC3-1-1-4 | [5 empty] | 2014-01-23 | 2014-01-01 |  | 2014-12-31 | Contract extension
Actual | 2-1 | BWC3-1-2-1 | Project Operations Advisor |  | Prior | Individual | IC | 2012-06-01 | 2012-06-01 | Randa Nemer | 2013-06-01
Actual | 2-2 | BWC3-1-2-2 | [5 empty] | 2013-06-01 | 2013-06-01 |  | 2014-06-01 | Contract extension
Actual | 2-3 | BWC3-1-2-3 | [5 empty] | 2014-06-01 | 2014-06-01 |  | 2014-12-31 | Contract extension
Actual | 3-1 | BWC1-4-1-1 | Project Engineer |  | Prior | Individual | IC | 2011-03-01 | 2011-03-01 | Elie Moussalli | 2012-01-30
Actual | 3-2 | BWC1-4-1-2 | [5 empty] | 2012-02-01 | 2012-02-01 |  | 2012-12-31 | Contract extension
Actual | 3-3 | BWC1-4-1-3 | [5 empty] | 2013-01-01 | 2013-01-01 |  | 2013-11-30 | Contract extension
Actual | 3-4 | BWC1-4-1-4 | [5 empty] | 2013-12-01 | 2013-12-01 |  | 2014-10-30 | Contract extension
Actual | 4-1 | BWC3-1-4-1 | Procurement Specialist |  | Prior | Individual | IC | 2010-12-24 | 2010-11-01 | Bassam Nasrallah | 2011-10-31
Actual | 4-2 | BWC3-1-4-2 | [5 empty] | 2012-01-01 | 2011-11-01 |  | 2012-10-31 | Extension in new contract form
Actual | 4-3 | BWC3-1-4-3 | [5 empty] | 2013-01-01 | 2012-11-01 |  | 2013-10-31 | Extension in new contract form
Planned |  | BWC3-1-4-3-1 | [5 empty] | 2013-11-01 | 2013-11-01 |  | 2013-12-31 | Addendum
Actual | 4-4 | BWC3-1-4-4 | [5 empty] | 2014-01-23 | 2014-01-01 |  | 2014-12-31 | Contract extension
Actual | 5-1 | BWC3-1-5-1 | Financial Manager |  | Prior | Individual | IC | 2010-12-24 | 2010-11-01 | Nizar Najem | 2011-10-31
Actual | 5-2 | BWC3-1-5-2 | [5 empty] | 2012-01-01 | 2011-11-01 |  | 2012-10-31 | Extension in new contract form
Actual | 5-3 | BWC3-1-5-3 | [5 empty] | 2013-01-01 | 2012-11-01 |  | 2013-10-31 | Extension in new contract form
Planned |  | BWC3-1-5-3-1 | [5 empty] | 2013-11-01 | 2013-11-01 |  | 2013-12-31 | Addendum
Actual | 5-4 | BWC3-1-5-4 | [5 empty] | 2014-01-23 | 2014-01-01 |  | 2014-12-31 | Contract extension
Actual | 6-1 | BWC3-1-6-1 | Administrative Assistant |  | Prior | Individual | IC | 2012-03-30 | 2012-03-30 | Farah Farraj | 2013-03-29
Actual | 6-2 | BWC3-1-6-2 | [5 empty] | 2013-03-30 | 2013-03-30 |  | 2014-03-29 | Extension in new contract form
Actual | 6-3 | BWC3-1-6-3 | [5 empty] | 2014-03-30 | 2014-03-30 |  | 2014-12-31 | Contract extension
Actual | 7-1 | BWC3-1-7-1 | Electro Mechanical Eng |  | Prior | Individual | IC | 2012-03-01 | 2012-03-30 | Mazen Hammoud | 2013-03-29
Actual | 7-2 | BWC3-1-7-2 | [5 empty] | 2013-03-01 | 2013-03-30 |  | 2014-03-29 | Extension in new contract form
Actual | 7-3 | BWC3-1-7-3 | [5 empty] | 2014-03-30 | 2014-03-30 |  | 2014-12-31 | Contract extension
Actual | 8-1 | BWC3-1-8-1 | Monitoring & Evaluation |  | Prior | Individual | IC | 2012-03-01 | 2012-03-01 | Joseph deeb | 2013-02-28
Actual | 8-2 | BWC3-1-8-2 | [5 empty] | 2013-03-01 | 2013-03-01 |  | 2014-02-28 | Extension in new contract form
Actual | 8-3 | BWC3-1-8-3 | [5 empty] | 2014-03-01 | 2014-03-01 |  | 2014-12-31 | Contract extension
Actual | 9-1 | BWC3-1-9-1 | Civil/Water Engineer |  | Prior | Individual | IC | 2012-03-01 | 2012-03-30 | Farid Maalouf | 2013-03-29
Actual | 9-2 | BWC3-1-9-2 | [5 empty] | 2013-03-01 | 2013-03-30 |  | 2014-01-31 | Extension in new contract form
Actual | 10-1 | BWC3-1-10-1 | Accountant |  | Prior | Individual | IC | 2012-03-01 | 2012-03-01 | Patrick Khoury | 2013-02-28
Actual | 10-2 | BWC3-1-10-2 | [5 empty] | 2013-03-01 | 2013-03-01 |  | 2014-02-28 | Extension in new contract form
Actual | 10-3 | BWC3-1-10-3 | [5 empty] | 2014-03-01 | 2014-03-01 |  | 2014-12-31 | Contract extension
Actual | 11-1 | BWC3-1-11-1 | Civil Engineer |  | Prior | Individual | IC | 2012-05-01 | 2012-05-01 | Michel Youssel | 2013-04-30
Actual | 11-2 | BWC3-1-11-2 | [5 empty] | 2013-05-01 | 2013-05-01 |  | 2014-04-30 | Extension in new contract form
Actual | 11-3 | BWC3-1-11-3 | [5 empty] | 2014-05-01 | 2014-05-01 |  | 2014-12-31 | Contract extension
Actual | 12-1 | BWC3-1-12-1 | Admin Assistant MoEW |  | Prior | Individual | IC | 2012-05-01 | 2012-05-01 | Ziad Najjar | 2013-04-30
Actual | 12-2 | BWC3-1-12-2 | [5 empty] | 2013-05-01 | 2013-05-01 |  | 2014-04-30 | Extension in new contract form
Actual | 12-3 | BWC3-1-12-3 | [5 empty] | 2014-05-01 | 2014-05-01 |  | 2014-12-31 | Contract extension
Actual | 13-1 | BWC3-1-13-1 | Admin Assistant |  | Prior | Individual | IC | 2010-12-24 | 2010-12-24 | Rolly Dagher | 2011-05-13
Actual | 14-1 | BWC3-1-14-1 | Project Legal Advisor |  | Prior | Individual | IC | 2012-06-01 | 2012-06-01 | Walid Dagher | 2013-05-31
Actual | 14-2 | BWC3-1-14-2 | [5 empty] | 2013-06-01 | 2013-06-01 |  | 2014-05-31 | Extension in new contract form
Actual | 14-3 | BWC3-1-14-3 | [5 empty] | 2014-06-01 | 2014-06-01 |  | 2014-12-31 | Contract extension
Actual | 15-1 | BWC3-1-15-1 | Water Engineer |  | Prior | Individual | IC | 2012-03-01 | 2012-03-30 | Ahmad El Hajj | 2013-03-29
Actual | 15-2 | BWC3-1-15-2 | [5 empty] | 2013-03-01 | 2013-03-30 |  | 2014-03-29 | Extension in new contract form
Actual | 15-3 | BWC3-1-15-3 | [5 empty] | 2014-03-30 | 2014-03-30 |  | 2014-12-31 | Contract extension
Actual | 16-1 | BWC3-1-16-1 | ESIA Specialist |  | Prior | Individual | IC | 2012-10-01 | 2012-10-01 | Noushig Kaloustian | 2013-09-30
Planned | 16-2 | BWC3-1-16-2 | [5 empty] | 2013-10-01 | 2013-10-01 |  | 2014-12-31 | Extension in new contract form
Actual | 17-1 | BWC1-4-2-1 | Finacial Specialist |  | Prior | Individual | IC | 2013-10-03 | 2013-09-15 | Bruna Sehnaoui | 2014-08-14
Formulas:
Services Completion (Date) = [Contract Start (Date)]+365
Services Completion (Date) = [Contract Start (Date)]+365-30
Contract Start (Date) = [Contract Signed (Date)]

## Capacity Building
Capacity Building Activities
SL No. | Package/ Reference No. | Expected Outcome/ Activity Description | Estimated Duration | Start Date | Completion Date | Comments
1 | BWC3-2-1-1 | Procurement for Works for WB financed projects | 4 days | 2011-05-03 | 2011-05-06 | Bassam Nasrallah training