## ASAT2-REV-7
MUNICIPAL SERVICES PROJECT - ADDITIONAL FINANCING - ASAT PROCUREMENT PLAN (Rev. 7, October 12, 2012 )
1 | 2 | 2 | 2' | 3 | 4 |  | 5 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Pack. No. | Description |  | Tanımlar | Type | No. of the Contract | Estimated Cost (Euro) |  |  | No. of packages | Proc. Method | Review by Bank Prior/Post | Invitation Date / Advertisement for EOI Date | Expected Bid-Open. Date/Proposal Submission Date | Contract Award Date | Start Date | Contract completion date
[6 empty] | Total | BF | NBF
| WORKS AND PROCUREMENT OF GOODS (INCLUDING SUPPLY & INSTALLATION) | İNŞAAT İŞLERİ (TEMİN VE MONTAJ DAHİL) | İNŞAAT İŞLERİ VE MAL ALIMI (TEMİN VE MONTAJ DAHİL)
1 | Construction of Water Network and House Connections in Kepez, Muratpaşa,Aksu, Döşemealtı Municipalities and Kızıllı, Kurşunlu, Topallı, Fettahlı Districts | Kanalizasyon Şebekesi İnşaatı (1. kademe) ve Pompa İstasyonu ve Yağmursuyu Drenajı | Kepez, Muratpaşa, Aksu,Döşemealtı İlçe Belediyeleri ile Kızıllı, Kurşunlui Topallı, Fettahlı Bölgeleri İçmesuyu Şebeke ve Evsel Bağlantılar İnşaatı işi | Works | ASAT2-W1 | 4095300.1477 | 4095300.1477 | 0 | 1 | NCB | POST | 28 February 2012 | 30 March 2012 | 2012-05-14 | 2012-05-21 | January 2014
2 | ASAT Water Facilities Rehabilitation Works |  | ASAT İçmesuyu Tesisleri Rehabilitasyon İşleri | Works | ASAT2-W2 | 7480000 | 7480000 | 0 | 1 | NCB | POST | November 2012 | December 2012 | February 2013 | February 2013 | October 2014
3 | Construction of Sewerage Network in Muratpaşa, Konyaaltı, Kepez Districts (Total contract amount: EUR 11,958,891, EUR 655,853 is to be financed from MSP, EUR 11,303,038 to be financed from MSP-AF) |  | Muratpaşa, Konyaaltı, Kepez Bölgeleri Kanalizasyon Şebeke İnşaatı İşi | Works | ASAT2-W3 | 11303038.4951 | 11303038.4951 | 0 | 1 | ICB | PRIOR | 27 June 2012 | 16 August 2012 | October 2012 | October 2012 | October 2014
4 | Construction of Sewerage Network - II CANCELLED |  | Atıksu Şebekesi İnşaatı - II İPTAL | Works | ASAT2-W4
5 | Construction of Sewerage Network - III CANCELLED |  | Atıksu Şebeke İnşaatı - III İPTAL | Works | ASAT2-W5
6 | Construction of Sewerage Network and Collectors in Kepez, Döşemealtı and Konyaaltı Districts |  | Kepez, Döşemealtı ve Konyaaltı Bölgelerinde Kanalizasyon Şebeke ve Kollektör İnşaatı İşi | Works | ASAT2-W6 | 8157753.3229 | 8157753.3229 | 0 | 1 | ICB | PRIOR | 16 April 2012 | 2012-05-30 | 23 July 2012 | 27 July 2012 | July 2014
7 | Construction of Hurma Environmental Protection and Controlling Laboratory Building |  | Hurma Çevre Koruma ve Kontrol Laboratuvarı Binası İnşaatı İşi | Works | ASAT2-W9 | 1531765.268 | 1531765.268 | 0 | 1 | NCB | POST | 11 April 2012 | 2012-05-15 | June 2012 | 05 July 2012 | 04 July 2013
8 | Supply and Instalation of Electronic Security Support System for the Facilities of ASAT |  | ASAT Tesisleri için Elektronik Güvenlik Destek Sistemini Temin ve Kurulum İşi | S+I | ASAT2 -SI1 | 3000000 | 3000000 | 0 | 1 | ICB | PRIOR | November 2012 | December 2012 | January 2013 | February 2013 | February 2014
9 | Design,Supply and Installation of PTC Systems in Hurma WWTP |  | Hurma AAT için PTC Sistemleri Tasarımı, Temini ve Kurulumu İşi | S+I | ASAT2-A30 | 3500000 | 3500000 | 0 | 1 | ICB | PRIOR | June 2012 | July 2012 | August 2012 | August 2012 | August 2013
10 | Procurement of 3 Nos. of Watering Truck |  | 3 adet Su Tankeri Temini | Goods | ASAT2- G2 (ASAT-G12) | The Subject Contract has been constituted and signed as to be financed from both MSP and MSP Additional Financing. But in accordance with the allocation of 900.000 € in the Municipal Services Project I- it has decided to be cancelled from the MSP-Additional Financing and inserted to the MSP-I Procurement Plan Combined Rev. 9.
11 | Procuremnet of Cold Water Meters |  | Soğuk su Sayaçları Temini | Goods | ASAT2 - G4 | This Package has been shifted to MSP Procurement Plan rev. 10
12 | Procurement of truck type multi purpose heavy machine with telescopic boom |  | Kamyon Tipi Teleskopik Bomlu Çok Amaçlı İş Makinası Temini | Goods | ASAT2-G3 | 700000 | 700000 | 0 | 1 | NCB | POST | November 2012 | December 2012 | January 2013 | February 2013 | August 2013
13 | Procurement of Asphalt Paving Machine for repair works - CANCELLED |  | Tamirat İşleri İçin Asfalt Serme Makinası Temini | Goods | ASAT2-G5
14 | Lot 1-Procurement of Water Leakage Detection Vehicle and Lot 2- Procurement of Water Leakage Detection Equipment |  | Lot 1-Su Kaçak Arama Aracı Alımı ve Lot 2- Su Kaçak Arama Ekipmanları Alımı | Goods | ASAT2-G6 | 365221.8 | 365221.8 | 0 | 1 | NCB | POST | 12 May 2011 | 15 June 2011 | 13 September 2011 | 13 September 2011 | January 2012
15 | Procurement of Hot Mix Bituminous Asphalt |  | Bitümlü Sıcak Karışım Asfalt Alımı | Goods | ASAT2-G7 | 570279.5152 | 570279.5152 | 0 | 1 | NCB | POST | 19 June 2012 | 01 August 2012 | September 2012 | October 2012 | October 2013
16 | Procurement of 1500 Nos of Sphero Manhole Covers (LOT1) and 2000 Nos of Composite or Silikopolimer Manhole Covers (LOT2) |  | 1500 Adet Sfero Döküm Kanalizasyon Baca Kapağı (LOT1) ve 2000 Adet Kompozit veya Silikopolimer Kanalizasyon Baca Kapağı Alımı (LOT2) | Goods | ASAT -G10 | 236042.8 | 236042.8 | 0 | 1 (with 2 Lots) | NCB | POST | 22 September 2010 | 24 November 2010 | Lot 1- 31Jan. 2011 - Lot 2- 20 Jan. 2011 | January 2011 | Lot1- April 2011 Lot2- June 2011
17 | Procurement of Pressure Reducing Control Valves and Strainers (TRANSFERED FROM THE PROCUREMENT PLAN FOR MSP I) | Basınç Düşürücü Kontrol Vanaları ve Pislik Tutucular Alımı (İPTAL EDİLDİ VE BHP II EK FİNANSMANA AİT SATIN ALMA PLANINA AKTARILDI) | Basınç Düşürücü Kontrol Vanaları ve Pislik Tutucular Alımı ( BHP I SATIN ALMA PLANINDAN AKTARILDI) | Goods | ASAT-G14 | 79000 | 79000 | 0 | 1 | SHOOPING | POST | November 2012 | December 2012 | January 2013 | January 2013 | July 2013
| Works- Goods- Supply and Installation Sub-Total | İnşaat İşleri Alt-Toplam | Yapım işi-Mal Alımı-Temin ve Montaj Alt-Toplam |  |  | 41018401.3489 | 41018401.3489 | 0
| CONSULTANT'S SERVICES AND TRAINING | DANIŞMANLIK HİZMETLERİ VE EĞİTİM | DANIŞMANLIK HİZMETLERİ VE EĞİTİM
1 | Preparation of EMP | ÇYP'nin Hazırlanması | ÇED ve ÇYP'nin Hazırlanması | C | IST-C1 |  |  |  | 6: 1; 7: LPM
1 | Preparation of Final Designs and Bidding Documents and Construction Supervision Services | Uygulama Projelerinin İncelenmesi, İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | Kesin Projelerin ve İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | C | ASAT2-C1-A ASAT2-C1-B | 2769654 | 2769654 | 0 | 1 | QCBS | PRIOR | July 2010 | 14 March 2011 | 25 August 2011 | September 2011 | September 2014
| Consultancy Services Sub-Total | Müşavirlik Alt-Toplam | Müşavirlik Alt-Toplam |  |  | 2769654 | 2769654 | 0
| PHYSICAL AND PRICE CONTINGENCY Sub- Total |  | Beklenmeyen Giderler Alt-Toplam |  |  | 3920374.6511 | 3920374.6511
| TOTAL | TOPLAM | TOPLAM |  |  | 47708430 | 47708430 | 0
Legend:
GOODS
ICB= | International Competitive Bidding (in accordance with section 2 of the Guidelines): For contracts valued at or more than Euro 750,000
NCB= | National Competitive Bidding (in accordance with section 3.3 of the Guidelines) : For contracts valued less than Euro 750,000
DC= | Direct Contracting (in accordance with section 3.6 of the Guidelines)
SH= | Shopping (in accordance with section 3.5 of the Guidelines)
For small works contracts valued at or less than Euro80,000
For provision of logistic services for workshops, seminars and etc: Euro80,000
For goods contracts valued at or less than Euro 80,000
Prior Review | All ICB contracts.
Technical Services for provision of logistic services for workshops, seminars and etc.: The first contract regardless of the value.
WORKS
ICB= | International Competitive Bidding (in accordance with section 2 of the Guidelines) : For contracts valued at or more than Euro 7,500,000
NCB= | National Competitive Bidding (in accordance with section 3.3 of the Guidelines) : For contracts valued less than Euro 7,500,000
Prior Review | All ICB contracts.
CONSULTANT'S SERVICES
QCBS = | Quality and Cost-based Selection (in accordance with sections 2.1 - 2.28 of the Consultant's Guidelines)
QBS= | Quality Based Selection (in accordance with sections 3.2-4 of the Consultant's Guidelines)
CQ= | Consultants Qualifications (in accordance with sections 3.7-8 of the Consultant's Guidelines)
LCS= | Least Cost Selection (in accordance with sections 3.6 of the Consultant's Guidelines)
SS= | Single Source Selection (in accordance with section 3.9 -13 of the Consultant's Guidelines)
IC= | Individual Consultant (in accordance with section V of the Consultant's Guidelines)
Prior Review | For firms: All contracts equal to Euro 250,000 or more and all SSS contracts.
For individual consultants: All contracts equal to Euro75,000 equivalent or more and all SSS contracts.
Note on B8: wb377902: For the sake of simplicity, we removed the footnote and inserted the information here
Note on M14: wb377902: We have not received and reviewed the BER, please do not modify this row for the dates

## ASAT2-REV-6 22 May 2012
MUNICIPAL SERVICES PROJECT - ADDITIONAL FINANCING - ASAT PROCUREMENT PLAN (Rev. 6 - May 22, 2012)
1 | 2 | 2 | 2' | 3 | 4 |  | 5 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Pack. No. | Description |  | Tanımlar | Type | No. of the Contract | Estimated Cost (Euro) |  |  | No. of packages | Proc. Method | Review by Bank Prior/Post | Invitation Date / Advertisement for EOI Date | Expected Bid-Open. Date/Proposal Submission Date | Contract Award Date | Start Date | Contract completion date
[6 empty] | Total | BF | NBF
| WORKS AND PROCUREMENT OF GOODS (INCLUDING SUPPLY & INSTALLATION) | İNŞAAT İŞLERİ (TEMİN VE MONTAJ DAHİL) | İNŞAAT İŞLERİ VE MAL ALIMI (TEMİN VE MONTAJ DAHİL)
1 | Construction of Water Network and House Connections in Kepez, Muratpaşa,Aksu, Döşemealtı Municipalities and Kızıllı, Kurşunlu, Topallı, Fettahlı Districts | Kanalizasyon Şebekesi İnşaatı (1. kademe) ve Pompa İstasyonu ve Yağmursuyu Drenajı | Kepez, Muratpaşa, Aksu,Döşemealtı İlçe Belediyeleri ile Kızıllı, Kurşunlui Topallı, Fettahlı Bölgeleri İçmesuyu Şebeke ve Evsel Bağlantılar İnşaatı işi | Works | ASAT2-W1 | 4012000 | 4012000 | 0 | 1 | NCB | POST | 28 February 2012 | 30 March 2012 | May 2012 | June 2012 | January 2014
2 | ASAT Water Facilities Rehabilitation Works |  | ASAT İçmesuyu Tesisleri Rehabilitasyon İşleri | Works | ASAT2-W2 | 5000000 | 5000000 | 0 | 1 | NCB | POST | June 2012 | July 2012 | August 2012 | August 2012 | April 2014
3 | Construction of Sewerage Network in Muratpaşa, Konyaaltı, Kepez Districts. |  | Muratpaşa, Konyaaltı, Kepez Bölgeleri Kanalizasyon Şebeke İnşaatı İşi | Works | ASAT2-W3 | 15425511 | 15425511 | 0 | 1 | ICB | PRIOR | May 2012 | June 2012 | July 2012 | July 2012 | July 2014
4 | Construction of Sewerage Network - II CANCELLED |  | Atıksu Şebekesi İnşaatı - II İPTAL | Works | ASAT2-W4
5 | Construction of Sewerage Network - III CANCELLED |  | Atıksu Şebeke İnşaatı - III İPTAL | Works | ASAT2-W5
6 | Construction of Sewerage Network and Collectors in Kepez, Döşemealtı and Konyaaltı Districts |  | Kepez, Döşemealtı ve Konyaaltı Bölgelerinde Kanalizasyon Şebeke ve Kollektör İnşaatı İşi | Works | ASAT2-W6 | 12000000 | 12000000 | 0 | 1 | ICB | PRIOR | 16 April 2012 | 2012-05-30 | June 2012 | July 2012 | July 2014
7 | Construction of Hurma Environmental Protection and Controlling Laboratory Building |  | Hurma Çevre Koruma ve Kontrol Laboratuvarı Binası İnşaatı İşi | Works | ASAT2-W9 | 1500000 | 1500000 | 0 | 1 | NCB | POST | 11 April 2012 | 2012-05-15 | June 2012 | July 2012 | July 2013
8 | Supply and Instalation of Electronic Security Support System for the Facilities of ASAT |  | ASAT Tesisleri için Elektronik Güvenlik Destek Sistemini Temin ve Kurulum İşi | S+I | ASAT2 -SI1 | 2000000 | 2000000 | 0 | 1 | ICB | PRIOR | June 2012 | July 2012 | August 2012 | August 2012 | August 2013
9 | Design,Supply and Installation of PTC Systems in Hurma WWTP |  | Hurma AAT için PTC Sistemleri Tasarımı, Temini ve Kurulumu İşi | S+I | ASAT2-A30 | 2500000 | 2500000 | 0 | 1 | ICB | PRIOR | June 2012 | July 2012 | August 2012 | August 2012 | August 2013
10 | Procurement of 3 Nos. of Watering Truck |  | 3 adet Su Tankeri Temini | Goods | ASAT2- G2 (ASAT-G12) | The Subject Contract has been constituted and signed as to be financed from both MSP and MSP Additional Financing. But in accordance with the allocation of 900.000 € in the Municipal Services Project I- it has decided to be cancelled from the MSP-Additional Financing and inserted to the MSP-I Procurement Plan Combined Rev. 9.
11 | Procuremnet of Cold Water Meters |  | Soğuk su Sayaçları Temini | Goods | ASAT2 - G4 | This Package has been shifted to MSP Procurement Plan rev. 10
12 | "Procurement of truck type multi purpose heavy machine with telescopic boom ¹ |  | "Kamyon Tipi Teleskopik Bomlu Çok Amaçlı İş Makinası Temini ¹ | Goods | ASAT2-G3 | 100000 | 100000 | 0 | 1 | NCB | POST | May 2012 | June 2012 | June 2012 | June 2012 | December 2012
13 | Procurement of Asphalt Paving Machine for repair works - CANCELLED |  | Tamirat İşleri İçin Asfalt Serme Makinası Temini | Goods | ASAT2-G5
14 | Lot 1-Procurement of Water Leakage Detection Vehicle and Lot 2- Procurement of Water Leakage Detection Equipment |  | Lot 1-Su Kaçak Arama Aracı Alımı ve Lot 2- Su Kaçak Arama Ekipmanları Alımı | Goods | ASAT2-G6 | 365221.8 | 365221.8 | 0 | 1 | NCB | POST | 12 May 2011 | 15 June 2011 | 13 September 2011 | 13 September 2011 | January 2012
15 | Procurement of Hot Mix Bituminous Asphalt |  | Bitümlü Sıcak Karışım Asfalt Alımı | Goods | ASAT2-G7 | 749000 | 749000 | 0 | 1 | NCB | POST | May 2012 | July 2012 | August 2012 | August 2012 | December 2014
16 | Procurement of 1500 Nos of Sphero Manhole Covers (LOT1) and 2000 Nos of Composite or Silikopolimer Manhole Covers (LOT2) |  | 1500 Adet Sfero Döküm Kanalizasyon Baca Kapağı (LOT1) ve 2000 Adet Kompozit veya Silikopolimer Kanalizasyon Baca Kapağı Alımı (LOT2) | Goods | ASAT -G10 | 236042.8 | 236042.8 | 0 | 1 (with 2 Lots) | NCB | POST | 22 September 2010 | 24 November 2010 | Lot 1- 31Jan. 2011 - Lot 2- 20 Jan. 2011 | January 2011 | Lot1- April 2011 Lot2- June 2011
| Works- Goods- Supply and Installation Sub-Total | İnşaat İşleri Alt-Toplam | Yapım işi-Mal Alımı-Temin ve Montaj Alt-Toplam |  |  | 43887775.6 | 43887775.6 | 0
| CONSULTANT'S SERVICES AND TRAINING | DANIŞMANLIK HİZMETLERİ VE EĞİTİM | DANIŞMANLIK HİZMETLERİ VE EĞİTİM
1 | Preparation of EMP | ÇYP'nin Hazırlanması | ÇED ve ÇYP'nin Hazırlanması | C | IST-C1 |  |  |  | 6: 1; 7: LPM
1 | Preparation of Final Designs and Bidding Documents and Construction Supervision Services | Uygulama Projelerinin İncelenmesi, İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | Kesin Projelerin ve İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | C | ASAT2-C1-A ASAT2-C1-B | 2769654 | 2769654 | 0 | 1 | QCBS | PRIOR | July 2010 | 14 March 2011 | 25 August 2011 | September 2011 | September 2014
| Works-Goods-S+I Sub-Total | Müşavirlik Alt-Toplam | Müşavirlik Alt-Toplam |  |  | 2769654 | 2769654 | 0
| PHYSICAL AND PRICE CONTINGENCY Sub- Total |  | Beklenmeyen Giderler Alt-Toplam |  |  | 1051000 | 1051000
| TOTAL | TOPLAM | TOPLAM |  |  | 47708429.6 | 47708429.6 | 0
Legend:
GOODS
ICB= | International Competitive Bidding (in accordance with section 2 of the Guidelines): For contracts valued at or more than Euro 750,000
NCB= | National Competitive Bidding (in accordance with section 3.3 of the Guidelines) : For contracts valued less than Euro 750,000
DC= | Direct Contracting (in accordance with section 3.6 of the Guidelines)
SH= | Shopping (in accordance with section 3.5 of the Guidelines)
For small works contracts valued at or less than Euro80,000
For provision of logistic services for workshops, seminars and etc: Euro80,000
For goods contracts valued at or less than Euro 80,000
Prior Review | All ICB contracts.
Technical Services for provision of logistic services for workshops, seminars and etc.: The first contract regardless of the value.
WORKS
ICB= | International Competitive Bidding (in accordance with section 2 of the Guidelines) : For contracts valued at or more than Euro 7,500,000
NCB= | National Competitive Bidding (in accordance with section 3.3 of the Guidelines) : For contracts valued less than Euro 7,500,000
Prior Review | All ICB contracts.
CONSULTANT'S SERVICES
QCBS = | Quality and Cost-based Selection (in accordance with sections 2.1 - 2.28 of the Consultant's Guidelines)
QBS= | Quality Based Selection (in accordance with sections 3.2-4 of the Consultant's Guidelines)
CQ= | Consultants Qualifications (in accordance with sections 3.7-8 of the Consultant's Guidelines)
LCS= | Least Cost Selection (in accordance with sections 3.6 of the Consultant's Guidelines)
SS= | Single Source Selection (in accordance with section 3.9 -13 of the Consultant's Guidelines)
IC= | Individual Consultant (in accordance with section V of the Consultant's Guidelines)
Prior Review | For firms: All contracts equal to Euro 250,000 or more and all SSS contracts.
For individual consultants: All contracts equal to Euro75,000 equivalent or more and all SSS contracts.
NOTE | 1 - It is planning to be financed under MSP. But for unexpected delays or unexpected increasings in contract budget, this package has been kept in MSP- Additional Financing.
BHP'den finanse edilecektir. Ancak, beklenmeyen gecikmeler veya sözleşme bütçelerinde öngörülmeyen artışlar durumu dikkate alınarak, BHP- Ek Kredi kapsamında da korunmuştur.

## ASAT2-REV-5-16 November 2011
MUNICIPAL SERVICES PROJECT - ADDITIONAL FINANCING - ASAT PROCUREMENT PLAN (Rev. 5 - November 16, 2011)
1 | 2 | 2 | 2' | 3 | 4 |  | 5 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Pack. No. | Description |  | Tanımlar | Type | No. of the Contract | Estimated Cost (Euro) |  |  | No. of packages | Proc. Method | Review by Bank Prior/Post | Invitation Date / Advertisement for EOI Date | Expected Bid-Open. Date/Proposal Submission Date | Contract Award Date | Start Date | Contract completion date
[6 empty] | Total | BF | NBF
| WORKS AND PROCUREMENT OF GOODS (INCLUDING SUPPLY & INSTALLATION) | İNŞAAT İŞLERİ (TEMİN VE MONTAJ DAHİL) | İNŞAAT İŞLERİ VE MAL ALIMI (TEMİN VE MONTAJ DAHİL)
1 | Construction of Water Network for Villages | Kanalizasyon Şebekesi İnşaatı (1. kademe) ve Pompa İstasyonu ve Yağmursuyu Drenajı | Köyler için İçmesuyu Şebekesi İnşaatı | Works | ASAT2-W1 | 2900000 | 2900000 | 0 | 1 | NCB | POST | December 2011 | January 2012 | March 2012 | March 2012 | November 2013
2 | Construction of Aksu River Water Facilities |  | Aksu Çayı İçmesuyu Tesisleri İnşaatı | Works | ASAT2-W2 | 10000000 | 10000000 | 0 | 1 | ICB | PRIOR | January 2012 | March 2012 | May 2012 | May 2012 | May 2014
3 | Construction of Sewerage Network - I |  | Atıksu Şebekesi İnşaatı - I | Works | ASAT2-W3 | 9226590 | 9226590 | 0 | 1 | ICB | PRIOR | November 2011 | December 2011 | March 2012 | March 2012 | November 2013
4 | Construction of Sewerage Network - II CANCELLED |  | Atıksu Şebekesi İnşaatı - II İPTAL | Works | ASAT2-W4
5 | Construction of Sewerage Network - III CANCELLED |  | Atıksu Şebeke İnşaatı - III İPTAL | Works | ASAT2-W5
6 | Construction of Sewerage Network - IV |  | Atıksu Şebeke İnşaatı - IV | Works | ASAT2-W6 | 12000000 | 12000000 | 0 | 1 | ICB | PRIOR | November 2011 | December 2011 | March 2012 | March 2012 | March 2014
7 | Construction of Hurma Laboratory Building |  | Hurma Laboratuvar Binası İnşaatı | Works | ASAT2-W9 | 1100000 | 1100000 | 0 | 1 | NCB | POST | October 2011 | November 2011 | December 2011 | January 2012 | August 2012
8 | Supply and Instalation of CCTV Scada System for the Facilities of ASAT |  | ASAT Tesisleri için CCTV Scada Sistemini Temin ve Kurulum İşi | S+I | ASAT2 -SI1 | 2000000 | 2000000 | 0 | 1 | ICB | PRIOR | October 2011 | November 2011 | December 2011 | January 2012 | January 2013
9 | Supply and Installation of PTC Solar Collectors in Hurma WWTP |  | Hurma AAT için PTC Solar Kollektör Temini ve Kurulumu İşi | S+I | ASAT2-A30 | 2500000 | 2500000 | 0 | 1 | ICB | PRIOR | October 2011 | November 2011 | December 2011 | December 2011 | August 2012
10 | Procurement of 3 Nos. of Watering Truck |  | 3 adet Su Tankeri Temini | Goods | ASAT2- G2 (ASAT-G12) | The Subject Contract has been constituted and signed as to be financed from both MSP and MSP Additional Financing. But in accordance with the allocation of 900.000 € in the Municipal Services Project I- it has decided to be cancelled from the MSP-Additional Financing and inserted to the MSP-I Procurement Plan Combined Rev. 9.
11 | Procurement of open channel excavator for cleaning of river |  | Nehir yatağı açık kanal temizleme ekskavatörü Temini | Goods | ASAT2-G3 | 500000 | 500000 | 0 | 1 | NCB | POST | November 2011 | December 2011 | January 2012 | January 2012 | May 2012
12 | Procurement of Cold Water Meters (The item is also included into the Combined Revision 9, dated August 15, 2011 of MSP procurement plan. The contract will be financed originally from the MSP, if needed the remaining amaount will be financed from Additional Loan ) |  | Soğuk Su sayaçları Alımı İşi (Bu kalem aynı zamanda 15 Ağustos 2011 tarihli 9 nolu Birleştirilmiş BHP satınalma planına dahil edilmiştir. Bu sözleşeme esas olarak BHP'den finanse edilecektir. İhtiyaç olması halinde kalan kısım Ek Krediden finanse edilecektir.) | Goods | ASAT2-G4 (ASAT-G14) | 304865 | 304865 | 0 | 1 | ICB | PRIOR | November 2011 | December 2011 | January 2012 | January 2012 | May 2012
13 | Procurement of Asphalt Paving Machine for repair works |  | Tamirat İşleri İçin Asfalt Serme Makinası Temini | Goods | ASAT2-G5 | 200000 | 200000 | 0 | 1 | NCB | POST | November 2011 | December 2011 | January 2012 | January 2012 | May 2012
14 | Lot 1-Procurement of Water Leakage Detection Vehicle and Lot 2- Procurement of Water Leakage Detection Equipments |  | Lot 1-Su Kaçak Arama Aracı Alımı ve Lot 2- Su Kaçak Arama Ekipmanları Alımı | Goods | ASAT2-G6 | 365221.8 | 365221.8 | 0 | 1 | NCB | POST | May 2011 | June 2011 | August 2011 | August 2011 | January 2012
15 | Procurement of Asphalt for the Work Contracts |  | İnşaat Sözleşmeleri için Asfalt Alımı | Goods | ASAT2-G7 | 2000000 | 2000000 | 0 | 1 | ICB | PRIOR | February 2012 | March 2012 | April 2012 | May 2012 | May 2013
16 | Procurement of 1500 Nos of Sphero Manhole Covers (LOT1) and 2000 Nos of Composite or Silikopolimer Manhole Covers (LOT2) |  | 1500 Adet Sfero Döküm Kanalizasyon Baca Kapağı (LOT1) ve 2000 Adet Kompozit veya Silikopolimer Kanalizasyon Baca Kapağı Alımı (LOT2) | Goods | ASAT -G10 | 236042.8 | 236042.8 | 0 | 1 (with 2 Lots) | NCB | POST | 22 September 2010 | 24 November 2010 | January 2011 | January 2011 | Lot1- April 2011 Lot2- June 2011
| Works- Goods- Supply and Installation Sub-Total | İnşaat İşleri Alt-Toplam | Yapım işi-Mal Alımı-Temin ve Montaj Alt-Toplam |  |  | 43332719.6 | 43332719.6 | 0
| CONSULTANT'S SERVICES AND TRAINING | DANIŞMANLIK HİZMETLERİ VE EĞİTİM | DANIŞMANLIK HİZMETLERİ VE EĞİTİM
1 | Preparation of EMP | ÇYP'nin Hazırlanması | ÇED ve ÇYP'nin Hazırlanması | C | IST-C1 |  |  |  | 6: 1; 7: LPM
1 | Preparation of Final Designs and Bidding Documents and Construction Supervision Services | Uygulama Projelerinin İncelenmesi, İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | Kesin Projelerin ve İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | C | ASAT2-C1-A ASAT2-C1-B | 2769654 | 2769654 | 0 | 1 | QCBS | PRIOR | July 2010 | March 2011 | August 2011 | September 2011 | September 2014
| Works-Goods-S+I Sub-Total | Müşavirlik Alt-Toplam | Müşavirlik Alt-Toplam |  |  | 2769654 | 2769654 | 0
| PHYSICAL AND PRICE CONTINGENCY Sub- Total |  | Beklenmeyen Giderler Alt-Toplam |  |  | 1606056 | 1606056
| TOTAL | TOPLAM | TOPLAM |  |  | 47708429.6 | 47708429.6 | 0
a) | All ICB contracts for works and goods and first NCB works, and goods contracts, first Shopping Contracts and all direct contracting will be subject to prior review by the Bank.
b) | The works contracts to cost less than Euro 7,5 million each may be awarded through NCB.
Bank’s sample NCB documents for ECA Region for Works will be used. The conditions for using NCB are listed in Schedule 4 to the Loan Agreement.
c) | Consultancy services by firms estimated to cost Euro 200,000 or more per contract, individual consultant contracts estimated to cost Euro 50,000 or more
and single source selection of consultants will be subject to prior review by the Bank.
d) | Short lists composed entirely of national consultants: Short lists of consultants for services estimated to cost less than Euro 200,000 equivalent per contract may be composed
entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.
Legend:
GOODS
ICB= | International Competitive Bidding (in accordance with section 2 of the Guidelines): For contracts valued at or more than Euro 750,000
NCB= | National Competitive Bidding (in accordance with section 3.3 of the Guidelines) : For contracts valued less than Euro 750,000
DC= | Direct Contracting (in accordance with section 3.6 of the Guidelines)
SH= | Shopping (in accordance with section 3.5 of the Guidelines)
For small works contracts valued at or less than Euro80,000
For provision of logistic services for workshops, seminars and etc: Euro80,000
For goods contracts valued at or less than Euro 80,000
Prior Review | All ICB contracts.
Technical Services for provision of logistic services for workshops, seminars and etc.: The first contract regardless of the value.
WORKS
ICB= | International Competitive Bidding (in accordance with section 2 of the Guidelines) : For contracts valued at or more than Euro 7,500,000
NCB= | National Competitive Bidding (in accordance with section 3.3 of the Guidelines) : For contracts valued less than Euro 7,500,000
Prior Review | All ICB contracts.
CONSULTANT'S SERVICES
QCBS = | Quality and Cost-based Selection (in accordance with sections 2.1 - 2.28 of the Consultant's Guidelines)
QBS= | Quality Based Selection (in accordance with sections 3.2-4 of the Consultant's Guidelines)
CQ= | Consultants Qualifications (in accordance with sections 3.7-8 of the Consultant's Guidelines)
LCS= | Least Cost Selection (in accordance with sections 3.6 of the Consultant's Guidelines)
SS= | Single Source Selection (in accordance with section 3.9 -13 of the Consultant's Guidelines)
IC= | Individual Consultant (in accordance with section V of the Consultant's Guidelines)
Prior Review | For firms: All contracts equal to Euro 250,000 or more and all SSS contracts.
For individual consultants: All contracts equal to Euro75,000 equivalent or more and all SSS contracts.
Note on M8: wb377902: Please provide the actual dates.
Note on M11: wb377902: Please provide the actual dates.
Note on M12: wb377902: Please provide the actual dates.
Note on M13: wb377902: Please provide the actual dates.
Note on M14: wb377902: Please provide the actual dates.

## ASAT2-REV-4-05 May 2011
MUNICIPAL SERVICES PROJECT - ADDITIONAL FINANCING - ASAT PROCUREMENT PLAN (Rev. 4 - May 05, 2011)
1 | 2 | 2 | 2' | 3 | 4 |  | 5 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Pack. No. | Description |  | Tanımlar | Type | No. of the Contract | Estimated Cost (Euro) |  |  | No. of packages | Proc. Method | Review by Bank Prior/Post | Invitation Date / Advertisement for EOI Date | Expected Bid-Open. Date/Proposal Submission Date | Contract Award Date | Start Date | Contract completion date
[6 empty] | Total | BF | NBF
| WORKS AND PROCUREMENT OF GOODS (INCLUDING SUPPLY & INSTALLATION) | İNŞAAT İŞLERİ (TEMİN VE MONTAJ DAHİL) | İNŞAAT İŞLERİ VE MAL ALIMI (TEMİN VE MONTAJ DAHİL)
1 | Construction of Water Network for Villages | Kanalizasyon Şebekesi İnşaatı (1. kademe) ve Pompa İstasyonu ve Yağmursuyu Drenajı | Köyler için İçmesuyu Şebekesi İnşaatı | Works | ASAT2-W1 | 2900000 | 2900000 | 0 | 1 | NCB | POST | July 2011 | August 2011 | October 2011 | October 2011 | June 2013
2 | Construction of Aksu River Water Facilities |  | Aksu Çayı İçmesuyu Tesisleri İnşaatı | Works | ASAT2-W2 | 10000000 | 10000000 | 0 | 1 | ICB | PRIOR | September 2011 | November 2011 | December 2011 | December 2011 | December 2013
3 | Construction of Sewerage Network - I |  | Atıksu Şebekesi İnşaatı - I | Works | ASAT2-W3 | 9226590 | 9226590 | 0 | 1 | ICB | PRIOR | June 2011 | August 2011 | October 2011 | October 2011 | June 2013
4 | Construction of Sewerage Network - II CANCELLED |  | Atıksu Şebekesi İnşaatı - II İPTAL | Works | ASAT2-W4
5 | Construction of Sewerage Network - III CANCELLED |  | Atıksu Şebeke İnşaatı - III İPTAL | Works | ASAT2-W5
6 | Construction of Sewerage Network - IV |  | Atıksu Şebeke İnşaatı - IV | Works | ASAT2-W6 | 12000000 | 12000000 | 0 | 1 | ICB | PRIOR | June 2011 | August 2011 | October 2011 | October 2011 | October 2013
7 | Construction of Hurma Laboratory Building |  | Hurma Laboratuvar Binası İnşaatı | Works | ASAT2-W9 | 1100000 | 1100000 | 0 | 1 | NCB | POST | March 2011 | April 2011 | May 2011 | Haz 2011 | January 2012
8 | Supply and Instalation of CCTV Scada System for the Facilities of ASAT |  | ASAT Tesisleri için CCTV Scada Sistemini Temin ve Kurulum İşi | S+I | ASAT2 -SI1 | 2000000 | 2000000 | 0 | 1 | ICB | PRIOR | March 2011 | April 2011 | May 2011 | Haz 2011 | June 2012
9 | Supply and Installation of PTC Solar Collectors in Hurma WWTP |  | Hurma AAT için PTC Solar Kollektör Temini ve Kurulumu İşi | S+I | ASAT2-A30 | 2500000 | 2500000 | 0 | 1 | ICB | PRIOR | January 2011 | February 2011 | March 2011 | March 2011 | November 2012
10 | Procurement of 3 Nos. of Watering Truck (The item is also included into the Combined Revision 8, dated May 05, 2011 of MSP procurement plan. The contract will be financed originally from the MSP, if needed the remaining amaount will be financed from Additional Loan ) |  | 3 adet Su tankeri Temini (Bu kalem aynı zamanda 05 Mayıs 2011 tarihli 8 nolu Birleştirilmiş BHP satınalma planına dahil edilmiştir. Bu sözleşeme esas olarak BHP'den finanse edilecektir. İhtiyaç olması halinde kalan kısım Ek Krediden finanse edilecektir.) | Goods | ASAT - G12 (ASAT2-G2) | 375000 | 250000 | 0 | 1 | NCB | POST | March 2011 | June 2011 | July 2011 | July 2011 | December 2011
11 | Procurement of open channel excavator for cleaning of river |  | Nehir yatağı açık kanal temizleme ekskavatörü Temini | Goods | ASAT2-G3 | 500000 | 500000 | 0 | 1 | NCB | POST | March 2011 | April 2011 | May 2011 | May 2011 | September 2011
12 | Procurement of Semi-Dry Type Class C Cold Water Meters |  | C Sınıfı Yaş Tip Soğuk Su sayaçları Alımı İşi | Goods | ASAT2-G4 | 1800000 | 1800000 | 0 | 1 | ICB | PRIOR | March 2011 | April 2011 | May 2011 | May 2011 | September 2011
13 | Procurement of Asphalt Paving Machine for repair works |  | Tamirat İşleri İçin Asfalt Serme Makinası Temini | Goods | ASAT2-G5 | 200000 | 200000 | 0 | 1 | NCB | POST | March 2011 | April 2011 | May 2011 | May 2011 | September 2011
14 | Lot 1-Procurement of Water Leakage Detection Vehicle and Lot 2- Procurement of Water Leakage Detection Equipments |  | Lot 1-Su Kaçak Arama Aracı Alımı ve Lot 2- Su Kaçak Arama Ekipmanları Alımı | Goods | ASAT2-G6 | 350000 | 350000 | 0 | 1 | NCB | POST | March 2011 | April 2011 | May 2011 | May 2011 | September 2011
15 | Procurement of Asphalt for the Work Contracts |  | İnşaat Sözleşmeleri için Asfalt Alımı | Goods | ASAT2-G7 | 2000000 | 2000000 | 0 | 1 | ICB | PRIOR | October 2011 | November 2011 | January 2012 | February 2012 | February 2013
16 | Procurement of 1500 Nos of Sphero Manhole Covers (LOT1) and 2000 Nos of Composite or Silikopolimer Manhole Covers (LOT2) |  | 1500 Adet Sfero Döküm Kanalizasyon Baca Kapağı (LOT1) ve 2000 Adet Kompozit veya Silikopolimer Kanalizasyon Baca Kapağı Alımı (LOT2) | Goods | ASAT -G10 | 300000 | 300000 | 0 | 1 (with 2 Lots) | NCB | POST | 22 September 2010 | 24 November 2010 | January 2011 | January 2011 | April 2011
| Works- Goods- Supply and Installation Sub-Total | İnşaat İşleri Alt-Toplam | Yapım işi-Mal Alımı-Temin ve Montaj Alt-Toplam |  |  | 45251590 | 45126590 | 0
| CONSULTANT'S SERVICES AND TRAINING | DANIŞMANLIK HİZMETLERİ VE EĞİTİM | DANIŞMANLIK HİZMETLERİ VE EĞİTİM
1 | Preparation of EMP | ÇYP'nin Hazırlanması | ÇED ve ÇYP'nin Hazırlanması | C | IST-C1 |  |  |  | 6: 1; 7: LPM
1 | Preparation of Final Designs and Bidding Documents and Construction Supervision Services | Uygulama Projelerinin İncelenmesi, İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | Kesin Projelerin ve İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | C | ASAT2-C1 | 2581840 | 2581840 | 0 | 1 | QCBS | PRIOR | July 2010 | February 2011 | April 2011 | April 2011 | March 2014
| Works-Goods-S+I Sub-Total | Müşavirlik Alt-Toplam | Müşavirlik Alt-Toplam |  |  | 2581840 | 2581840 | 0
| PHYSICAL AND PRICE CONTINGENCY Sub- Total |  | Beklenmeyen Giderler Alt-Toplam
| TOTAL | TOPLAM | TOPLAM |  |  | 47833430 | 47708430 | 0
a) | All ICB contracts for works and goods and first NCB works, and goods contracts, first Shopping Contracts and all direct contracting will be subject to prior review by the Bank.
b) | The works contracts to cost less than Euro 7,5 million each may be awarded through NCB.
Bank’s sample NCB documents for ECA Region for Works will be used. The conditions for using NCB are listed in Schedule 4 to the Loan Agreement.
c) | Consultancy services by firms estimated to cost Euro 200,000 or more per contract, individual consultant contracts estimated to cost Euro 50,000 or more
and single source selection of consultants will be subject to prior review by the Bank.
d) | Short lists composed entirely of national consultants: Short lists of consultants for services estimated to cost less than Euro 200,000 equivalent per contract may be composed
entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.
Legend:
GOODS
ICB= | International Competitive Bidding (in accordance with section 2 of the Guidelines): For contracts valued at or more than Euro 750,000
NCB= | National Competitive Bidding (in accordance with section 3.3 of the Guidelines) : For contracts valued less than Euro 750,000
DC= | Direct Contracting (in accordance with section 3.6 of the Guidelines)
SH= | Shopping (in accordance with section 3.5 of the Guidelines)
For small works contracts valued at or less than Euro80,000
For provision of logistic services for workshops, seminars and etc: Euro80,000
For goods contracts valued at or less than Euro 80,000
Prior Review | All ICB contracts.
Technical Services for provision of logistic services for workshops, seminars and etc.: The first contract regardless of the value.
Domestic Preferen. | will apply to all goods contracts only.
WORKS
ICB= | International Competitive Bidding (in accordance with section 2 of the Guidelines) : For contracts valued at or more than Euro 7,500,000
NCB= | National Competitive Bidding (in accordance with section 3.3 of the Guidelines) : For contracts valued less than Euro 7,500,000
Prior Review | All ICB contracts.
CONSULTANT'S SERVICES
QCBS = | Quality and Cost-based Selection (in accordance with sections 2.1 - 2.28 of the Consultant's Guidelines)
QBS= | Quality Based Selection (in accordance with sections 3.2-4 of the Consultant's Guidelines)
CQ= | Consultants Qualifications (in accordance with sections 3.7-8 of the Consultant's Guidelines)
LCS= | Least Cost Selection (in accordance with sections 3.6 of the Consultant's Guidelines)
SS= | Single Source Selection (in accordance with section 3.9 -13 of the Consultant's Guidelines)
IC= | Individual Consultant (in accordance with section V of the Consultant's Guidelines)
Prior Review | For firms: All contracts equal to Euro 250,000 or more and all SSS contracts.
For individual consultants: All contracts equal to Euro75,000 equivalent or more and all SSS contracts.
Note on H15: wb377902: Please revise these amount to be identical
Note on H22: wb377902: Please revise this amount to be identical with the total cost

## ASAT2-REV-3-07 January 2011
MUNICIPAL SERVICES PROJECT - ADDITIONAL FINANCING - ASAT PROCUREMENT PLAN (Rev. 3 - January 07, 2011)
1 | 2 | 2 | 2' | 3 | 4 |  | 5 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Pack. No. | Description |  | Tanımlar | Type | No. of the Contract | Estimated Cost (Euro) |  |  | No. of packages | Proc. Method | Review by Bank Prior/Post | Invitation Date / Advertisement for EOI Date | Expected Bid-Open. Date/Proposal Submission Date | Contract Award Date | Start Date | Contract completion date
[6 empty] | Total | BF | NBF
| WORKS AND PROCUREMENT OF GOODS (INCLUDING SUPPLY & INSTALLATION) | İNŞAAT İŞLERİ (TEMİN VE MONTAJ DAHİL) | İNŞAAT İŞLERİ VE MAL ALIMI (TEMİN VE MONTAJ DAHİL)
1 | Construction of Water Network for Villages | Kanalizasyon Şebekesi İnşaatı (1. kademe) ve Pompa İstasyonu ve Yağmursuyu Drenajı | Köyler için İçmesuyu Şebekesi İnşaatı | Works | ASAT2-W1 | 2900000 | 2900000 | 0 | 1 | NCB | POST | July 2011 | August 2011 | October 2011 | October 2011 | June 2013
2 | Construction of Aksu River Water Facilities |  | Aksu Çayı İçmesuyu Tesisleri İnşaatı | Works | ASAT2-W2 | 10000000 | 10000000 | 0 | 1 | ICB | PRIOR | September 2011 | November 2011 | December 2011 | December 2011 | December 2013
3 | Construction of Sewerage Network - I |  | Atıksu Şebekesi İnşaatı - I | Works | ASAT2-W3 | 9226590 | 9226590 | 0 | 1 | ICB | PRIOR | June 2011 | August 2011 | October 2011 | October 2011 | June 2013
4 | Construction of Sewerage Network - II CANCELLED |  | Atıksu Şebekesi İnşaatı - II İPTAL | Works | ASAT2-W4
5 | Construction of Sewerage Network - III CANCELLED |  | Atıksu Şebeke İnşaatı - III İPTAL | Works | ASAT2-W5
6 | Construction of Sewerage Network - IV |  | Atıksu Şebeke İnşaatı - IV | Works | ASAT2-W6 | 12000000 | 12000000 | 0 | 1 | ICB | PRIOR | June 2011 | August 2011 | October 2011 | October 2011 | October 2013
7 | Construction of Hurma Laboratory Building |  | Hurma Laboratuvar Binası İnşaatı | Works | ASAT2-W9 | 1100000 | 1100000 | 0 | 1 | NCB | POST | March 2011 | April 2011 | May 2011 | Haz 2011 | January 2012
8 | Supply and Instalation of CCTV Scada System for the Facilities of ASAT |  | ASAT Tesisleri için CCTV Scada Sistemini Temin ve Kurulum İşi | S+I | ASAT2 -SI1 | 2000000 | 2000000 | 0 | 1 | ICB | PRIOR | March 2011 | April 2011 | May 2011 | Haz 2011 | June 2012
9 | Supply and Installation of PTC Solar Collectors in Hurma WWTP |  | Hurma AAT için PTC Solar Kollektör Temini ve Kurulumu İşi | S+I | ASAT2-A30 | 2500000 | 2500000 | 0 | 1 | ICB | PRIOR | January 2011 | February 2011 | March 2011 | March 2011 | November 2012
10 | Procurement of 2 Nos. of Watering Truck |  | 2 adet Su tankeri Temini | Goods | ASAT2-G2 | 250000 | 250000 | 0 | 1 | NCB | POST | March 2011 | April 2011 | May 2011 | May 2011 | September 2011
11 | Procurement of open channel excavator for cleaning of river |  | Nehir yatağı açık kanal temizleme ekskavatörü Temini | Goods | ASAT2-G3 | 500000 | 500000 | 0 | 1 | NCB | POST | March 2011 | April 2011 | May 2011 | May 2011 | September 2011
12 | Procurement of Semi-Dry Type Class C Cold Water Meters |  | C Sınıfı Yaş Tip Soğuk Su sayaçları Alımı İşi | Goods | ASAT2-G4 | 1800000 | 1800000 | 0 | 1 | ICB | PRIOR | March 2011 | April 2011 | May 2011 | May 2011 | September 2011
13 | Procurement of Asphalt Paving Machine for repair works |  | Tamirat İşleri İçin Asfalt Serme Makinası Temini | Goods | ASAT2-G5 | 200000 | 200000 | 0 | 1 | NCB | POST | March 2011 | April 2011 | May 2011 | May 2011 | September 2011
14 | Lot 1-Procurement of Water Leakage Detection Vehicle and Lot 2- Procurement of Water Leakage Detection Equipments |  | Lot 1-Su Kaçak Arama Aracı Alımı ve Lot 2- Su Kaçak Arama Ekipmanları Alımı | Goods | ASAT2-G6 | 350000 | 350000 | 0 | 1 | NCB | POST | March 2011 | April 2011 | May 2011 | May 2011 | September 2011
15 | Procurement of Asphalt for the Work Contracts |  | İnşaat Sözleşmeleri için Asfalt Alımı | Goods | ASAT2-G7 | 2000000 | 2000000 | 0 | 1 | ICB | PRIOR | October 2011 | November 2011 | January 2012 | February 2012 | February 2013
16 | Procurement of 1500 Nos of Sphero Manhole Covers (LOT1) and 2000 Nos of Composite or Silikopolimer Manhole Covers (LOT2) |  | 1500 Adet Sfero Döküm Kanalizasyon Baca Kapağı (LOT1) ve 2000 Adet Kompozit veya Silikopolimer Kanalizasyon Baca Kapağı Alımı (LOT2) | Goods | ASAT -G10 | 300000 | 300000 | 0 | 1 (with 2 Lots) | NCB | POST | 22 September 2010 | 24 November 2010 | January 2011 | January 2011 | April 2011
| Works- Goods- Supply and Installation Sub-Total | İnşaat İşleri Alt-Toplam | Yapım işi-Mal Alımı-Temin ve Montaj Alt-Toplam |  |  | 45126590 | 45126590 | 0
| CONSULTANT'S SERVICES AND TRAINING | DANIŞMANLIK HİZMETLERİ VE EĞİTİM | DANIŞMANLIK HİZMETLERİ VE EĞİTİM
1 | Preparation of EMP | ÇYP'nin Hazırlanması | ÇED ve ÇYP'nin Hazırlanması | C | IST-C1 |  |  |  | 6: 1; 7: LPM
1 | Preparation of Final Designs and Bidding Documents and Construction Supervision Services | Uygulama Projelerinin İncelenmesi, İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | Kesin Projelerin ve İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | C | ASAT2-C1 | 2581840 | 2581840 | 0 | 1 | QCBS | PRIOR | July 2010 | February 2011 | April 2011 | April 2011 | March 2014
| Works-Goods-S+I Sub-Total | Müşavirlik Alt-Toplam | Müşavirlik Alt-Toplam |  |  | 2581840 | 2581840 | 0
| PHYSICAL AND PRICE CONTINGENCY Sub- Total |  | Beklenmeyen Giderler Alt-Toplam
| TOTAL | TOPLAM | TOPLAM |  |  | 47708430 | 47708430 | 0
a) | All ICB contracts for works and goods and first NCB works, and goods contracts, first Shopping Contracts and all direct contracting will be subject to prior review by the Bank.
b) | The works contracts to cost less than Euro 7,5 million each may be awarded through NCB.
Bank’s sample NCB documents for ECA Region for Works will be used. The conditions for using NCB are listed in Schedule 4 to the Loan Agreement.
c) | Consultancy services by firms estimated to cost Euro 200,000 or more per contract, individual consultant contracts estimated to cost Euro 50,000 or more
and single source selection of consultants will be subject to prior review by the Bank.
d) | Short lists composed entirely of national consultants: Short lists of consultants for services estimated to cost less than Euro 200,000 equivalent per contract may be composed
entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.
Legend:
GOODS
ICB= | International Competitive Bidding (in accordance with section 2 of the Guidelines): For contracts valued at or more than Euro 750,000
NCB= | National Competitive Bidding (in accordance with section 3.3 of the Guidelines) : For contracts valued less than Euro 750,000
DC= | Direct Contracting (in accordance with section 3.6 of the Guidelines)
SH= | Shopping (in accordance with section 3.5 of the Guidelines)
For small works contracts valued at or less than Euro80,000
For provision of logistic services for workshops, seminars and etc: Euro80,000
For goods contracts valued at or less than Euro 80,000
Prior Review | All ICB contracts.
Technical Services for provision of logistic services for workshops, seminars and etc.: The first contract regardless of the value.
Domestic Preferen. | will apply to all goods contracts only.
WORKS
ICB= | International Competitive Bidding (in accordance with section 2 of the Guidelines) : For contracts valued at or more than Euro 7,500,000
NCB= | National Competitive Bidding (in accordance with section 3.3 of the Guidelines) : For contracts valued less than Euro 7,500,000
Prior Review | All ICB contracts.
CONSULTANT'S SERVICES
QCBS = | Quality and Cost-based Selection (in accordance with sections 2.1 - 2.28 of the Consultant's Guidelines)
QBS= | Quality Based Selection (in accordance with sections 3.2-4 of the Consultant's Guidelines)
CQ= | Consultants Qualifications (in accordance with sections 3.7-8 of the Consultant's Guidelines)
LCS= | Least Cost Selection (in accordance with sections 3.6 of the Consultant's Guidelines)
SS= | Single Source Selection (in accordance with section 3.9 -13 of the Consultant's Guidelines)
IC= | Individual Consultant (in accordance with section V of the Consultant's Guidelines)
Prior Review | For firms: All contracts equal to Euro 250,000 or more and all SSS contracts.
For individual consultants: All contracts equal to Euro75,000 equivalent or more and all SSS contracts.

## REW-2-WB-cleared-26-october2010
MUNICIPAL SERVICES PROJECT - ADDITIONAL FINANCING - ASAT PROCUREMENT PLAN (Rev. II - October 22- 2010)
1 | 2 | 2 | 2' | 3 | 4 |  | 5 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Pack. No. | Description |  | Tanımlar | Type | No. of the Contract | Estimated Cost (Euro) |  |  | No. of packages | Proc. Method | Review by Bank Prior/Post | Invitation Date / Advertisement for EOI Date | Expected Bid-Open. Date/Proposal Submission Date | Contract Award Date | Start Date | Contract completion date
[6 empty] | Total | BF | NBF
| WORKS AND PROCUREMENT OF GOODS (INCLUDING SUPPLY & INSTALLATION) | İNŞAAT İŞLERİ (TEMİN VE MONTAJ DAHİL) | İNŞAAT İŞLERİ VE MAL ALIMI (TEMİN VE MONTAJ DAHİL)
1 | Construction of Water Network for Villages | Kanalizasyon Şebekesi İnşaatı (1. kademe) ve Pompa İstasyonu ve Yağmursuyu Drenajı | Köyler için İçmesuyu Şebekesi İnşaatı | Works | ASAT2-W1 | 2567855 | 2567855 | 0 | 1 | NCB | POST | July 2011 | August 2011 | October 2011 | October 2011 | September 2013
2 | Construction of Aksu River Water Facilities |  | Aksu Çayı İçmesuyu Tesisleri İnşaatı | Works | ASAT2-W2 | 7506739 | 7506739 | 0 | 1 | ICB | PRIOR | July 2011 | September 2011 | November 2011 | November 2011 | October 2013
3 | Construction of Sewerage Network - I |  | Atıksu Şebekesi İnşaatı - I | Works | ASAT2-W3 | 9849366 | 9849366 | 0 | 1 | ICB | PRIOR | June 2011 | August 2011 | October 2011 | October 2011 | September 2013
4 | Construction of Sewerage Network - II |  | Atıksu Şebekesi İnşaatı - II | Works | ASAT2-W4 | 8768986 | 8768986 | 0 | 1 | ICB | PRIOR | June 2011 | August 2011 | October 2011 | October 2011 | September 2013
5 | Construction of Sewerage Network - III |  | Atıksu Şebeke İnşaatı - III | Works | ASAT2-W5 | 5634356 | 5634356 | 0 | 1 | NCB | POST | June 2011 | August 2011 | October 2011 | October 2011 | September 2013
6 | Construction of Sewerage Network - IV |  | Atıksu Şebeke İnşaatı - IV | Works | ASAT2-W6 | 7849288 | 7849288 | 0 | 1 | ICB | PRIOR | June 2011 | August 2011 | October 2011 | October 2011 | September 2013
7 | Procurement of 1500 Nos of Sphero Manhole Covers (LOT1) and 2000 Nos of Composite or Silikopolimer Manhole Covers (LOT2) |  | 1500 Adet Sfero Döküm Kanalizasyon Baca Kapağı (LOT1) ve 2000 Adet Kompozit veya Silikopolimer Kanalizasyon Baca Kapağı Alımı (LOT2) | Goods | ASAT -G10 | 450000 | 450000 | 0 | 1 (with 2 Lots) | NCB | POST | 22 September 2010 | 27 October 2010 | November 2010 | November 2010 | February 2011
8 | Supply And Installation of PTC Solar Collectors in Hurma WWTP |  | Hurma Atıksu Arıtma Tesisi İçin PTC Solar Kollektör Temini ve Montajı | S+I | ASAT2-A30 | 2500000 | 2500000 | 0 | 1 | ICB | PRIOR | November 2010 | December 2010 | January 2011 | January 2011 | September 2011
| Works Sub-Total | İnşaat İşleri Alt-Toplam | İnşaat İşleri Alt-Toplam |  |  | 45126590 | 45126590 | 0
| CONSULTANT'S SERVICES AND TRAINING | DANIŞMANLIK HİZMETLERİ VE EĞİTİM | DANIŞMANLIK HİZMETLERİ VE EĞİTİM
1 | Preparation of EMP | ÇYP'nin Hazırlanması | ÇED ve ÇYP'nin Hazırlanması | C | IST-C1 |  |  |  | 6: 1; 7: LPM
1 | Preparation of Final Designs and Bidding Documents and Construction Supervision Services | Uygulama Projelerinin İncelenmesi, İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | Kesin Projelerin ve İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | C | ASAT2-C1 | 2581840 | 2581840 | 0 | 1 | QCBS | PRIOR | July 2010 | October 2010 | January 2011 | January 2011 | October 2013
| Consultant Sub-Total | Müşavirlik Alt-Toplam | Müşavirlik Alt-Toplam |  |  | 2581840 | 2581840 | 0
| PHYSICAL AND PRICE CONTINGENCY Sub- Total |  | Beklenmeyen Giderler Alt-Toplam
| TOTAL | TOPLAM | TOPLAM |  |  | 47708430 | 47708430 | 0
This Revision has been made regarding to the short of budget in MSP I Procurement Plan. Contract Packages ASAT2-A30 and ASAT G10 have been transfered from MSP I Procurement Plan
a) | All ICB contracts for works and goods and first NCB works, and goods contracts, first Shopping Contracts and all direct contracting will be subject to prior review by the Bank.
b) | The works contracts to cost less than Euro 7,5 million each may be awarded through NCB.
Bank’s sample NCB documents for ECA Region for Works will be used. The conditions for using NCB are listed in Schedule 4 to the Loan Agreement.
c) | Consultancy services by firms estimated to cost Euro 200,000 or more per contract, individual consultant contracts estimated to cost Euro 50,000 or more
and single source selection of consultants will be subject to prior review by the Bank.
d) | Short lists composed entirely of national consultants: Short lists of consultants for services estimated to cost less than Euro 200,000 equivalent per contract may be composed
entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.
Legend:
GOODS
ICB= | International Competitive Bidding (in accordance with section 2 of the Guidelines): For contracts valued at or more than Euro 750,000
NCB= | National Competitive Bidding (in accordance with section 3.3 of the Guidelines) : For contracts valued less than Euro 750,000
DC= | Direct Contracting (in accordance with section 3.6 of the Guidelines)
SH= | Shopping (in accordance with section 3.5 of the Guidelines)
For small works contracts valued at or less than Euro80,000
For provision of logistic services for workshops, seminars and etc: Euro80,000
For goods contracts valued at or less than Euro 80,000
Prior Review | All ICB contracts.
Technical Services for provision of logistic services for workshops, seminars and etc.: The first contract regardless of the value.
Domestic Preferen. | will apply to all goods contracts only.
WORKS
ICB= | International Competitive Bidding (in accordance with section 2 of the Guidelines) : For contracts valued at or more than Euro 7,500,000
NCB= | National Competitive Bidding (in accordance with section 3.3 of the Guidelines) : For contracts valued less than Euro 7,500,000
Prior Review | All ICB contracts.
CONSULTANT'S SERVICES
QCBS = | Quality and Cost-based Selection (in accordance with sections 2.1 - 2.28 of the Consultant's Guidelines)
QBS= | Quality Based Selection (in accordance with sections 3.2-4 of the Consultant's Guidelines)
CQ= | Consultants Qualifications (in accordance with sections 3.7-8 of the Consultant's Guidelines)
LCS= | Least Cost Selection (in accordance with sections 3.6 of the Consultant's Guidelines)
SS= | Single Source Selection (in accordance with section 3.9 -13 of the Consultant's Guidelines)
IC= | Individual Consultant (in accordance with section V of the Consultant's Guidelines)
Prior Review | For firms: All contracts equal to Euro 250,000 or more and all SSS contracts.
For individual consultants: All contracts equal to Euro75,000 equivalent or more and all SSS contracts.

## ASAT2-1 -JULY 2010
MUNICIPAL SERVICES PROJECT - ADDITIONAL FINANCING - ASAT PROCUREMENT PLAN (Rev. 1 - August 03, 2010)
1 | 2 | 2 | 2' | 3 | 4 |  | 5 |  | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13
Pack. No. | Description |  | Tanımlar | Type | No. of the Contract | Estimated Cost (Euro) |  |  | No. of packages | Proc. Method | Review by Bank Prior/Post | Invitation Date / Advertisement for EOI Date | Expected Bid-Open. Date/Proposal Submission Date | Contract Award Date | Start Date | Contract completion date
[6 empty] | Total | BF | NBF
| WORKS (INCLUDING SUPPLY & INSTALLATION) | İNŞAAT İŞLERİ (TEMİN VE MONTAJ DAHİL) | İNŞAAT İŞLERİ (TEMİN VE MONTAJ DAHİL)
1 | Construction of Water Network for Villages | Kanalizasyon Şebekesi İnşaatı (1. kademe) ve Pompa İstasyonu ve Yağmursuyu Drenajı | Köyler için İçmesuyu Şebekesi İnşaatı | Works | ASAT2-W1 | 2567855 | 2567855 | 0 | 1 | NCB | POST | July 2011 | August 2011 | October 2011 | October 2011 | September 2013
2 | Construction of Aksu River Water Facilities |  | Aksu Çayı İçmesuyu Tesisleri İnşaatı | Works | ASAT2-W2 | 7506739 | 7506739 | 0 | 1 | ICB | PRIOR | July 2011 | September 2011 | November 2011 | November 2011 | October 2013
3 | Construction of Sewerage Network - I |  | Atıksu Şebekesi İnşaatı - I | Works | ASAT2-W3 | 11049366 | 11049366 | 0 | 1 | ICB | PRIOR | June 2011 | August 2011 | October 2011 | October 2011 | September 2013
4 | Construction of Sewerage Network - II |  | Atıksu Şebekesi İnşaatı - II | Works | ASAT2-W4 | 9518986 | 9518986 | 0 | 1 | ICB | PRIOR | June 2011 | August 2011 | October 2011 | October 2011 | September 2013
5 | Construction of Sewerage Network - III |  | Atıksu Şebeke İnşaatı - III | Works | ASAT2-W5 | 6134356 | 6134356 | 0 | 1 | NCB | POST | June 2011 | August 2011 | October 2011 | October 2011 | September 2013
6 | Construction of Sewerage Network - IV |  | Atıksu Şebeke İnşaatı - IV | Works | ASAT2-W6 | 8349288 | 8349288 | 0 | 1 | ICB | PRIOR | June 2011 | August 2011 | October 2011 | October 2011 | September 2013
| Works Sub-Total | İnşaat İşleri Alt-Toplam | İnşaat İşleri Alt-Toplam |  |  | 45126590 | 45126590 | 0
| CONSULTANT'S SERVICES AND TRAINING | DANIŞMANLIK HİZMETLERİ VE EĞİTİM | DANIŞMANLIK HİZMETLERİ VE EĞİTİM
1 | Preparation of EMP | ÇYP'nin Hazırlanması | ÇED ve ÇYP'nin Hazırlanması | C | IST-C1 |  |  |  | 6: 1; 7: LPM
1 | Preparation of Final Designs and Bidding Documents and Construction Supervision Services | Uygulama Projelerinin İncelenmesi, İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | Kesin Projelerin ve İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | C | ASAT2-C1 | 2581840 | 2581840 | 0 | 1 | QCBS | PRIOR | July 2010 | October 2010 | January 2011 | January 2011 | October 2013
| Consultant Sub-Total | Müşavirlik Alt-Toplam | Müşavirlik Alt-Toplam |  |  | 2581840 | 2581840 | 0
| PHYSICAL AND PRICE CONTINGENCY Sub- Total |  | Beklenmeyen Giderler Alt-Toplam
| TOTAL | TOPLAM | TOPLAM |  |  | 47708430 | 47708430 | 0
a) | All ICB contracts for works and goods and first NCB works, and goods contracts, first Shopping Contracts and all direct contracting will be subject to prior review by the Bank.
b) | The works contracts to cost less than Euro 7,5 million each may be awarded through NCB.
Bank’s sample NCB documents for ECA Region for Works will be used. The conditions for using NCB are listed in Schedule 4 to the Loan Agreement.
c) | Consultancy services by firms estimated to cost Euro 200,000 or more per contract, individual consultant contracts estimated to cost Euro 50,000 or more
and single source selection of consultants will be subject to prior review by the Bank.
d) | Short lists composed entirely of national consultants: Short lists of consultants for services estimated to cost less than Euro 200,000 equivalent per contract may be composed
entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.
Legend:
GOODS
ICB= | International Competitive Bidding (in accordance with section 2 of the Guidelines): For contracts valued at or more than Euro 750,000
NCB= | National Competitive Bidding (in accordance with section 3.3 of the Guidelines) : For contracts valued less than Euro 750,000
DC= | Direct Contracting (in accordance with section 3.6 of the Guidelines)
SH= | Shopping (in accordance with section 3.5 of the Guidelines)
For small works contracts valued at or less than Euro80,000
For provision of logistic services for workshops, seminars and etc: Euro80,000
For goods contracts valued at or less than Euro 80,000
Prior Review | All ICB contracts.
Technical Services for provision of logistic services for workshops, seminars and etc.: The first contract regardless of the value.
Domestic Preferen. | will apply to all goods contracts only.
WORKS
ICB= | International Competitive Bidding (in accordance with section 2 of the Guidelines) : For contracts valued at or more than Euro 7,500,000
NCB= | National Competitive Bidding (in accordance with section 3.3 of the Guidelines) : For contracts valued less than Euro 7,500,000
Prior Review | All ICB contracts.
CONSULTANT'S SERVICES
QCBS = | Quality and Cost-based Selection (in accordance with sections 2.1 - 2.28 of the Consultant's Guidelines)
QBS= | Quality Based Selection (in accordance with sections 3.2-4 of the Consultant's Guidelines)
CQ= | Consultants Qualifications (in accordance with sections 3.7-8 of the Consultant's Guidelines)
LCS= | Least Cost Selection (in accordance with sections 3.6 of the Consultant's Guidelines)
SS= | Single Source Selection (in accordance with section 3.9 -13 of the Consultant's Guidelines)
IC= | Individual Consultant (in accordance with section V of the Consultant's Guidelines)
Prior Review | For firms: All contracts equal to Euro 250,000 or more and all SSS contracts.
For individual consultants: All contracts equal to Euro75,000 equivalent or more and all SSS contracts.

## ASAT2-1 -DEC. 2009
MUNICIPAL SERVICES PROJECT - ADDITIONAL FINANCING - ASAT PROCUREMENT PLAN (December 31, 2009)
1 | 2 | 2 | 2' | 3 | 4 | 5 |  | 6 |  | 7 | 8 | 9 | 10 | 11 | 12
Ref. No. | Description |  | Tanımlar | Type | No. of the Contract | No. of packages | Estimated Cost (Euro) |  |  | Proc. Method | Review by Bank Prior/Post | Preperation BD/RFP date | Expected Bid-Open. Date/Proposal Submission Date | Conctract signed date | Contract completion date
[7 empty] | Total | BF | NBF
| WORKS (INCLUDING SUPPLY & INSTALLATION) | İNŞAAT İŞLERİ (TEMİN VE MONTAJ DAHİL) | İNŞAAT İŞLERİ (TEMİN VE MONTAJ DAHİL)
1 | Construction of Water Network for Villages | Kanalizasyon Şebekesi İnşaatı (1. kademe) ve Pompa İstasyonu ve Yağmursuyu Drenajı | Köyler için İçmesuyu Şebekesi İnşaatı | Works | ASAT2-W1 | 1 | 2398665 | 2398665 | 0 | NCB | POST | March 2011 | May 2011 | July 2011 | June 2013
2 | Construction of Aksu River Water Facilities |  | Aksu Çayı İçmesuyu Tesisleri İnşaatı | Works | ASAT2-W2 | 1 | 7651500 | 7651500 | 0 | ICB | PRIOR | March 2011 | April 2011 | August 2011 | July 2013
3 | Construction of Sewerage Network - I |  | Atıksu Şebekesi İnşaatı - I | Works | ASAT2-W3 | 1 | 10818011 | 10818011 | 0 | ICB | PRIOR | May 2011 | July 2011 | September 2011 | August 2013
4 | Construction of Sewerage Network - II |  | Atıksu Şebekesi İnşaatı - II | Works | ASAT2-W4 | 1 | 9287631 | 9287631 | 0 | ICB | PRIOR | May 2011 | July 2011 | September 2011 | August 2013
5 | Construction of Sewerage Network - III |  | Atıksu Şebeke İnşaatı - III | Works | ASAT2-W5 | 1 | 8117935 | 8117935 | 0 | ICB | PRIOR | May 2011 | July 2011 | September 2011 | August 2013
6 | Construction of Sewerage Network - IV |  | Atıksu Şebeke İnşaatı - IV | Works | ASAT2-W6 | 1 | 5903001 | 5903001 | 0 | NCB | POST | May 2011 | July 2011 | September 2011 | August 2013
| Works Sub-Total | İnşaat İşleri Alt-Toplam | İnşaat İşleri Alt-Toplam |  |  |  | 44176743 | 44176743 | 0
| CONSULTANT'S SERVICES AND TRAINING | DANIŞMANLIK HİZMETLERİ VE EĞİTİM | DANIŞMANLIK HİZMETLERİ VE EĞİTİM
1 | Preparation of EMP | ÇYP'nin Hazırlanması | ÇED ve ÇYP'nin Hazırlanması | C | IST-C1 | 1 |  |  |  | LPM
1 | Preparation of Final Designs and Bidding Documents and Construction Supervision Services | Uygulama Projelerinin İncelenmesi, İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | Kesin Projelerin ve İhale Dokümanlarının Hazırlanması ve İnşaat Kontrolluğu | C | ASAT2-C1 | 1 | 2143559 | 2143559 | 0 | QCBS | PRIOR | February 2010 | July 2010 | November 2010 | August 2013
| Consultant Sub-Total | Müşavirlik Alt-Toplam | Müşavirlik Alt-Toplam |  |  |  | 2143559 | 2143559 | 0
| PHYSICAL AND PRICE CONTINGENCY Sub- Total |  | Beklenmeyen Giderler Alt-Toplam
| TOTAL | TOPLAM | TOPLAM |  |  |  | 46320302 | 46320302 | 0
a) | All ICB contracts for works and goods and first NCB works, and goods contracts, first Shopping Contracts and all direct contracting will be subject to prior review by the Bank.
b) | The works contracts to cost less than Euro 7,5 million each may be awarded through NCB.
Bank’s sample NCB documents for ECA Region for Works will be used. The conditions for using NCB are listed in Schedule 4 to the Loan Agreement.
c) | Consultancy services by firms estimated to cost Euro 200,000 or more per contract, individual consultant contracts estimated to cost Euro 50,000 or more
and single source selection of consultants will be subject to prior review by the Bank.
d) | Short lists composed entirely of national consultants: Short lists of consultants for services estimated to cost less than Euro 200,000 equivalent per contract may be composed
entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.