## Goods
PROCUREMENT PLAN FOR GOODS
No. | Activity | Quantity | Reference No. | Estimated Cost (IDR) | Proc. Method | Review |  | Schedule
[8 empty] | Prep. Of RFQ | WB NOL | Issue of Documents | Submission of Quotation | Eval. Report | WB NOL | Finalization of PO / Contract | Comm. | Compl. | Contract Amount | Remarks
1 | Computer Equipment | 1 package | CE |  | Shopping | Post | Planned | 2013-02-25 | NA | 2013-03-07 | 2013-03-14 | 2013-03-17 | NA | 2013-03-22 | 2013-03-27 | 2013-04-03
[7 empty] | Revised | 2013-03-05 |  | 2013-03-06
Actual
2 | Office Furniture | 1 package | OF |  | Shopping | Post | Planned | 2013-02-25 | NA | 2013-03-07 | 2013-03-14 | 2013-03-17 | NA | 2013-03-22 | 2013-03-27 | 2013-04-03
[7 empty] | Revised | 2013-03-05 |  | 2013-03-07
Actual
3 | Telephones | 1 package | TPH |  | Shopping | Post | Planned | 2013-02-25 | NA | 2013-03-07 | 2013-03-14 | 2013-03-17 | NA | 2013-03-22 | 2013-03-27 | 2013-04-03
[7 empty] | Revised | 2013-03-05 |  | 2013-03-07
Actual
4 | Camera & Video Camera | 1 package | CA |  | Shopping | Post | Planned | 2013-02-25 | NA | 2013-03-07 | 2013-03-14 | 2013-03-17 | NA | 2013-03-22 | 2013-03-27 | 2013-04-03
[7 empty] | Revised | 2013-03-05 |  | 2013-03-07
Actual
5 | Airconditioning | 1 package | AC |  | Shopping | Post | Planned | 2013-02-25 | NA | 2013-03-07 | 2013-03-14 | 2013-03-17 | NA | 2013-03-22 | 2013-03-27 | 2013-04-03
[7 empty] | Revised | 2013-03-05 |  | 2013-03-07
Actual
Total
Formulas:
Issue of Documents = [Schedule]+10
Submission of Quotation = [Issue of Documents]+7
Eval. Report = [Submission of Quotation]+3
Finalization of PO / Contract = [Eval. Report]+5
Comm. = [Finalization of PO / Contract]+5
Compl. = [Comm.]+7

## Individual Consultants
PROCUREMENT PLAN FOR SELECTION OF INDIVIDUAL CONSULTANTS
No. | Activity | Reference No. | Estimated Cost (IDR) | Proc. Method | Review |  | Schedule
[7 empty] | Prep. of TOR | WB NOL | ADV | Sub. of CV | Evaluation | Negotiation / Draft Contract | WB NOL | Contract Signing | Comm. | Expected Date | Compl. | Contract Amount
1 | Procurement & Financial Specialist | PFS 1 |  | Competitive Selection | Prior review only for TOR and CV of the selected candidate | Planned | 2013-02-06 | 2013-02-13 | 2013-02-16 | 2013-02-23 | 2013-02-28 | 2013-03-05 | 2013-03-12 | 2013-03-17 | 2013-03-22 | 2014-03-30
Revised
Actual
2 | Communication Specialist | CS 1 |  | Competitive Selection | Post | Planned | 2013-02-06 | NA | 2013-02-16 | 2013-02-23 | 2013-02-28 | 2013-03-05 | NA | 2013-03-15 | 2013-03-20 | 2014-03-30
Revised
Actual
3 | Cultural Specialist | AFS 2 |  | Single Source** | Post | Planned | 2013-02-06 | NA | 2013-02-18 | 2013-02-25 | 2013-03-02 | 2013-03-07 | NA | 2013-03-17 | 2013-03-22 | 2014-03-30
Revised
Actual
4 | Project Manager | PM 1 |  | Competitive Selection | Post | Planned | 2013-02-06 | NA | 2013-02-18 | 2013-02-25 | 2013-03-02 | 2013-03-07 | NA | 2013-03-17 | 2013-03-22 | 2014-03-30
Revised
Actual
5 | Assisstant Project Manager | APM 1 |  | Single Source** | Post | Planned | 2013-02-06 | NA | 2013-02-18 | 2013-02-25 | 2013-03-02 | 2013-03-07 | NA | 2013-03-17 | 2013-03-22 | 2014-03-30
Revised
Actual
6 | Project Staff | PS 1 |  | Competitive Selection | Post | Planned | 2013-02-06 | NA | 2013-02-18 | 2013-02-25 | 2013-03-02 | 2013-03-07 | NA | 2013-03-17 | 2013-03-22 | 2014-03-30
Revised
Actual
7 | Administrative/Finance Staff | PS 2 |  | Competitive Selection | Post | Planned | 2013-02-06 | NA | 2013-02-18 | 2013-02-25 | 2013-03-02 | 2013-03-07 | NA | 2013-03-17 | 2013-03-22 | 2014-03-30
Revised
Actual
Total
* | TOR and draft contract must be sent to CC2 Coordinator
** | Justification, TOR and draft contract must be sent tto CC2 Coordinator
Formulas:
WB NOL = [Schedule]+7
WB NOL = [Negotiation / Draft Contract]+7
ADV = [WB NOL]+3
Sub. of CV = [ADV]+7
Evaluation = [Sub. of CV]+5
Negotiation / Draft Contract = [Evaluation]+5
Contract Signing = [WB NOL]+5
Comm. = [Contract Signing]+5

## Firm Consultants
PROCUREMENT PLAN FOR SELECTION OF FIRM CONSULTANTS
No. | Activity | Ref. No. | Estimated Cost (IDR) | Proc. Method | Review |  | Schedule
[7 empty] | Prep. Of TOR/RFP/Cost Estimate | WB NOL | EOI/ Adv. | Sub. Of EOI | EOI Evaluation | Sub. Of Technical/Financial Proposal | Proposal Evaluation | Negotiation/ Draft Contract | WB NOL | Contract Signing | Commencement | Compl. | Contract Amount
1 | Financial Audit | A.1 |  | Single Source | Prior review only for justification made for single-source selection of particular firm and TOR | Planned | 2013-04-15 | 2013-04-29 | 2013-05-02 | 2013-05-16 | 2013-05-23 | 2013-06-06 | 2013-06-13 | 2013-06-20 | 2013-06-27 | 2013-07-04 | 2013-07-11 | 2013-08-10
Revised
Actual
Total
Formulas:
WB NOL = [Schedule]+14
EOI/ Adv. = [WB NOL]+3
Sub. Of EOI = [EOI/ Adv.]+14
EOI Evaluation = [Sub. Of EOI]+7
Sub. Of Technical/Financial Proposal = [EOI Evaluation]+14
Compl. = [Commencement]+30

## Training & Workshops
PROCUREMENT PLAN FOR TRAINING AND WORKSHOPS
Note: this is not part of the Procurement Plan.
It is included to ensure the total amount can be cross-referenced with the budget
No. | Activity | Ref. No. | Estimated Cost (IDR)
1 | CULTURE MODEL DESIGN, pilot in 3 locations and 12 presentations | CMD
2 | TRAINING FOR TRAINERS ON CULTURAL APPROACHES TO STRENGTHEN COMMUNITY EMPOWERMENT in PNPM | TOTCA
3 | Communication & Outreach | CW
4 | SUB-GRANTEES SELECTION AND DOCUMENTATION | SGD
Total