|  |
| --- |
| **Restructuring** **Status:** **Archived** |
| **Restructuring Type:** **Level two** |
| Last modified on date : 11/29/2012 |

|  |
| --- |
| **1. Basic Information** |
| Project ID & Name | P098949: VIP 2 |
| Country | Kyrgyz Republic |
| Task Team Leader | Aly Zulficar Rahim |
| Sector Manager/Director | Elisabeth Huybens |
| Country Director | Saroj Kumar Jha |
| Original Board Approval Date | 08/03/2006 |
| Original Closing Date: | 06/30/2011 |
| Current Closing Date | 12/31/2012 |
| Proposed Closing Date [if applicable] | 06/29/2013 |
| EA Category | F-Financial Intermediary Assessment |
| Revised EA Category | F-Financial Intermediary Assessment-Financial Intermediary Assessment |
| EA Completion Date |  |
| Revised EA Completion Date |  |

|  |
| --- |
| **2. Revised Financing Plan (US$m)** |
| **Source** | **Original** | **Revised** |
|  BORR | 7.50 | 7.50 |
|  DFID | 13.20 | 13.62 |
|  IDA | 0.00 | 8.00 |
|  IDAT | 15.00 | 15.00 |
|  **Total** | 35.70 | 44.12 |

|  |
| --- |
| **3. Borrower** |
| **Organization** | **Department** | **Location** |
|  Kyrgyz Republic |  | Kyrgyz Republic |

|  |
| --- |
| **4. Implementing Agency** |
| **Organization** | **Department** | **Location** |

|  |
| --- |
| **5. Disbursement Estimates (US$m)** |
| **Actual amount disbursed as of 12/03/2012** **23.90** |
| **Fiscal Year** | **Annual** | **Cumulative** |
|  2012 | 0.00 | 23.90 |
|  2013 | 0.00 | 23.90 |
|   | **Total** | **23.90** |

|  |
| --- |
| **6. Policy Exceptions and Safeguard Policies** |
| **Does the restructured project require any exceptions to Bank policies?** | N |
|  |  |
|  |  |
| **Does the restructured projects trigger any new safeguard policies? If yes, please select from the checklist below and update ISDS accordingly before submitting the package.** | N |

|  |
| --- |
| **7a. Project Development Objectives/Outcomes****Original/Current Project Development Objectives/Outcomes** |
| The objective of the Project is to assist the Recipient with: (a) improving governance and capacity at the local level; (b) strengthening the provision of, and access to, essential infrastructure services; and (c) supporting private group-owned small scale enterprise development.  |

|  |
| --- |
| **7b. Revised Project Development Objectives/Outcomes** [if applicable] |
|   |