# Procurement Plan

# São Tomé and Príncipe: Adaptation to Climate Change Project

(P111669; GEF PMIS 4018)

## General

- Project: The project aims to increase the adaptive capacity of vulnerable coastal communities in S. Tome and Principe to the adverse impacts of climate variability and change.

- Country:   São Tomé and Príncipe

- Borrower: Democratic Republic of São Tomé and Príncipe

- Project Name:  Adaptation to Climate Change Project

- Loan/Credit No.  P111669/GEF PMIS 4018

- Project Implementing Agency:  Ministry of Public Works and Natural Resources, Directorate General of Environment (through a Project Coordinating Unit, PCU)

- Bank’s approval Date of the Procurement Plan: Original: April 25, 2011; Revised: May 03, 2012

- Date of General Procurement Notice: May 16, 2011

- Period covered by this Procurement Plan:  May 2012 to December 31, 2016

##### II. Goods and Works and Non-Consulting Services

- Prior Review Threshold: Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement. Thresholds for applicable procurement methods (not limited to the list below) will be determined by the Procurement Specialist /Procurement Accredited Staff based on the assessment of the implementing agency’s capacity.

|  | Procurement Method | Prior Review Threshold | Comments |
| --- | --- | --- | --- |
| 1. | ICB and LIB (Goods) | > 250,000 | All |
| 2. | NCB (Goods) | ≥50,000<250,000 | First two contracts |
| 3. | Shopping (Goods) | < 50,000 | Post review |
| 4. | ICB (Works) | > 500,000.00 | All |
| 5. | NCB (Works) | ≥50,000<500,000 | First two activities |
| 6. | Three (03) Quotations (Works) | <50,000 | Post review |

2.	Prequalification. N/A.

3.	Proposed Procedures for Community Participation Activities (as per paragraph. 3.17 of the Guidelines:

Pilot adaptation works under Component 2(b) ii, estimated at a cumulative total of US$310,000 would be procured under Community Participation procedures and will be detailed in the procurement chapter of the Project Operation Manual

- Reference to (if any) Project Operational/Procurement Manual: The Project Operational Manual (including Procurement) was prepared and is being used. The Procurement Chapter of the Manual was conditionally approved by the Bank on September 23, 2011. Procedures related to community participation are being improved.

- Any Other Special Procurement Arrangements: N/A

##### Procurement Packages with Methods and Time Schedule

| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| --- | --- | --- | --- | --- | --- | --- |
| Ref. No. | Contract (Description) | Estimated Cost | Procurement Method | Review by Bank (Prior / Post) | Expected Bid-Opening Date | Comments |
| GOODS |  |  |  |  |  |  |
| 01/PAMCZC/G/2012 | Vehicles |  | Shopping | Post | March 2012 | Already procured |
| 02/PAMCZC/G/2012 | Office Equipment |  | Shopping | Post | March 2012 | Already procured |
| 03/PAMCZC/G/2012 | Office Furnishings |  | Shopping | Post | September 2012 |  |
| 04/PAMCZC/G2012 | Air conditioner |  | shopping | post | May 2012 |  |
| 05/PAMCZC/G2012 | Vehicles MARAPA |  | Shopping | Post | May 2012 |  |
| 04/PAMCZC/G/2012 | Purchase of equipments to support fisheries |  | Shopping | Prior | May 2012 | 4 Lots (, Life Vests, Emergency Flares, , Rain Coats, First Aid Kits) |
| 05/PAMCZC/G/2012 | Radar Detectors |  | Shopping | Post | May 2012 |  |
| 06/PAMCZC/G/2012 | Mobile Phone Covers |  | Shopping | Post | May 2012 |  |
| 07/PAMCZC/G/2012 | Purchase of fishery equipments |  | Shopping | Post | May 2012 | 3 Lots (Compasses, Lights for Marking Nets, Tools for Building Radar Reflectors) |
| 08/PAMCZC/G/2012 | Meteorological Marine Station |  | LIB | Prior | September 2012 | Review Technical specification, qualification, draft contract |
| 09/PAMCZC/G/2012 | GPS |  | Shopping | Post | May 2012 |  |
| 10/PAMCZC/G/2012 | Studio Equipment for Preparation and Dissemination of Weather Forecasts |  | Shopping | Post | September 2012 |  |
| 11/PAMCZC/G/2013 | Doppler Weather Radar |  | LIB | Prior | March 2013 | Review Technical specification, selection, qualification, draft contract |
| 12/PAMCZC/G/2013 | Network Server, Data Link and Computers |  | Shopping | Post | April 2013 | 4 Lots (Netwark server and data link/Computer for Safety at Sea (Crowdsourcing)/ Computer for Meteorological Data Processing/ Computer for Preparation of Weather Reports) |
| 13/PAMCZC/G/2013 | GSM Network |  | NCB | Prior | April 2013 |  |
| WORKS |  |  |  |  |  |  |
| 01/PAMCZC/W/2013 | Coastal Protection Works: Beach protection (Ribeira Afonso) |  | NCB | Prior | January 2013 | Review Technical specification, selection, qualification, draft contract |
| 02/PAMCZC/W/2013 | Coastal Protection Works: Beach works Malanza |  | NCB | Prior | October 2013 | Review Technical specification, selection, qualification, draft contract |
| 03/PAMCZC/W/2014 | Coastal Protection Works: Beach protection (Sta Catarina) |  | NCB | Post | April 2014 | Review Technical specification, selection, qualification, draft contract |
| 04/PAMCZC/W/2013 | River bed dredging and embankment and large drainage: Malanza |  | NCB | Post | October 2013 | Review Technical specification, selection, qualification, draft contract |
| 05/PAMCZC/W/2014 | River bed dredging and embankment and large drainage: Sta. Catarina |  | NCB | Post | April 2014 | Review Technical specification, selection, qualification, draft contract |
| 06/PAMCZC/W/2014 | River bed dredging and embankment and large drainage: Sundy |  | NCB | Post | October 2014 | Review Technical specification, selection, qualification, draft contract |

##### III. Selection of Consultants

- Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:

|  | Selection Method | Prior Review Threshold | Comments |
| --- | --- | --- | --- |
| 1. | QCBS (Firms) | > 100,000 | All |
| 2. | Selection Based on Consultants’ Qualification | <100,000 | First two contracts |
| 3. | Least Cost Selection | <100,000 | First two contracts |
| 3. | Single Source (Firms) | All |  |
| 4. | Individual Consultants | >50,000 <50,000 | All Project Unit Staff |
| 5. | Individual Consultants (SSS) | All |  |

2.  	Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than $100,000 equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.

3.	Any Other Special Selection Arrangements: N/A

4.	Consultancy Assignments with Selection Methods and Time Schedule

bril

| 1 | 2 | 3 | 4 | 5 | 6 | 7 |
| --- | --- | --- | --- | --- | --- | --- |
| Ref. No. | Description of Assignment | Estimated Cost | Selection Method | Review by Bank (Prior / Post) | Expected Proposals Submission Date | Comments |
| 01/PAMCZC/C/2012 | Extension of Geomorphological Study to Malanza and Sundy |  | Single Source | Prior | April 2012 | Single Source contract with UNESCO-IHE/DELTARES Already procured |
| 02/PAMCZC/C/2012 | External Audits |  | LCS | Prior | April 2012 | Proposals must be submitted no later than the following date and time:30/04/2012,17h00m |
| 03/PAMCZC/C/2012 | Project Advisor to Coordinator (Island System Resilience) |  | IC | Prior | January 2012 | Already procured |
| 04/PAMCZC/C/2011 | Procurement Specialist |  | IC | Prior | September 2011 | Already hired |
| 04/PAMCZC/C/2011 | Procurement specialist |  | SSS | Prior | September 2012 |  |
| 05/PAMCZC/C/2011 | Financial Management Specialist |  | IC | Prior | September 2011 | Already hired |
| 05/PAMCZC/C/2011 | Financial management specialist |  | SSS | Prior | September 2012 |  |
| 06/PAMCZC/C/2012 | National Expert for Early Warning and Safety at Sea |  | IC | Prior | March 2012 | Already hired |
| 07/PAMCZC/C/2012 | Software contabilidade |  | SSS | prior | May 2012 |  |
| 08/PAMCZC/C/2012 | Spatial Planning Trainer (Coastal) |  | IC | Post | June 2012 |  |
| 09/PAMCZC/C/2012 | Training and Sensitization of Target Fishers |  | Single Source | Prior | March 2012 | Single Source contract with MARAPA Already hired |
| 09/PAMCZC/C/2012 | Training and Sensitization of Target Fishers |  | SSS | Prior | February 2013 |  |
| 10/PAMCZC/C/2012 | Radar Assessment Expert |  | IC | Post | September 2012 | Comparison of at least 3 CVs from qualified and specialized candidates |
| 11/PAMCZC/C/2013 | International Safety at Sea Expert |  | IC | Post | January 2013 |  |
| 12/PAMCZC/C/2012 | Detailed Engineering Design of Flood Protection Works |  | IC | Prior | July 2012 |  |
| 13/PAMCZC/C/2014 | Finalization of Decree on Coastal Early Warning System /o |  | IC | Post | March 2014 |  |
| 14/PAMCZC/C/2014 | Coastal Policy Expert |  | IC | Post | March 2014 |  |
| 15/PAMCZC/C/2015 | Project Evaluation |  | IC | Post | November 2015 |  |
| 16/PAMCZC/C/2015 | Participatory Evaluation |  | CQS | Prior | November 2015 |  |

IV. Training Seminaries and Workshops

1.	In this section the agreed Capacity Building Activities (some items could be from CPAR recommendation) are listed with time schedule

| No. | Expected outcome / Activity Description | Estimated Cost | Estimated Duration | Start Date | Comments |
| --- | --- | --- | --- | --- | --- |
| 1 | Establishment of Local Risk Management Committees |  | 10 months | March 2012 – December 2012 |  |
| 2 | Community Sensitization and Behavioral Change Workshops |  | 1 week for each community | March 2012 – April 2015 |  |
| 3 | Specialized Training in Maintenance of Maritime Meteorology |  | 1 month | February 2013 | 1 technician, trained at Niamey or Dakar for one month |
| 4 | Introductory Meeting on Protocol for Coastal Early Warning System |  | 1 day | February 2013 | 30 persons, 1 day workshop |
| 5 | Local Training for Radio Journalists |  | 2 months | June 2012 | 2 radio journalists in weather reporting at Meteorological Institute for 2 months each |
| 6 | Workshop for Development of Operation Plan of Coastal Early Warning System |  | 3 days | November 2012 | 40-50 participants, 3 day workshop |
| 7 | Training in Marine Meteorology |  | 4 months | October 2012 | 2 observers to be trained in Lisbon (2 persons x 4 months) |
| 8 | Specialized Training in Presentation of Weather Reports over Media |  | 2 months | September 2012 | 5 meteorologists x 2 months at Regional Meteorological Center in Dakar or Morocco |
| 9 | Agreement on Monitoring System for Safety-at-Sea Incidents |  | 2 days | May 2012 | 40-50 people workshop, after system prepared by Safety-at-Sea specialist |
| 10 | Study Tours to Pilot Sites |  | 6 days | March 2012 to June 2015 | Assumes study tour by district/village representatives to pilot sites (ca. 30 people x 1 day, 6 cars, fuel and per diem costs and US$1000 per village for reception/organization costs) |
| 11 | Lessons Learned Discussion Workshop |  | 4 days | February 2013 | Ca. 40-50 participants, 2x 2-day workshops |
| 12 | Preparation of Policy and Legal Framework for Building Climate Resilience into Spatial Planning |  | 4 days | April 2013 | 4-day workshop for 40-50 participants |
| 13 | Training on Safeguards for DGE/PCU Staff |  | 1 weeks 2 phases | November 2012 | Training in lusophone hub (Maputo, Luanda, or Brasilia) on WB related safeguards for 3 DGE/PCU staff on first year, and 2 on second year |
| 14 | Quarterly Review Meetings and Project Monitoring |  | 20 days | April/May 2012 | Quarterly review 1-day workshop meetings for members of steering committee (ca. 30 people) at US$1000/day |

# Text boxes

68525