## Goods
Procurement Plan (PP) for Goods [FY 2012/2013], Partial
Project Name & ID: Second Higher Education Project(SHEP) | [8 empty] | Executing Agency: University Grants Commission, Sanothimi, Bhaktapur
Loan/Credit/Grant No: H274-NEP | [8 empty] | Implementing Agency: Hari Khetan Multiple Campus, Birganj, Parsa
S. No. | Description of Goods or Works & Contract ID No. | Prior/Post Review | PP Status | Cost Estimate (NRs. Million) | Method of Procurement | Proc. Procedure: GoN or WB? | Bid Document to WB | WB's NOL to Bid Document | Bid Invitation | Public Opening of Bids | BER & Award Recomm. To WB | WB's NOL to Award Recommendation | Contract Signing | Completion fo the Contract | Procuremetn at Center or District | Remarks
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17
1 | Procurement of Furniture and Furnishing Materials (SHEP/UGC/HariKhetan/G/NCB-01) | Post | P |  | NCB | GoN | NA | NA | 2013-04-03 | 2013-05-03 | NA | NA | 2013-05-28 | 2013-07-27 | District
R
A
2 | Procurement of Books (SHEP/UGC/HariKhetan/G/SQ-02) | Post | P |  | SQ | GoN | NA | NA | 2013-04-03 | 2013-04-18 | NA | NA | 2013-04-30 | 2013-07-19 | District
R
A
| TOTAL |  |  | 0
Formulas:
Public Opening of Bids = [Bid Invitation]+30
Contract Signing = [Public Opening of Bids]+25
Completion fo the Contract = [Contract Signing]+60