## Combined PP 22-2-13
Annexure.II : PROCUREMENT SCHEDULE FOR WORKS
Country: INDIA
Borrower: GOVERNMENT OF ANDHRA PRADESH
Project: A.P.M.D.P. Status as on 23rd Feb. 2013
S No | WBR No. | Method of Procurement | Description | Procurement Authority | Quantity (Number) | Estimated Cost (Rs. Crores) local currency) | Estimated Cost (Million USD) | Proir/Post Review | Stage | Preparation of DPR/ Submission of DPR | Technical sanction from PHED | Initiate preparation of Specification and Bid Document | Preparation of IFB and submission to the Bank | Submission of the Bid Document | Approval of IFB and Bid documents by the World Bank | Publication of IFB in Newspapers / UNDB | Beginning of Sale of Bid document | Opening of Bids | Submission of BER to Bank for approval | Approval of BER | Issue of contract award notice | Signing of the contract | Agreemet No.& Dt. | 50% work complete | 100% work complete | Completion of contractual obligations | Procurement Monitaring.
[7 empty] | 1 US $ = Rs. 55 | [19 empty] | No. of Contractors |  |  | Bid Premium | Contract completion time |  | No. of Contracts rebid | No. of Contracts with insufficient bids | Extension of bid validity
[27 empty] | Applied | Participated | Qualified |  | Planned | Actual
1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36
1 |  | NCB | Comprehensive Water Supply Improvement of services in Markapur | MSU/ULB | 1 | 37.7 | 6.8545 | Prior | Comlpeted | 19/4/2012 | 26/7/2012 | 14/2/2012 | 19/4/2012 | 23/6/2012 | 15/7/2012 | 30/7/2012 | 30/7/2012 | 17/9/2012 | 18/10/2012 | 2012-01-11 | 2012-01-12 | 2013-07-01 | 58/2012-13 Dt: 7-1-2013
2 |  | NCB | Comprehensive Water Supply Improvement of services in Vizianagaram(Package-I) | MSU/ULB | 1 | 8.4 | 1.5273 | Post | Actual Estimated | [6 empty] | 11/1/2013 3rd call | 2013-11-01 | 15/2/2013 | Post Review | - | 31/3/2013 | 28/4/2013
3 |  | NCB | Comprehensive Water Supply Improvement of services in Vizianagaram(Package-II a) | MSU/ULB | 1 | 41 | 7.4545 | Prior | Actual Estimated | 2012-12-01 | 30/4/2012 | 2012-09-01 | 20/4/2012 | 23/4/2012 | 2012-10-05 | 14/11/2012 2nd call | 14/11/2012 | 17/12/2012 | 19/1/2013 | 2013-03-02 | 15/2/2013 | 31/3/2013
4 |  | NCB | Comprehensive Water Supply Improvement of services in Kakinada(Package-I) | MSU/ULB | 1 | 22.03 | 4.0055 | Prior | Actual Estimated | 31/3/2012 | 30/4/2012 | 31/3/2012 | 2012-10-09 | 2012-10-09 | 24/9/2012 | 31/10/2012 | 31/10/2012 | 14/12/2012 | 19/1/2013 | 2013-07-02 | 15/2/2013 | 31/3/2013 |  | - | - | -
5 |  | NCB | Comprehensive Water Supply Improvement of services in Kakinada(Package-IV) | MSU/ULB | 1 | 29.83 | 5.4236 | Prior | Actual Estimated | 31/3/2012 | 30/4/2012 | 31/3/2012 | 2012-10-09 | 2012-10-09 | 24/9/2012 | 31/10/2012 | 31/10/2012 | 14/12/2012 | 24/1/2013 | 2013-07-02 | 28/2/2013 | 31/3/2013
6 |  | ICB | Comprehensive Water Supply Improvement of services in Kakinada(Package-II) | MSU/ULB | 1 | 112.68 | 20.4873 | Prior | Actual Estimated | 31/3/2012 | 30/4/2012 | 31/3/2012 | 17/9/2012 | 17/9/2012 | 2012-12-10 | 30/1/2013 | 31/1/2013 | 15/3/2013 | 31/3/2013 | 15/4/2013 | 30/4/2013 | 31/5/2013
7 |  | ICB | Comprehensive Water Supply Improvement of services in Badvel | MSU/ULB | 1 | 94.6 | 17.2 | Prior | Actual Estimated | 31/3/2012 | 30/4/2012 | 31/3/2012 | 2012-10-09 | 2012-10-09 | 24/9/2012 | 2012-05-11 | 2012-05-11 | 2013-07-01 | 2013-06-02 | 28/2/2013 | 31/3/2013 | 30/4/2013
8 |  | ICB | Comprehensive Water Supply Improvement of services in Ananatapur | MSU/ULB | 1 | 117.72 | 21.4036 | Prior | Actual Estimated | 2012-12-01 | 30/4/2012 | 2012-09-01 | 17/9/2012 | 17/9/2012 | 15/10/2012 | 30/11/2012 | 30/11/2012 | 2013-01-02 | 28/2/2013 | 15/3/2013 | 31/3/2013 | 30/4/2013
9 |  | ICB | Comprehensive Water Supply Improvement of services in Guntur(Package-I) | MSU/ULB | 1 | 291.6 | 53.0182 | Prior | Actual Estimated | 15/4/2012 | 30/5/2012 | 31/3/2012 | 2012-12-09 | 2012-12-09 | 2012-03-10 | 13/12/2012 | 13/12/2012 | 2013-05-03 | 15/3/2013 | 31/3/2013 | 15/4/2013 | 15/5/2013
10 |  | ICB | Comprehensive Water Supply Improvement of services in Guntur(Package-II) | MSU/ULB | 1 | 100.95 | 18.3545 | Prior | Actual Estimated | 15/4/2012 | 30/5/2012 | 31/3/2012 | 2012-12-09 | 2012-12-09 | 2012-03-10 | 2012-12-11 | 2012-12-11 | 2013-05-01 | 30/1/2013 | 28/2/2013 | 31/3/2013 | 30/4/2013
11 |  | ICB | Comprehensive Water Supply Improvement of services in Armoor | MSU/ULB | 1 | 93.11 | 16.9291 | Prior | Actual Estimated | 2013-01-01 | 21/1/2013 | 15/12/2012 | 15/2/2013 | 15/2/2013 | 28/2/2013 | 2013-11-03 | 2013-11-03 | 30/4/2013 | 15/5/2013 | 31/5/2013 | 30/6/2013 | 31/7/2013
12 |  | NCB | Comprehensive water supply service improvements In Malkajgiri(part of GHMC) package-I | MSU/ULB | 1 | 50 | 9.0909 | Prior | Estimated | 15/12/2012 | 28/2/2013 | 2013-01-02 | 2013-11-03 | 2013-11-03 | 31/3/2013 | 15/4/2013 | 15/4/2013 | 20/5/2013 | 31/5/2013 | 15/6/2013 | 2013-10-07 | 14/8/2013
13 |  | ICB | Comprehensive water supply service improvements In Malkajgiri(part of GHMC) Package-II | MSU/ULB | 1 | 240.2 | 43.6727 | Prior | Estimated | 15/12/2012 | 28/2/2013 | 2013-01-02 | 2013-11-03 | 2013-11-03 | 31/3/2013 | 15/4/2013 | 15/4/2013 | 15/6/2013 | 30/6/2013 | 15/7/2013 | 14/8/2013 | 15/9/2013
14 |  | NCB | Comprehensive Water Supply Improvement of services in Manuguru | MSU/ULB | 1 | 25 | 4.5455 | Post | Estimated | 15/12/2012 | 15/3/2013 | 2013-01-02 | 15/3/2013 | 15/3/2013 | 31/3/2013 | 15/4/2013 | 15/4/2013 | 20/5/2013 |  |  | 15/6/2013 | 15/7/2013
|  |  | Date: | [8 empty] | Version No: | [9 empty] | Approved Date: