|  |
| --- |
| 62611 v2  **Restructuring** **Status:** **Archived** |
| **Restructuring Type:** **Level two** |
| Last modified on date : 06/14/2011 |

|  |  |
| --- | --- |
| **1. Basic Information** | |
| Project ID & Name | P101955: SD-North Sudan Livestock (FY07) |
| Country | Sudan |
| Task Team Leader | Mohamed Osman Hussein |
| Sector Manager/Director | Karen Mcconnell Brooks |
| Country Director | Ian Bannon |
| Original Board Approval Date | 08/29/2007 |
| Original Closing Date: | 08/30/2011 |
| Current Closing Date | 08/30/2011 |
| Proposed Closing Date [if applicable] | 06/30/2012 |
| EA Category | B-Partial Assessment |
| Revised EA Category | B-Partial Assessment-Partial Assessment |
| EA Completion Date | 12/31/2007 |
| Revised EA Completion Date | 10/28/2010 |

|  |  |  |
| --- | --- | --- |
| **2. Revised Financing Plan (US$m)** | | |
| **Source** | **Original** | **Revised** |
| BORR | 12.00 | 12.00 |
| MDNS | 8.00 | 8.00 |
| **Total** | 20.00 | 20.00 |

|  |  |  |
| --- | --- | --- |
| **3. Borrower** | | |
| **Organization** | **Department** | **Location** |

|  |  |  |
| --- | --- | --- |
| **4. Implementing Agency** | | |
| **Organization** | **Department** | **Location** |
| Ministry of Animal Resources and Fisheries | Livestock Development | Sudan |

|  |  |  |
| --- | --- | --- |
| **5. Disbursement Estimates (US$m)** | | |
| **Actual amount disbursed as of 06/16/2011** **4.86** | | |
| **Fiscal Year** | **Annual** | **Cumulative** |
| 2010 | 0.00 | 4.86 |
| 2011 | 0.00 | 4.86 |
|  | **Total** | **4.86** |

|  |  |
| --- | --- |
| **6. Policy Exceptions and Safeguard Policies** | |
| **Does the restructured project require any exceptions to Bank policies?** | N |
|  |  |
|  |  |
| **Does the restructured projects trigger any new safeguard policies? If yes, please select from the checklist below and update ISDS accordingly before submitting the package.** | N |

|  |
| --- |
| **7a. Project Development Objectives/Outcomes**  **Original/Current Project Development Objectives/Outcomes** |
| Development objective of the project is to improve livestock production and marketing in selected rainfed areas of Central and Eastern Sudan. |

|  |
| --- |
| **7b. Revised Project Development Objectives/Outcomes** [if applicable] |
|  |