## General
PROJECT NAME: Gaza Water Supply and Sewage Systems Improvement Project WSSSIP
PROCUREMENT PLAN
I. General
1. Project information:
· Project Name: | Gaza Water Supply and Sewage Systems Improvement Projecy
· Country: | West Bank and Gaza
· Project ID: | P101289
Loan/Grant No. | TF013564
Proc Plan Revision | 1 | 01-December-2013
II. Goods and Works
1. Procurement Methods and Thresholds
Category | Method of Procurement | Threshold | Prior Review Threshold
|  | (US$ Equivalent) | (US$ Equivalent)
Goods | NCB | <500,000 | First Contract
| Shopping | <100,000 | None
| Direct Contracting | No threshold | All contracts
Works | NCB | <2,000,000 | First Contract
| Shopping | <200,000 | None
| Direct Contracting | No threshold | All contracts
Non-Consultancy Services | NCB | <500,000 | First Contract
| Shopping | <100,000 | None
| Direct Contracting | No threshold | All contracts
2 . Pre-qualification.
3. Reference to Project Operational and Procurement Manual: NA
4. Any Other Special Procurement Arrangements:
5. Procurement Packages with Methods and Time Schedule – Attachment: Goods (Annex I), Works (Annex II)
III. Selection of Consultants
1 Selection Methods and Thresholds
Category | Selection Method | Threshold | Prior Review Threshold
|  | (US$ Equivalent) | (US$ Equivalent)
Consulting Services Firms | QCBS/QBS | No threshold | First contract selected under each of the two methods and thereafter all contracts above $1,000,000
| FBS/CQS/LCS | <300,000 | First contract selected under each of the three methods
| Sole Source | No threshold | All contracts
Individuals | IC | No threshold | First contract and thereafter all contracts above $300,000
| Sole Source | No threshold | All contracts
2. Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than $300,000 equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.

## Works
Palestinian Water Authority PWA
Gaza Water Supply and Sewage Systems Improvement Project GWSSSIP | [9 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation |  | Variations |  | Payments |  | Conract Progress
No. | Comp. No. | Task No. | Description | Task Manager | Plan vs. Actual | Lot Number | Estimated US $ | Proc. Method | Prior or Post Review | Submittal Date | Bank No Objection on BD | Bid Invitation Date | Bid Opening Date | Submission Bid Eval Rpt | No-objection Date | Contract Amount in US$ | Contract Signing Date | Contract Completion Date | Supplier Name | Arrival of Goods | Inspection Final Acceptance | Total V.O. | Contract Final Amount | Total Paid | Total to be Paid | Notes
Works
A. Construction of Resorvoirs and Water Booster Stations in Middle & South Areas.
1 | 1.1 | A.1 | Construction Service Building and Installation of Electromechanical Equipments at Bani Suhaila Reservoir | Ahmad Shaker | Planned |  |  | NCB | Post | NA | NA | 2014-01-10 | 2014-01-30 | NA | NA |  | 2014-02-19 | 2014-08-18
Actual
2 | 1.1 | A.2 | Construction of Carrier Lines aned Connections for Al Moghraqa Reservoir | Ahmad Shaker | Planned |  |  | NCB | Post | NA | NA | 2014-01-20 | 2014-02-09 | NA | NA |  | 2014-03-03 | 2014-08-30
Actual
B. Rehabilitation and Reallocation of Water Wells
3.1 | 1.2 | B.1 | Electromechanical Rehabilitaion and Upgrading of water Wells Including Pumps Replacement & Electro and Mechanical Repairs and Refurbishment of Electrical Power Supply generators for Water Facilities - Phase I | Omar Shatat | Planned |  |  |  | Prior | 2013-01-10 | 2013-01-16 | 2013-01-25 | 2013-02-12 | 2013-02-26 | 2013-03-01 |  | 2013-03-03 | 2015-03-03
[5 empty] | Actual | NCB W 02a-02/2013-GWSSSIP |  | NCB |  | 2013-02-05 | 2013-05-13 | 2013-05-15 | 2013-06-16 | 2013-07-18 | 2013-07-22 | 172217 | 24-Jul-13 | 2015-01-15 | Esmael Alawa & Sons Co. |  |  |  | 172217 | 20871.03 | 151345.97 | Ongoing
[6 empty] | NCB W 02b-02/2013-GWSSSIP |  | NCB |  | 2013-02-05 | 2013-05-13 | 2013-05-15 | 2013-06-16 | 2013-07-18 | 2013-07-22 | 67310 | 24-Jul-13 | 2015-01-15 | Abed Al Rahman Yasine Shops |  |  |  | 67310 | 10876.55 | 56433.45 | Ongoing
3.2 | 1.2 | B.1 | Electromechanical Rehabilitaion and Upgrading of water Wells Including Pumps Replacement & Electro and Mechanical Repairs and Refurbishment of Electrical Power Supply generators for Water Facilities - Phase II | Omar Shatat | Planned |  |  | NCB | Post | 2014-04-20 | 2014-04-25 | 2014-05-05 | 2014-05-23 | 2014-06-06 | 2014-06-09 |  | 2014-06-11 | 2016-06-10
Actual
4 | 1.2 | B.2 | Realocate Wadi Al Salga and Al Nussirat Water Wells, Drilling New Wells with all Associated Facilities. | Omar Shatat | Planned | NCB W 06-10/2013-GWSSSIP |  | NCB | Post | NA | NA | 2014-08-15 | 2014-09-04 | NA | NA | 194286.15 | 2014-09-26 | 2015-09-26
[5 empty] | Actual |  |  |  | Post | NA | NA | 2013-10-03 | 2013-11-03 | NA | NA
5 | 1.2 | B.3 | Electrical Upgrading of Water Wells Systems | Omar Shatat | Planned | NS W 03-02/2013-GWSSSIP-Retendering |  | S | Post | NA | NA | 2013-02-01 | 2013-02-17 | NA | NA | 39876 | 2013-03-10 | 2013-09-06 | Electro Co. |  |  | 3200 | 43076 | 17570.25 | 25505.75 | Ongoing
[5 empty] | Actual |  |  |  | Post | NA | NA | 2013-04-04 | 2013-04-18 | NA | NA |  | 2013-05-15 | 2014-03-11
6 | 1.2 | B.4 | Electromechanical rehabilitation and upgrading of water wells including pumps replacement | Omar Shatat | Planned | NS W 01–02/2012-GWSREP |  | S | Post | NA | NA | 2012-02-15 | 2012-02-27 | NA | NA | 34809.6 | 2012-03-05 | 2012-06-03 | Al Abnia Al Haditha Co. |  |  | 4064.6 | 38874.2 | 38863.56 | 10.64 | Closed
[5 empty] | Actual |  |  |  | Post | NA | NA | 2012-02-15 | 2012-02-21 | NA | NA |  | 2012-03-04 | 2012-08-01
C. Upgrading and Maintenance of Wastewater Pumping Stations
7 | 1.4 | C.1 | Upgrading of Wastewater Pumping Stations in Gaza Strip & Electro and Mechanical Repairs and Refurbishment of Electrical Power Supply Generators for Wastewater Facilities | Omar Shatat | Planned |  |  | NCB 2 Lots | Post | NA | NA | 2013-07-06 | 2013-07-23 | NA | NA |  | 2013-08-08 | 2015-08-08
[5 empty] | Actual | NCBW 04a-08/2013-GWSSSIP |  |  | Post | NA | NA | 2013-08-28 | 2013-09-29 | NA | NA | 194410 |  | 1900-12-30 | Electro Co.
[6 empty] | NCBW 04b-08/2013-GWSSSIP |  |  | Post | NA | NA | 2013-08-28 | 2013-09-29 | NA | NA | 97275 |  | 1900-12-30 | Abed El Rahman Yasine Sons Shops
8 | 1.4 | C.2 | Electromechanical Maintenance for Sewage Lifting Stations and its associates & Upgrading of Wastewater Networks to Cope with the Pump Stations Upgrading | Omar Shatat | Planned | NCBW 05-08/2013-GWSSSIP |  | NCB 2 Lots | Post | NA | NA | 2013-07-06 | 2013-07-21 | NA | NA | 150000 | 2013-08-08 | 2015-08-08 | Electro Co.
[5 empty] | Actual |  |  |  | Post | NA | NA | 2013-08-28 | 2013-09-29 | NA | NA |  | 2013-10-28 | 2014-10-28
9 | 1.2 | C.3 | Electrical Service Contract for CMWU Water & Wastewater Facilities | Maged Zakout | Planned | NS W 02–02/2012-GWSREP |  | S | Post | NA | NA | 2012-02-15 | 2012-02-25 | NA | NA |  | 2012-03-01 | 2012-07-14 | Electro for Trade & Contracting Co. |  |  | -83 | 18417 | 18417 | 0 | Closed
[5 empty] | Actual |  |  |  | Post | NA | NA | 2012-02-15 | 2012-02-22 | NA | NA | 18500 | 2012-03-14 | 2012-11-09
D. Service Connections and Bulk Meters Replacement
10 | 1.3 | D.1 | Repair and Replacement of Water Meters |  | Planned |  |  | NCB | Post | NA | NA | 2014-05-16 | 2014-06-03 | NA | NA |  | 2014-06-23 | 2015-06-23
Actual
11 | 1.1 | D.2 | Replacement, Rehabilitation and Upgrading of Water Distribution Networks |  | Planned |  |  | NCB | Post | NA | NA | 2014-06-10 | 2014-06-26 | NA | NA |  | 2014-07-21 | 2015-01-17
Actual
12 | 1.1 | D.3 | Calibration and Modeling for Water Networks in Rafah and Deir Al Balah | Maher Al Najjar | Planned |  |  | S | Post | NA | NA | 2013-12-15 | 2014-01-14 | NA | NA | 40000 | 2014-02-08 | 2014-10-06
Actual
|  |  | Total Works |  | Plan | Total Budget
[5 empty] | Actual | Total Committed
S: Shopping. ~ NCB : National Competitive Bidding. ~ NA: Not Applicable. ~ Na: Not Available.
Formulas:
Bid Opening Date = [Bidding Period]+20
Contract Signing Date = [Bid Opening Date]+20
Contract Signing Date = [No-objection Date]+2
Contract Completion Date = [Contract Signing Date]+180
Bank No Objection on BD = [Submittal Date]+6
Bidding Period = [Bank No Objection on BD]+9
Bid Evaluation = [Bid Opening Date]+14
No-objection Date = [Bid Evaluation]+3
Note on D25: safaa elrabii: This contract shall be signed by the end of Feb. 2012 and paid retroactively
Note on D35: safaa elrabii: This contract shall be signed by the end of Feb. 2012 and paid retroactively

## Goods
Palestinian Water Authority PWA
Gaza Water Supply and Sewager Systems Improvement Project WSSSIP | [9 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | Bidding Period |  | Bid Evaluation |  | Contract Finalization |  |  |  | Contract Implementation |  | Variations |  | Payments |  | Conract Progress
No. | Comp. No. | Task No. | Description | Task Manager | Plan vs. Actual | Lot Number | Estimated US$ | Proc. Method | Prior or Post Review | Submittal Date | Bank No Objection on BD | Bid Invitation Date | Bid Opening Date | Submission Bid Eval Rpt | No-objection Date | Contract Amount in US$ | Contract Signing Date | Contract Completion Date | Supplier Name | Arrival of Goods | Inspection Final Acceptance | Total V.O. | Contract Final Amount | Total Paid | Total to be Paid | Notes
Goods
1 | 1.1 | A.1 | Supply of Electromechanical spare parts, equipments and materials for sewage lifting stations, fittings, fixtures and pipes for WW distribution networks and 2000 | Omar Shatat |  | NCB G 01-09/2011-WB-AFIII - Lot No. 1 |  | NCB | Prior | 2011-09-14 | 2011-10-02 | 2011-10-04 | 2011-11-01 | 2011-12-13 | 2011-12-22 | 59930 | 2012-01-04 | 2012-03-14 | Gemco |  |  | -3840 | 56090 | 56090 | 0 | Closed
[6 empty] | NCB G 01-09/2011-WB-AFIII - Lot No. 2 | [9 empty] | 33525 | 2012-01-04 | 2012-03-14 | Saqqa and Khudary |  |  |  | 33525 | 33525 | 0 | Closed
[6 empty] | NCB G 01-09/2011-WB-AFIII-Lot No. 3 | [9 empty] | 68650 | 2012-01-04 | 2012-03-14 | Abed El Aziz Abu Rabi |  |  |  | 68650 | 38350 | 30300 | Ongoing
2 | 1.1 | A.2 | Supply of electrical and mechanical equipment and spare parts for water wells and pumping facilities and Supply of electrical and mechanical equipment and spare parts for wastewater pumping and treatment facilities | Omar Shatat | Planned |  |  | NCB 2 Lots | Prior | 2013-04-15 | 2013-04-30 | 2013-05-02 | 2013-06-01 | 2013-06-16 | 2013-06-26 |  | 2013-06-29 | 2015-06-29 | Al Abnia Al Haditha Co. |  |  |  | 189725 | 168705 | 21020 | Ongoing
[5 empty] | Actual | NCB G 03A-03/2013-GWSSSIP |  | NCB |  | 2013-03-11 | 2013-04-10 | 2013-04-15 | 2013-05-15 | 2013-07-03 | 2013-07-13 | 189725 | 2013-07-16 | 2013-10-14
[6 empty] | NCB G 03B-03/2013-GWSSSIP |  | NCB |  | 2013-03-11 | 2013-04-10 | 2013-04-15 | 2013-05-15 | 2013-07-03 | 2013-07-13 | 40044 | 2013-07-16 | 2013-10-14 | Electro Company for General Trade & Contracting LTD |  |  | 0 | 40044 | 40044 | 0 | Closed
3 | 2.1 | B.1 | Supply To CMWU Central Warehouse Equipment and Tools | Omar Shatat | Planned |  |  | S | Post | NA | NA | 2013-05-10 | 2013-05-24 | NA | NA |  | 2013-06-18 | 2013-09-16
Actual
4 | 2.1 | B.2 | Supply CMWU Headquarter with Wooden Furniture | Ashraf Mushtaha | Planned |  |  | S | Post | NA | NA | 2014-01-15 | 2014-02-02 | NA | NA |  | 2014-02-28 | 2014-04-29
Actual
System Hardware & Software
5 |  | C.1 | Supply GIS Hardware & Software | Ashraf Mushtaha | Planned | NS G 06-07/2013-GWSSSIP-Retendring |  | S | Post | NA | NA | 2013-06-15 | 2013-07-02 | NA | NA |  | 2013-07-31 | 2013-12-28 | Jerusalem Co. |  |  | 0 | 45085 |  | 45085 | Ongoing
[5 empty] | Actual |  |  |  | Post | NA | NA | 2013-07-22 | 2013-07-28 | NA | NA | 45085 | 2013-08-25 | 2013-11-23
6 | 2.3 |  | Supply Fuel for Water and Wastewater Facilities | Omar Shatat | Planned | NS G 04-05/2013-GWSSSIP |  | S (Multiple) | Post | NA | NA | 2014-01-15 | 2014-02-14 | NA | NA |  | 2014-03-01 | 2014-05-30 | Bahlol & Salah for Petrol |  |  |  | 78300 | 78299.37 | 0.63 | Closed
[5 empty] | Actual |  |  |  | Post | NA | NA | 2013-05-06 | 2013-05-12 | NA | NA | 78300 | 2013-05-19 | 2013-09-16
|  |  | Total Works |  | Plan | Total Budget
[5 empty] | Actual | Total Committed
S: Shopping. ~ NCB : National Competitive Bidding. ~ NA: Not Applicable. ~ Na: Not Available.
Formulas:
Contract Completion Date = [Contract Signing Date]+70
Bank No Objection on BD = [Submittal Date]+15
Bidding Period = [Bank No Objection on BD]+2
Bid Opening Date = [Bidding Period]+30
Bid Evaluation = [Bid Opening Date]+15
No-objection Date = [Bid Evaluation]+10
Contract Signing Date = [No-objection Date]+3
Contract Signing Date = [Bid Opening Date]+25
Note on D7: safaa elrabii: These contracts were signed in 05/01/2012 and 16/01/2012 and shall be paid retroactively

## Consultancy Services 2011
Palestinian Water Authority PWA
Gaza Water Supply and Sewage Systems Improvement Project WSSSIP | [5 empty] | BASIC DATA |  |  | EOI |  | Preparation of TOR and RFP |  | Bidding Period |  | Technical Evaluation Report |  | FIN. | Combined Technical/ Financial Report & Contract Negotiation |  | Contract Award & Assignment Completion Date
No. | Comp. No. | Description | Task Manager | Plan vs. Actual | Package Number | Estimated US $ | Proc. Method | Prior or Post Review | EOI Date | EOI Closing Date | Submittal Date | Bank No-Objection Date | RFP Issuance Date | Proposal Submission Date | Submittal Date | Bank No Objection Date | Financial Opening Date | Submittal Date | Bank No Objection Date | Contract Amount in US$ | Contract Award Date | Assignment Completion Date | Consultant | Final Report Submittal Date | Final Report Acceptance
Cosultancy Services
1 | 2.2 | Consultancy Service for CMWU Documented Management System | Mamdouh Al Ghazali | Plan |  |  |  | Post | 2013-06-15 | 2013-06-29 | NA | NA | 2013-07-13 | 2013-08-12 | NA | NA | 2013-08-26 | NA | NA |  | 2013-08-31 | 2014-03-29
|  |  |  | Actual |  |  | QCBS
2 | 2.2 | Consultancy service for preparation of CMWU strategic plan | Maher Al Najjar | Plan | CS 03-10/2011 |  | IC | Prior | 2011-09-05 | 2011-09-10 | NA | NA | 2011-09-15 | 2011-09-25 | NA | NA | NA | 2011-10-05 | 2011-10-10 | 24000 | 2011-10-12 | 2012-01-10 | Dr. Refat Rostom
|  |  |  | Actual |  |  | IC |  | NA | NA | 2011-10-13 | 2011-10-18 | NA | NA | 2011-11-30 | 2011-12-13 | NA | 2012-01-09 | 2012-01-16 |  | 2012-01-18 | 2012-06-15 |  | 2012-02-12 | 2012-02-20
3 | 2.2 | Consultancy Services for Design of major water supply projects | Ahmad Shaker | Plan | CS 01-07/2011 |  | QCBS | Prior | 2011-03-15 | 2011-03-30 | 2011-08-10 | 2011-08-24 | 2011-08-29 | 2011-09-21 | 2011-09-28 | 2011-10-01 | 2011-10-03 | 2011-10-04 | 2011-10-07 | 30800 | 2011-10-12 | 2012-01-20 | Engineering and Consulting Management Center
|  |  |  | Actual |  |  | QCBS |  | 2011-08-10 | 2011-08-24 | 2011-10-03 | 2011-10-12 | 16/10/2011 | 13/11/2011 | 2011-12-07 | 14/12/2011 | 19/12/2011 | 2012-01-09 | 2012-01-16 |  | 2012-01-18 | 18-Arp-12 |  | 2012-02-02 | 2012-03-05
4 | 2.2 | Environmental & Social +Imapact Assessment | Maher Al Najjar | Plan | CS 04-10/2011 |  | CQS | Prior | 2011-07-15 | 2011-07-30 | 2011-08-24 | 2011-09-07 | 2011-09-12 | 2011-10-02 | 2011-10-09 | 2011-10-12 | 2011-10-14 | 2011-10-16 | 2011-10-20 | 26000 | 2011-10-25 | 2012-01-03 | Engineering and Consulting Management Center
|  |  |  | Actual |  |  | CQS |  | 2011-08-24 | 2011-09-08 | 2011-08-25 | 2011-09-08 | 2011-12-13 | 2011-12-26 | NA | NA | 2011-12-26 | 2012-01-11 | 2012-01-16 |  | 2012-01-18 | 2012-03-19 |  | 2012-02-06 | 2012-02-22
5 | 1.1 | Calibration and Modeling for Water Networks in Rafah and Deir Al Balah | Maher Al Najjar | Plan | CS 01-04/2013-GWSSSIP |  | QCBS | Prior | 2013-01-15 | 2013-01-29 | 2013-02-08 | 2013-02-13 | 2013-02-18 | 2013-03-18 | 2013-04-01 | 2013-04-06 | 2013-04-11 | 2013-04-14 | 2013-04-19 |  | 2013-04-22 | 2013-12-18
|  |  |  | Actual |  |  |  |  | 2013-05-28 | 2013-06-11 | 2013-07-11 | 2013-07-22 | 2013-07-23 | 2013-08-27 | 2013-09-17 | NA | Cancelled and Reallocated in Works catogary (Task no. D.3, Com. No. 1.1)
6 | 2.2 | Consultancy Services for Design of water and wastewater project | Ahmad Shaker | Plan |  |  | QCBS | Post | 2014-02-15 | 2014-03-01 | 2014-03-11 | 2014-03-16 | 2014-03-21 | 2014-04-18 | 2014-05-02 | 2014-05-07 | 2014-05-12 | 2014-05-15 | 2014-05-20 |  | 2014-05-23 | 2015-05-23
Actual
7 | 2.2 | NGEST O& M Consultancy | Maher Al Najjar | Plan |  |  | IC | Prior | 2013-08-20 | 2013-09-03 | 2013-09-13 | 2013-09-18 | 2013-09-23 | 2013-10-21 | 2013-11-04 | 2013-11-09 | 2013-11-14 | 2013-11-17 | 2013-11-22 |  | 2013-11-25 | 2014-11-25
Actual
8 | 3 | Auditing Services |  |  |  |  | LCS | To be implemented by MOF
9 | 3 | Monitoring & Evaluation Consultant | Maher Al Najjar |  |  |  | IC | Post | 2013-11-15 | 2013-11-29 | NA | NA | 2013-12-13 | 2014-01-10 | NA | NA | 2014-01-30 | NA | NA |  | 2014-03-01 | 2015-10-22
|  | Total Consultancy Services |  | Plan
Actual
~ IC: Individual Consultants. ~ CQS: Selection based on Cosultant Qualification. ~ SS: Single Source Selection. ~ NA: Not Applicable. ~ Na: Not Available.
Formulas:
EOI Closing Date = [EOI Date]+14
RFP Issuance Date = [EOI Closing Date]+14
RFP Issuance Date = [Bank No-Objection Date]+5
Proposal Submission Date = [RFP Issuance Date]+30
Proposal Submission Date = [Bank No-Objection Date]+28
Financial Opening Date = [Proposal Submission Date]+14
Financial Opening Date = [Bank No Objection Date]+2
Contract Award Date = [Financial Opening Date]+5
Contract Award Date = [Bank No Objection Date]+2
Assignment Completion Date = [Contract Award Date]+210
Submittal Date = [Proposal Submission Date]+10
Submittal Date = [Financial Opening Date]+1
Bank No Objection Date = [Submittal Date]+5
Bank No-Objection Date = [Submittal Date]+14
Note on C9: safaa elrabii: Paid Retroactively
Note on C12: safaa elrabii: Paid Retroactively
Note on C15: safaa elrabii: Paid Retroactively
Note on C18: safaa elrabii: Paid Retroactively