## Works & Goods
Ln. # | Status P R/A d/ | Contract Reference # Standard Prefix "KOS-IDEP/H3420/" removed from below listings | Comp. | Description | Estim. No. of Lots | 2012-10-16 14:49 |  | Proc. Method | WB Review | Schedule (dd-Mmm-yy) | [22 empty] | Comments | Procure- ment Accounts
[6 empty] | Appraisal Estimates P (planned) Enter New Estimates in EUR Under R/A Rows below |  |  |  | Prep. of Doc. | Int. /a | WB "No Objection" | Int. /a | Advert- izing | Int. /a | Issue of Documents | Int. /a | Sub- mission of Bids | Int. /a | Evalu- ation & Recomm. | Int. /a | WB "No Objection" | Int. /a | Contract Award | Int. /a | Contract Signature | Int. /a | Start | Exec. /b | Comple- tion | Pysical Progress % | Payment to vendor %
Procurement Steps (1-11)
[6 empty] | USD | EUR |  |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 | 12 | 13
1 |  | COMPONENT 1. STRENGTHENING ORGANIZATION & FINANCING OF EDUCATION SYSTEM
2 |  | GOODS
3 | P | C1.2/GD-SH/10-01 | 1.2 | Developing the Software for Municipal-to School Budget Allocation | 1 | 40540 | 30000 | SH | PRIOR | 2010-10-21 | 14 | 2010-11-04 | 7 | 2010-11-11 | 3 | 2010-11-14 | 14 | 2010-11-28 | 7 | 2010-12-05 | 14 | 2010-12-19 | 2 | 2010-12-21 | 7 | 2010-12-28 | 7 | 2010-12-22 | 374 | 2011-12-31
4 | R/A | Hardsoft Integration |  |  |  |  | 49325 |  |  | 2010-10-21 |  | 2010-11-16 |  | 2010-11-22 |  | 2010-11-22 |  | 2010-12-06 |  | 2010-12-13 |  | 2010-12-17 |  | 2010-12-22 |  | 2010-12-22 |  | 2010-12-22 |  | 18-Oct-11 | 75 | 0 | Completed
5 | R/A | Hardsoft Integration |  | Amendment #1 extending completion date | [5 empty] | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 18-Oct-11 |  | 18-Oct-11 |  | 28-Dec-11 | 100 | 100 | Completed
6 | P | C1.2/GD-SH/10-02 | 1.2 | Layout and Printing of Manual for School budget and Finances |  |  | 4500 | SH | PRIOR | 2010-11-25 | 14 | 2010-12-09 | 7 | 2010-12-16 | 3 | 2010-12-19 | 14 | 2011-01-02 | 7 | 2011-01-09 | 14 | 2011-01-23 | 2 | 2011-01-25 | 7 | 2011-02-01 | 7 | 2011-02-08 | 30 | 2011-03-10
7 | R/A | Blendi |  |  |  |  | 3900 |  |  | 2010-11-26 |  | 2010-12-07 |  | 2010-12-08 |  | 2010-12-08 |  | 2010-12-23 |  | 2010-12-24 |  | 2010-12-30 |  | 2011-01-10 |  | 2011-01-10 |  | 2011-01-10 |  | 2011-05-12 | 100 | 100 | Completed
8 | P | C1.2/GD/SH/11-03 | 1.2 | Hardware for server for school finance |  |  | 15000 | SH | PRIOR | 2011-05-16 | 14 | 2011-05-30 | 7 | 2011-06-06 | 3 | 2011-06-09 | 14 | 2011-06-23 | 7 | 2011-06-30 | 14 | 2011-07-14 | 2 | 2011-07-16 | 7 | 2011-07-23 | 7 | 2011-07-30 | 30 | 2011-08-29
9 | R/A | Hardsoft systems |  |  |  |  | 36970 |  |  | 2011-05-18 |  | 2011-06-02 |  | 2011-06-06 |  | 2011-06-06 |  | 2011-06-20 |  | 2011-06-21 |  | 2011-06-29 |  | 2011-07-01 | 0 | 2011-07-01 | 0 | 2011-07-01 | 31 | 2011-08-01 | 100 | 100 | Completed
10 | P | C1.3/GD-ICB/SDG-01 | 1.3 | IT equipment for SDG | 1 |  | 199301.39 | ICB | PRIOR | 2011-12-30 | 14 | 2012-02-14 | 7 | 2012-02-21 | 3 | 2012-02-24 | 42 | 2012-04-06 | 7 | 2012-04-13 | 14 | 2012-06-15 | 2 | 2012-06-17 | 7 | 2012-06-24 | 7 | 2012-07-01 | 30 | 2012-09-12
11 | R/A | JV Interadria and Telefoniku |  |  |  |  | 164946.98 |  |  | 2011-12-30 |  | 2012-02-14 |  | 2012-02-16 |  | 2012-02-16 |  | 2012-04-23 |  | 2012-05-14 |  | 2012-07-21 |  | 2012-07-12 |  | 2012-07-12 |  | 2012-07-12
12 | p | C1.3/GD-ICB/SDG-02 | 1.3 | Teaching aids for SDG | 1 |  | 61738.1 | NCB | PRIOR | 2012-01-13 | 14 | 2012-01-27 | 7 | 2012-02-03 | 3 | 2012-02-06 | 42 | 2012-07-06 | 7 | 2012-06-15 | 14 | 2012-06-29 | 2 | 2012-07-01 | 7 | 2012-07-08 | 7 | 2012-07-15 | 30 | 2012-08-14
13 | R/A | [8 empty] | 2012-02-29 |  | 2012-03-13 |  | 2012-04-06 |  | 2012-04-12 |  | 2012-05-25 |  | 2012-05-29 |  | 2012-06-13 |  | NA |  | NA |  | NA |  | NA
14 | R/A |  |  | Rebiding Procedure | [5 empty] | 2012-06-21 |  | 2012-05-13 |  | 2012-06-22 |  | 2012-06-25 |  | 2012-07-06
15 | P | C1.3/GD-SH/SDG-04 | 1.3 | Purchasing of books for SDG | 1 |  | 21444.6 | SH | PRIOR | 2012-01-06 | 14 | 2012-01-20 | 7 | 2012-01-27 | 3 | 2012-01-30 | 7 | 2012-02-06 | 7 | 2012-02-13 | 7 | 2012-02-20 | 2 | 2012-02-22 | 1 | 2012-02-23 | 1 | 2012-02-24 | 8 | 2012-03-03
16 | R/A | Korabi |  |  |  |  | 14331.4 |  |  | 2012-01-06 |  | 2012-01-09 |  | 2012-01-12 |  | 2012-01-12 |  | 2012-01-26 |  | 2012-01-31 |  | 2012-02-02 |  | 2012-02-03 |  | 2012-02-03 |  | 2012-02-03 |  | 2012-03-28 | 100 | 100 | Completed
17 | P | C1.3/GD-SH/SDG-03 | 1.3 | Purchasing of music instruments for SDG | 1 |  | 38527 | SH | PRIOR | 2012-01-20 | 14 | 2012-02-03 | 7 | 2012-02-10 | 3 | 2012-02-13 | 14 | 2012-02-27 | 7 | 2012-03-05 | 14 | 2012-03-19 | 2 | 2012-03-21 | 7 | 2012-03-28 | 7 | 2012-04-04 | 13 | 2012-06-08
18 | R/A | Star Graf |  |  |  |  | 52878 |  |  | 2012-02-16 |  | 2012-02-22 |  | 2012-02-28 | 0 | 2012-02-28 | 0 | 2012-03-12 | 0 | 2012-04-04 |  | 2012-04-30 |  | 2012-05-04 |  | 2012-05-08 |  | 2012-05-08 |  | 2012-06-11 | 100 |  | Completed
19 | P | C1.3/GD-ICB/SDG-05 | 1.3 | IT equipment for SDG for Round III | 1 |  | 98033.64 | ICB | PRIOR | 2012-08-10 | 14 | 2012-08-24 | 7 | 2012-08-31 | 3 | 2012-09-03 | 28 | 2012-10-01 | 7 | 2012-10-08 | 14 | 2012-10-22 | 2 | 2012-10-24 | 7 | 2012-10-31 | 7 | 2012-11-07
20 | R/A
21 | P | Component 1. Subtotals |  |  | 1 | 40540 | 370511.09
22 | R/A |  |  |  |  | 0 | 322351.38
23 |  | COMPONENT 2. BUILDING INSTITUTIONS & MANAGEMENT CAPACITY IN PRIMARY & SECONDARY EDUCATION
24
25 |  | GOODS
26 | P | C2.1/GD-SH/09-06 | 2.1 | Developing a sofware for teacher licencing | 1 |  | 35000 | SH | PRIOR | 2010-04-12 | 14 | 2010-04-26 | 7 | 2010-05-03 | 3 | 2010-05-06 | 14 | 2010-05-20 | 7 | 2010-05-27 | 14 | 2010-06-10 | 2 | 2010-06-12 | 7 | 2010-06-19 | 7 | 2010-08-12 | 460 | 2011-11-15
27 | R/A | Hardsoft Integration |  |  |  |  | 37000 |  |  | 2010-04-12 |  | 2010-06-25 |  | 2010-07-01 |  | 2010-07-01 |  | 2010-07-09 |  | 2010-07-20 |  | 2010-07-31 |  | 2010-08-12 |  | 2010-08-12 |  | 2010-08-12 |  | 2011-11-15 | 100 | 100 | Completed
28 | P | C2.1/GD-SH/11-07 | 2.1 | Hardware for server for teacher licesning database |  |  | 15000 | SH | PRIOR | 2011-05-16 | 14 | 2011-05-30 | 7 | 2011-06-06 | 3 | 2011-06-09 | 14 | 2011-06-23 | 7 | 2011-06-30 | 14 | 2011-07-14 | 2 | 2011-07-16 | 7 | 2011-07-23 | 7 | 2011-07-30 | 30 | 2011-08-29
29 | R/A | Hardsoft systems |  |  |  |  | 18485 |  |  | 2011-05-18 |  | 2011-06-02 |  | 2011-06-06 |  | 2011-06-06 |  | 2011-06-20 |  | 2011-06-21 |  | 2011-06-29 |  | 2011-07-01 | 0 | 2011-07-01 | 0 | 2011-07-01 | 31 | 2011-08-01 | 100 | 100 | Completed
30 | P | C2.1/GD-SH/12-02 | 2.1 | Teacher license production support hardware and software | 1 |  | 29000 | SH | PRIOR | 2012-09-03 | 14 | 2012-09-17 | 7 | 2012-09-24 | 3 | 2012-09-27 | 14 | 2012-10-11 | 7 | 2012-10-18 | 14 | 2012-11-01 | 2 | 2012-11-03 | 7 | 2012-11-10 | 7 | 2012-11-17 | 31 | 2012-12-18
31 | R/A
32 | P | C2.1/GD-SH/11-09 | 2.1 | Computers for 7 regional +1 main offices for licensing | 1 |  | 8000 | SH | PRIOR | 2012-01-09 | 7 | 2012-01-16 | 2 | 2012-01-18 | 1 | 2012-01-19 | 7 | 2012-01-26 | 7 | 2012-02-02 | 2 | 2012-02-04 | 2 | 2012-02-06 | 1 | 2012-02-07 | 1 | 2012-02-08 | 12 | 2012-02-20
33 | R/A | SI Consulting |  |  |  |  | 6680 |  |  | 2011-12-27 |  | 2012-01-06 |  | 2012-01-10 |  | 2012-01-10 |  | 2012-01-20 |  | 2012-01-25 |  | 2012-02-05 |  | 2012-02-10 |  | 2012-02-10 |  | 2012-02-10 |  |  | 100 | 100 | completed
34 | P | C2.3/GD-SH/09-01 | 2.3 | Computers & Peripherals for MED | 1 | 6400 | 4736 | SH | PRIOR | 2009-01-07 | 14 | 2009-01-21 | 7 | 2009-01-28 | 3 | 2009-01-31 | 14 | 2009-02-14 | 7 | 2009-02-21 | 14 | 2009-03-07 | 2 | 2009-03-09 | 7 | 2009-03-16 | 7 | 2009-03-23 | 60 | 2009-05-22 |  |  |  | COM
35 | R/A | Illir Kosova |  |  |  |  | 32967 |  |  | 2009-10-01 |  | 2009-10-15 |  | 2009-10-21 |  | 2009-12-11 |  | 2009-12-18 |  | 2010-01-06 |  | 2010-02-23 |  | 2010-03-10 |  | 2010-03-10 | 0 | 2010-03-10 | 45 | 2010-04-29 | 100 | 100 | Completed
36 | P | C2.3/GD-SH/12-03 | 2.3 | Printing of brochures for the parents and publication of test models | 1 | 41800 | 20000 | SH | PRIOR | 2012-10-01 | 14 | 2012-10-15 | 7 | 2012-10-22 | 3 | 2012-10-18 | 14 | 2012-11-01 | 7 | 2012-11-08 | 14 | 2012-11-22 | 2 | 2012-11-24 | 7 | 2012-12-01 | 7 | 2012-12-08 | 30 | 2013-01-07 |  |  |  | PUB
37 | R/A
38 | P | C2.3/GD-SH/09-03 | 2.3 | Software (assessment analysis) Software upgrades (for assessment) and specialized equipment (optical readers) | 1 | 88600 | 65564 | SH | PRIOR | 2009-10-05 | 14 | 2009-10-19 | 7 | 2009-10-26 | 3 | 2009-10-29 | 14 | 2009-11-12 | 7 | 2009-11-19 | 14 | 2009-12-03 | 2 | 2009-12-05 | 7 | 2009-12-12 | 7 | 2009-12-19 | 30 | 2010-01-18 |  |  | Combined beyond the Shopping threshold. Requested waiver to award shopping contract. | COM
39 | R/A | Comtrade Computers |  |  |  |  | 70239.52 |  |  | 2010-02-04 |  | 2010-02-19 |  | NA |  | 2010-03-31 |  | 2010-04-09 |  | 2010-04-20 |  | 2010-05-10 |  | 2010-05-13 |  | 2010-05-13 |  | 2010-05-13 | 45 | 2010-06-28 | 100 | 100 | Completed
40 | P | C2.3/GD-SH/12-01 | 2.3 | Development of the Item Bank Software | 1 |  | 30000 | SH | PRIOR | 2012-01-09 | 14 | 2012-01-23 | 7 | 2012-01-30 | 3 | 2012-02-02 | 14 | 2012-02-16 | 7 | 2012-06-15 | 14 | 2012-06-29 | 2 | 2012-07-01 | 7 | 2012-07-06 | 7 | 2012-07-13 | 30 | 2013-06-07 |  |  | Not Planned | COM
41 | R/A | Abellardo |  |  |  |  | 37128 |  |  | 2012-04-13 |  | 2012-04-27 |  | 2012-04-30 |  | 2012-04-30 |  | 2012-05-16 |  | 2012-05-23 |  | 2012-06-06 |  | 2012-06-07 |  | 2012-06-07 |  | 2012-06-07 |  |  |  |  | Under Implementation
42 | P | C2.3/GD-SH/12-02 | 2.3 | Hardware Support for Item Bank Database Application | 1 |  | 20000 | SH | PRIOR | 2012-05-16 | 14 | 2012-06-10 | 7 | 2012-06-17 | 3 | 2012-06-15 | 14 | 2012-06-29 | 7 | 2012-07-06 | 14 | 2012-07-20 | 2 | 2012-07-22 | 7 | 2012-07-29 | 7 | 2012-08-05 | 30 | 2012-08-30 |  |  | Not Planned
43 | R/A | SI Consulting |  |  |  |  | 21066 |  |  | 2012-05-16 |  | 2012-06-08 |  | 2012-06-15 |  | 2012-05-15 |  | 2012-06-29 |  | 2012-07-04 |  | 2012-07-18 |  | 2012-07-24 |  | 2012-07-30 |  | 2012-07-30 |  |  |  |  | Under Implementation
44 | P | C2.4/GD-SH/09-01 | 2.4 | Computer systems for EMIS | 1 | 25800 | 19092 | SH | PRIOR | 2009-08-03 | 14 | 2009-08-17 | 7 | 2009-08-24 | 3 | 2009-08-27 | 14 | 2009-09-10 | 7 | 2009-09-17 | 14 | 2009-10-01 | 2 | 2009-10-03 | 7 | 2009-10-10 | 7 | 2009-10-17 | 30 | 2009-11-16 |  |  |  | COM
45 | R/A | Illir Kosova |  |  |  |  | 27940 |  |  | 2009-12-05 |  | 2009-12-07 |  | 2009-12-08 |  | 2009-12-17 |  | 2009-12-28 |  | 2010-01-06 |  | 2010-02-07 |  | 2010-03-08 |  | 2010-03-08 |  | 2010-03-08 | 30 | 2010-04-29 | 100 | 100 | Completed
46 | p | C2.4/G-ICB/09-01 | 2.4 | Firm - EMIS software upgrade & training at the national, municipal and school levels | 1 | 88100 | 200000 | ICB | PRIOR | 2009-11-15 | 14 | 2009-11-29 | 7 | 2009-12-06 | 14 | 2009-12-20 | 14 | 2010-01-03 | 7 | 2010-01-10 | 14 | 2010-01-24 | 2 | 2010-01-26 | 7 | 2010-02-02 | 7 | 2010-10-27 |  | 2012-05-30
47 | R/A | Neocom & Edusoft |  |  |  |  | 108000 |  |  | 2010-03-01 |  | 2010-03-15 |  | 2010-07-22 |  | 2010-07-26 |  | 2010-08-30 |  | 2010-09-18 |  | 2010-09-29 |  | 2010-10-27 |  | 2010-10-27 | 0 | 2010-10-27 |  | 2012-09-29 | 100 | 100 | Completed
48 | R/A | Neocom & Edusoft |  | Amendment #1 modification of original contract |  |  | 27000 |  |  | 2011-10-28 |  | 2011-11-17 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-11-29 |  | 2011-11-30 |  | 2011-11-30 |  | 2012-05-30 | 100 | 100 | Completed
49 | P | C2.4/GD-SH/11-02 | 2.4 | USB for EMIS |  |  | 6000 | SH | PRIOR | 2011-06-01 | 14 | 2011-06-15 | 7 | 2011-06-22 | 14 | 2011-07-06 | 14 | 2011-07-20 | 7 | 2011-07-27 | 14 | 2011-08-10 | 2 | 2011-08-12 | 7 | 2011-08-19 | 7 | 2011-08-26 | 30 | 2011-09-25
50 | R/A | Hardsoft systems |  |  |  |  | 8950 |  |  | 2011-07-05 |  | 2011-08-14 |  | 2011-08-14 |  | 2011-08-01 |  | 2011-08-01 |  | 2011-08-05 |  | 2011-08-12 |  | 2011-08-16 |  | 2011-08-16 | 0 | 2011-08-16 | 16 | 2011-09-01 | 100 | 100 | Completed
51 | P | C2.4/GD-SH/11-03 | 2.4 | Backup software for three servers of EMIS | 1 |  | 8000 | SH | PRIOR | 2011-11-15 | 14 | 2011-11-29 | 7 | 2011-12-06 | 14 | 2011-12-20 | 14 | 2012-01-03 | 7 | 2012-01-10 | 14 | 2012-01-24 | 2 | 2012-01-26 | 7 | 2012-02-02 | 7 | 2012-02-09 | 30 | 2012-02-10
52 | R/A | SI Consulting |  |  |  |  | 8850 |  |  | 2011-11-15 |  | 2011-12-06 |  | 2011-12-07 |  | 2011-12-07 |  | 2011-12-21 |  | 2011-12-28 |  | 2012-01-04 |  | 2012-01-10 |  | 2012-01-10 |  | 2012-01-10 |  | 2012-02-27 | 100 | 100 | Completed
53 | P | C2.5/GD-SH/09-01 | 2.5 | IT equipment for the PCT | 1 | 13200 | 9768 | SH | PRIOR | 2008-11-30 | 14 | 2008-12-14 | 7 | 2008-12-21 | 3 | 2008-12-24 | 14 | 2009-01-07 | 7 | 2009-01-14 | 14 | 2009-01-28 | 2 | 2009-01-30 | 7 | 2009-02-06 | 7 | 2009-02-13 | 60 | 2009-04-14 |  |  |  | COM
54 | R/A | Comtrade Computers |  |  |  |  | 16610.38 |  |  | 2008-11-07 |  | 2008-12-04 |  | 2008-12-05 |  | 2008-12-10 |  | 2008-12-22 |  | 2008-12-25 |  | 2009-01-12 |  | 2009-01-14 |  | 2009-01-14 |  | 2009-01-14 | 90 | 2009-04-01 | 100 | 100 | Completed
55 | P | C2.5/GD-SH/10-02 | 2.5 | IT equipment for the PCT | 1 | 13200 | 2800 | SH | PRIOR | 2008-11-30 | 14 | 2008-12-14 | 7 | 2008-12-21 | 3 | 2008-12-24 | 14 | 2009-01-07 | 7 | 2009-01-14 | 14 | 2009-01-28 | 2 | 2009-01-30 | 7 | 2009-02-06 | 7 | 2009-02-13 | 60 | 2009-04-14 |  |  |  | COM
56 | R/A | Comtrade Computers |  |  |  |  | 3521.42 |  |  | 2010-06-09 |  | 2010-06-23 |  | 2010-06-25 |  | 2010-07-14 |  | 2010-07-26 |  | 2010-08-19 |  | 2010-08-25 |  | 2010-08-27 |  | 2010-08-27 |  | 2010-08-27 | 30 | 2010-09-27 | 100 | 100 | Completed
57 | P | C2.5/GD-SH/09-03 | 2.5 | Office furniture for the PCT | 1 | 8500 | 6290 | SH | PRIOR | 2009-01-07 | 14 | 2009-01-21 | 7 | 2009-01-28 | 3 | 2009-01-31 | 14 | 2009-02-14 | 7 | 2009-02-21 | 14 | 2009-03-07 | 2 | 2009-03-09 | 7 | 2009-03-16 | 7 | 2009-03-23 | 30 | 2009-04-22 |  |  |  | OEF
58 | R/A | SM Commerce |  |  | 0 |  | 6088 |  |  | 2009-01-07 |  | 2009-02-03 |  |  |  | 2009-03-10 |  | 2009-02-20 |  | 2009-02-24 |  | 2009-03-04 | 2 | 2009-03-06 | 0 | 2009-03-06 | 0 | 2009-03-06 | 1 | 2009-03-06 | 100 | 100 | Completed
59
60 | P | Component 2. Subtotals |  |  | 9 | 285600 | 459250
61 | R/A |  |  |  | 0 | 0 | 409459.32
62
63 |  | COMPONENT 3. CREATING CONDITIONS TO INTRODUCE EFFICIENT DESIGNS IN KOSOVO'S SCHOOLS
64
65 |  | GOODS
66 | P | C3.1/GD-SH/09-01 | 3.1 | Rent for 7 GPS devices | 1 | 2200 |  | SH | PRIOR | 2009-12-10 | 14 | 2009-12-24 |  | NA | 3 | 2009-12-27 | 14 | 2010-01-10 | 7 | 2010-01-17 | 14 | 2010-01-31 | 2 | 2010-02-02 | 7 | 2010-02-09 | 7 | 2010-02-16 | 30 | 2010-03-18 |  |  |  | COM
67 | R/A |  |  | Incorporated under CMC contract | 0
68 | P | C3.1/GD-SH/09-04 | 3.1 | Software (GIS, Office, Photoshop) Computers and color printer | 1 | 32700 |  | SH | PRIOR | 2010-01-03 | 14 | 2010-01-17 |  | NA | 3 | 2010-01-20 | 14 | 2010-02-03 | 7 | 2010-02-10 | 14 | 2010-02-24 | 2 | 2010-02-26 | 7 | 2010-03-05 | 7 | 2010-03-12 | 30 | 2010-04-11 |  |  |  | COM
69 | R/A |  |  | Subsumed under the Invertory Taker's Contract | 0
70 | P | C3.1/GD-SH/12-01 | 3.1 | Design and Layout of the Guideline on School Facilities Design- Norms and Standards |  |  | 1000 | SH | PRIOR | 2012-01-12 | 14 | 2012-01-26 | 7 | 2012-02-02 | 3 | 2012-02-05 | 14 | 2012-02-19 | 7 | 2012-02-26 | 14 | 2012-03-11 | 2 | 2012-03-13 | 7 | 2012-03-20 | 7 | 2012-03-27 | 60 | 2012-08-31
71 | R/A | Trembelat |  |  |  |  | 2260 |  |  | 2012-03-28 |  | 2012-04-02 |  | 2012-04-03 |  | 2012-04-03 |  | 2012-04-18 |  | 2012-03-05 |  | 2012-05-09 |  | 2012-05-14 |  | 2012-05-14 |  | 2012-05-14 |  | 2012-06-04 |  |  | Completed
72 | R/A | Trembelat |  | Amendment #1 extending completion date | [5 empty] | 2012-06-21 |  | 2012-06-26 |  | NA |  | NA |  | NA |  | NA |  | 2012-06-26 |  | 2012-06-26 |  | 2012-06-26 |  | 2012-06-26 |  |  |  |  | Under Implementation
73 | R/A | Trembelat |  | Amendment #2 extending completion date | [5 empty] | 2012-08-17 |  |  |  | NA |  | NA |  | NA |  | NA
74 | P | C3.2/GD-SH/12-02 | 3.2 | Printing of the Guideline on School Facilities Design- Norms and Standards |  |  | 2000 | SH | PRIOR | 2012-03-28 | 14 | 2012-04-11 | 7 | 2012-04-18 | 3 | 2012-04-21 | 14 | 2012-05-05 | 7 | 2012-05-12 | 14 | 2012-05-26 | 2 | 2012-05-28 | 7 | 2012-06-04 | 7 | 2012-06-11 | 60 | 2012-09-30
75 | R/A | Grafika Rezniqi |  |  |  |  | 1829 |  |  | 2012-03-28 |  | 2012-04-02 |  | 2012-04-03 |  | 2012-04-03 |  | 2012-04-19 |  | 2012-05-03 |  | 2012-05-14 |  | 2012-05-28 |  | 2012-05-28 |  | 2012-05-28 |  | 2012-06-18 |  |  | Completed
76 | R/A | Grafika Rezniqi |  | Amendment #1 extending completion date | [5 empty] | 2012-06-21 |  | 2012-06-26 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-06-26 |  | 2012-06-26 |  | 2012-06-26 |  |  |  |  | under implementation
77 | R/A | Grafika Rezniqi |  | Amendment #2 extending completion date | [5 empty] | 2012-08-17 |  |  |  | NA |  | NA |  | NA |  | NA |  | NA
78 | P | C3.2/GD-SH/10-01 | 3.2 | Computers & Peripherals and Software | 1 | 11400 | 10000 | SH | PRIOR | 2010-06-15 | 14 | 2010-06-29 | 7 | 2010-07-06 | 3 | 2010-07-09 | 14 | 2010-07-23 | 7 | 2010-07-30 | 14 | 2010-08-13 | 2 | 2010-08-15 | 7 | 2010-08-22 | 7 | 2010-08-29 | 30 | 2010-09-28 |  |  |  | COM
79 | R/A | Comtrade Computers |  |  | 0 |  | 7483.21 |  |  | 2010-06-15 |  | 2010-06-23 |  | 2010-06-25 |  | 2010-07-14 |  | 2010-07-26 |  | 2010-08-19 |  | 2010-08-25 |  | 2010-08-27 | 0 | 2010-08-27 | 0 | 2010-08-27 | 30 | 2010-09-27 | 100 | 100 | Completed
80 | p | C3.2/GD-SH/10-02 | 3.2 | Auto Cad 2011 | 1 | 6081 | 4500 | SH | PRIOR | 2010-08-19 | 14 | 2010-09-02 | 7 | 2010-09-09 | 3 | 2010-09-12 | 14 | 2010-09-26 | 7 | 2010-10-03 | 14 | 2010-10-17 | 2 | 2010-10-19 | 7 | 2010-10-26 | 7 | 2010-11-02 | 30 | 2010-12-02
81 | R/A | Comtrade Computers |  |  |  |  | 3991 |  |  | 2010-08-19 |  | 2010-08-25 |  | 2010-08-27 |  | 2010-08-27 |  | 2010-09-10 |  | 2010-09-18 |  | 2010-09-29 |  | 2010-10-15 | 0 | 2010-10-15 | 0 | 2010-10-15 | 30 | 2010-11-15 | 100 | 100 | Completed
82 | P | C3.3/GD-ICB/12-01 | 3.3 | Equipment for the model Basic Education School (0-9) | 4 | 164600 | 122840 | ICB | PRIOR | 2012-07-20 | 45 | 2012-09-03 | 3 | 2012-09-06 | 2 | 2012-09-08 | 30 | 2012-10-08 | 14 | 2012-10-22 | 10 | 2012-11-01 | 2 | 2012-11-03 | 2 | 2012-11-05 | 7 | 2012-11-12 | 120 | 2013-03-12 |  |  |  | COM
83 | R/A |  |  |  | 0
84 | P | C3.3/GD-NCB/12-02 | 3.3 | Furniture for the model Basic Education School (0-9) | 3 | 81000 | 200000 | NCB | PRIOR | 2012-07-20 | 45 | 2012-09-03 | 10 | 2012-09-13 | 3 | 2012-09-06 | 2 | 2012-09-08 | 30 | 2012-10-08 | 10 | 2012-10-18 | 10 | 2012-10-28 | 2 | 2012-10-30 | 2 | 2012-11-01 | 120 | 2013-03-01 |  |  |  | COM
85 | R/A |  |  |  | 0
86 |  | WORKS
87 | P | C3.3/WK-ICB/11-01 | 3.3 | Basic Education Model Primary School (Grades 0-9) | 1 | 1650300 | 1500000 | ICB | PRIOR | 2011-10-31 | 1 | 2011-11-01 | 2 | 2011-11-03 | 6 | 2011-11-09 | 60 | 2012-01-08 | 14 | 2012-01-22 | 17 | 2012-06-20 | 8 | 2012-06-29 | 3 | 2012-07-02 | 14 | 2012-07-16 | 468 | 2013-06-30 |  |  |  | CW
88 | R/A | Standard |  |  |  | 0 | 2480942.47 |  |  | 2011-11-21 |  | 2012-01-26 |  | 2012-01-28 |  | 2012-01-02 |  | 2012-03-16 |  | 2012-04-03 |  | 2012-06-20 |  | 2012-06-29 |  | 2012-06-29 |  | 2012-06-29 |  |  |  |  | under implementation
89
90 | P | Component 3. Subtotals |  |  | 12 | 1948281 | 1838340
91 | R/A |  |  |  | 0 | 0 | 2494676.68
92 |  | COMPONENT 4. FINANCING MECHANISMS FOR HIGHER EDUCATION
93 |  | GOODS
94 | P | C4.2/GD-SH/10-01 | 4.2 | Publication of feasibility study | 1 | 18300 | 15000 | SH | PRIOR | 2010-11-10 | 14 | 2010-11-24 |  | NA | 3 | 2010-11-27 | 14 | 2010-12-11 | 7 | 2010-12-18 | 14 | 2011-01-01 | 2 | 2011-01-03 | 7 | 2011-01-10 | 7 | 2011-01-17 | 30 | 2011-02-16 |  |  |  | PUB
95 | R/A | Rrota |  |  | 0 |  | 2000 |  |  | 2010-11-05 |  | 2010-11-11 |  | 2010-11-12 |  | 2010-11-12 |  | 2010-11-26 |  | 2010-12-03 |  | 2010-12-10 |  | 2010-12-13 | 0 | 2010-12-13 | 0 | 2010-12-13 | 133 | 2011-04-25 | 100 | 100 | Completed
96
97 | P | Component 4. Subtotals |  |  | 1 | 18300 | 15000
98 | R/A |  |  |  | 0 | 0 | 2000
Legend: |  |  |  |  | Conditional Formatting:
ICB = International Competitive Bidding (in accordance with section 2 of the Guidelines) |  |  |  |  | Red Text Rows: |  | = R/A Revised/Actuals
LIB = Limited International Bidding (in accordance with section 3.2 of the Guidelines) |  |  |  |  | Yellow Columns: |  | Cell turns red if planned date has passed
NCB = National Competitive Bidding (in accordance with section 3.3 of the Guidelines) | [6 empty] | Cell turns normal again if cell for R/A (revised/actual) date is filled in.
SH = Shopping (in accordance with section 3.5 of the Guidelines) |  |  |  |  | Condition 1:
MNL = In accordance with the procedures of the Grants Manual |  |  |  |  | Cell value is less than of equal to cell below it (R/A)
NA = Not applicable
OTHER = Direct expenditures |  |  |  |  | Condition 2:
Cell value is less than the "now" cell (G$2)
Notes:
a/ Interval for preparation or clearance (in days); working document PP only
b/ Number of days to execute the contract; working document PP only
c/ Estimates include price contingencies
d/ Status: P=Planned (original scope and estimate); R/A=Revised or Actual
Prior Review:
All ICB contracts, first two NCB contracts, and first two shopping contracts irrespective of cost
All direct contracting (if any)
|  |  |  | Database Subtotals Tool | 49 | 4504362 | 10482347
Exchange rate used on November 17, 2010 = 0.74
Formulas:
WB "No Objection" = [Prep. of Doc.]+[Int. /a]
WB "No Objection" = [Evalu- ation & Recomm.]+[Int. /a]
Advert- izing = [WB "No Objection"]+[Int. /a]
Issue of Documents = [Advert- izing]+[Int. /a]
Issue of Documents = [WB "No Objection"]+[Int. /a]
Sub- mission of Bids = [Issue of Documents]+[Int. /a]
Evalu- ation & Recomm. = [Sub- mission of Bids]+[Int. /a]
Contract Award = [WB "No Objection"]+[Int. /a]
Contract Signature = [Contract Award]+[Int. /a]
Comple- tion = [Start]+[Exec. /b]
Comple- tion = [Exec. /b]+[Start]
Start = [Contract Signature]+[Int. /a]

## Consultants
Ln. # | Status P R/A d/ | Contract Reference # Standard Prefix "KOS-IDEP/H3420/" removed from below listings | Comp. | Activity | 2012-10-16 14:49 |  | Proc. Method | WB Review | Schedule (dd-Mmm-yy) | [38 empty] | Comments
[5 empty] | Appraisal Estimates P (planned) Enter New Estimates in EUR Under R/A Rows below |  |  |  | Prep of TOR | Int. /a | WB "No Objection" | Int. /a | EOI/ Advert. Date | Int. /a | Subm. of EOI | Int. /a | Eval. Of EOI/SL | Int. /a | WB "No Objection" | Int. /a | Prep. Of RFP | Int. /a | WB "No Objection" | Int. /a | Issue of RFP/Inv. | Int. /a | Sub. Of Proposals | Int. /a | Tech. Eval. | Int. /a | WB "No Objection" | Int. /a | Open. Of Fin. Proposals | Int. /a | Invitation for Neg. | Int. /a | Negot. /Draft Contract | Int. /a | WB "No Objection" | Int. /a | Contract Signature | Int. /a | Start | Exec. /b | Compl. | Pysical Progress % | Payment to vendor %
Procurement Steps (1-19)
[5 empty] | USD | EUR |  |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11 |  | 12 |  | 13 |  | 14 |  | 15 |  | 16 |  | 17 |  | 18 |  | 19
1 |  | COMPONENT 1. STRENGTHENING ORGANIZATION & FINANCING OF EDUCATION SYSTEM
2
3 |  | CONSULTANTS
4 | P | C1.1/CS-IC/09-01 | 1.1 | Consultant - legal framework development | 92600 |  | IC | PRIOR | 2009-03-12 | 14 | 2009-03-26 | 7 | 2009-04-02 | 14 | 2009-04-16 | 7 | 2009-04-23 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-04-30 | 14 | 2009-05-14 | 14 | 2009-05-28 | 7 | 2009-06-04 | 7 | 2009-06-11 | 202 | 2009-12-30
5 | R/A | Dennis Farrington |  |  |  | 72000 |  |  | 2008-12-20 |  | 2009-01-16 |  | 2009-04-01 |  | 2009-04-25 |  | 2009-04-25 |  | 2009-04-27 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-05-10 |  | 2009-05-13 |  | 2009-05-20 |  | 2009-06-08 | 0 | 2009-06-08 | 206 | 2009-12-31 | 100 | 100 | Completed
6 | R/A | Dennis Farrington | 1.1 | Amendment #1 extending completion date |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-10-25 |  | 2009-10-25 |  | 2009-10-31 | 1 | 2009-10-31 | 1 | 2009-10-31 | 210 | 2010-05-31 | 100 | 100 | Completed
7 | P | C1.1/CS-IC/11-02 | 1.1 | New legislation implementation | 40540 | 30000 | IC | PRIOR | 2011-11-01 | 14 | 2011-11-15 | 7 | 2011-11-22 | 14 | 2011-12-06 | 7 | 2011-12-13 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-12-20 | 10 | 2011-12-30 | 14 | 2012-01-13 | 7 | 2012-01-20 | 7 | 2012-01-27 | 150 | 2012-09-30 | 81 | 81
8 | R/A | Dennis Farrington |  |  |  | 27040 |  |  | 2011-10-27 |  | 2011-11-09 |  | 2011-11-25 |  | 2011-12-07 |  | 2012-01-06 |  | 2012-01-06 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-01-10 |  | 2012-01-12 |  | 2012-01-26 |  | 2012-01-26 |  | 2012-01-26 |  |  |  |  | Completed
9 | R/A | Dennis Farrington |  | Amendment #1 modification of original contract |  |  |  |  | 2012-05-23 |  | 2012-05-24 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-05-23 |  | 2012-05-23 |  | 2012-05-24 |  | 2012-05-25 |  | 2012-05-25 |  |  |  |  | Under Implementation
10 | P | No Number | 1.2 | Consultant - financing formula development | 107500 | 79550 | IC | PRIOR | 2008-03-03 | 14 | 2009-03-18 | 7 | 2008-04-25 | 14 | 2008-04-09 | 7 | 2008-04-16 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2008-04-23 | 14 | 2008-05-08 | 14 | 2008-05-23 | 7 | 2008-05-30 | 7 | 2008-06-06 | 120 | 2008-10-04
11 | R/A | Rosalind Levacic | 1.2 |  | 45220 |  |  |  | 2008-06-20 |  | 2008-07-01 | [5 empty] | 2008-07-03 |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2008-07-18 |  | 2008-07-20 |  | 2008-07-22 |  | 2008-07-25 |  | 2008-07-25 | 442 | 2009-10-10 | 100 | 100 | Completed
12 | R/A | Rosalind Levacic | 1.2 | Amendment #1 modification of original contract | 4500 |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | [7 empty] | 2008-10-21 |  | 2008-10-21 | 9 | 2008-10-30 | 100 | 100 | Completed
13 | R/A | Rosalind Levacic | 1.2 | Amendment #2 modification of contract | 14379 |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-03-12 |  | 2009-03-12 |  | 2009-03-13 |  | 2009-03-13 |  | 2009-03-13 | 63 | 2009-05-10 | 100 | 100 | Completed
14 | P | C1.2/CS-IC/09-01 | 1.2 | Consultant - financing formula development | 0 |  | SSS | PRIOR | 2008-03-03 | 14 | 2008-03-17 | 7 | 2008-03-24 | 14 | 2008-04-07 | 7 | 2008-04-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2008-04-21 | 14 | 2008-05-05 | 14 | 2008-05-19 | 7 | 2008-05-26 | 7 | 2008-06-02 |  | 2012-12-31
15 | R/A | Rosalind Levacic | 1.2 |  |  | 35540 |  |  | 2009-10-21 |  | 2009-10-22 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-10-25 |  | 2010-10-25 |  | 2010-10-29 |  | 2009-11-12 |  | 2009-11-12 | 279 | 2010-08-18 | 100 | 100 | Completed
16 | R/A | Rosalind Levacic | 1.2 | Amendment #1 modification of original contract |  | 50980 |  | PRIOR | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-08-09 |  | 2010-08-10 |  | 2010-08-18 |  | 2010-08-18 |  | 2010-08-18 |  | 2012-03-28 | 82 | 82 | Completed
17 | R/A | Rosalind Levacic | 1.2 | Amendment #2 modification of original contract |  | 5440 |  |  | 2012-03-19 |  | 2012-03-28 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-03-15 |  | 2012-03-16 |  | 2012-03-28 |  | 2012-03-28 |  | 2012-03-28 |  |  |  |  | Under Implementation
18 | P | C1.2/CS-CQS/09-02 | 1.2 | Firm - Survey evaluation | 0 |  | CQS | PRIOR | 2009-05-15 | 14 | 2009-05-29 | 7 | 2009-06-05 | 14 | 2009-06-19 | 14 | 2009-07-03 |  | NA |  | NA |  | NA | 7 | 2009-07-10 | 14 | 2009-07-24 |  | NA |  | NA |  | NA | 7 | 2009-07-31 | 21 | 2009-08-21 | 14 | 2009-09-04 | 14 | 2009-09-18 | 7 | 2009-09-25 | 90 | 2009-12-24 |  |  | Not planned
19 | R/A | Prism Research |  |  |  | 24674 |  |  | 2009-03-10 |  | 2009-03-20 |  | 2009-03-27 |  | 2009-04-06 |  | 2009-04-30 |  | 2009-05-12 | [11 empty] | 2009-08-19 |  |  |  | 2009-08-20 |  | 2009-08-24 |  | 2009-08-31 |  | 2009-09-02 |  | 2009-09-02 | 179 | 2010-02-28 | 100 | 100 | Completed
20 | R/A | Prism Research | 1.2 | Amendment #1 extending completion date |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-02-11 |  | 2010-02-12 |  | 2010-02-15 |  | 2010-02-12 |  | 2010-02-12 | 47 | 2010-03-31 | 100 | 100 | Completed
21 | R/A | Prism Research | 1.2 | Amendment #2 extending completion date |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-02-09 |  | 2010-02-13 |  | 2010-02-15 |  | 2010-03-31 |  | 2010-03-31 | 30 | 2010-04-30 | 100 | 100 | Completed
22 | P | C1.2/CS-IC/09-03 | 1.2 | Consultant - system data entry | 6800 |  | IC | PRIOR | 2009-12-03 | 14 | 2009-12-17 | 7 | 2009-12-24 | 14 | 2010-01-07 | 7 | 2010-01-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2010-01-21 | 14 | 2010-02-04 | 14 | 2010-02-18 | 7 | 2010-02-25 | 7 | 2010-03-04 | 90 | 2010-06-02
23 | R/A | Besnik Limaj |  |  |  | 6400 | [6 empty] | 2009-01-19 |  | 2009-02-06 |  | 2009-02-12 |  | 2009-02-12 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-02-25 |  | 2009-02-25 |  | 2009-02-27 |  | 2009-03-01 |  | 2009-03-01 | 152 | 2009-07-31 | 100 | 100 | Completed
24 | P | C1.2/CS-IC/09-05 | 1.2 | Consultant - finance help desk-1 | 0 |  | IC | PRIOR | 2009-07-14 | 14 | 2009-07-29 | 7 | 2009-08-05 | 14 | 2009-08-20 | 7 | 2009-08-27 |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-09-02 | 14 | 2009-09-04 | 14 | 2009-09-06 | 7 | 2009-09-08 | 7 | 2009-09-10 | 365 | 2009-09-09 |  |  | Not planned
25 | R/A | Pakize Isufaj |  |  |  | 10800 |  |  | 2009-06-15 |  | 2009-06-10 |  | 2009-08-05 |  | 2009-09-03 |  | 2009-09-10 |  | 2009-09-10 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-09-10 |  | 2009-09-15 |  | 2009-09-17 |  | 2009-09-22 |  | 2009-09-22 | 365 | 2010-09-21 | 50 | 50 | Terminated on 22-March-10
26 | P | C1.2/CS-IC/09-06 | 1.2 | Consultant - finance help desk-2 | 0 |  | IC | PRIOR | 2009-07-14 | 14 | 2009-07-28 | 7 | 2009-08-04 | 14 | 2009-08-18 | 7 | 2009-08-25 | 7 | 2009-09-01 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-09-08 | 14 | 2009-09-22 | 14 | 2009-10-06 | 7 | 2009-10-13 | 7 | 2009-10-20 | 365 | 2010-10-20 |  |  | Not planned
27 | R/A | Hysni Maxharraj |  |  |  | 10800 |  |  | 2009-06-15 |  | 2009-07-10 |  | 2009-08-05 |  | 2009-09-03 |  | 2009-09-10 |  | 2009-09-11 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-09-10 |  | 2009-09-15 |  | 2009-09-17 |  | 2009-09-22 |  | 2009-09-22 |  | 2010-02-28 | 44 | 44 | Terminated on:28-Feb-10
28 | P | C1.2/CS-IC/09-07 | 1.2 | Consultant - training materials analyst | 0 |  | IC | PRIOR | 2009-09-20 | 14 | 2009-10-04 | 7 | 2009-10-11 | 14 | 2009-10-25 | 7 | 2009-11-01 | 7 | 2009-11-08 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-11-15 | 14 | 2009-11-29 | 14 | 2009-12-13 | 7 | 2009-12-20 | 7 | 2009-12-27 | 365 | 2010-12-27
29 | R/A | Edi Bunjaku |  |  |  | 1300 |  |  | 2009-09-20 |  | 2009-10-01 |  |  |  | NA |  | 2009-10-29 |  | 2009-11-01 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-11-10 |  | 2009-11-13 |  | 2009-11-17 |  | 2009-11-20 |  | 2009-11-20 | 31 | 2009-12-21 | 100 | 100 | Completed
30 | P | C1.2/CS-IC/10-08 | 1.2 | Consultant - Head of help desk | 0 |  | IC | PRIOR | 2010-02-18 | 14 | 2010-03-04 | 7 | 2010-03-11 | 14 | 2010-03-25 | 7 | 2010-04-01 | 7 | 2010-04-08 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2010-04-15 | 14 | 2010-04-29 | 14 | 2010-05-13 | 7 | 2010-05-20 | 7 | 2010-05-27 |  | 2012-12-31
31 | R/A | Pakize Isufaj |  |  |  | 13200 |  |  | 2010-02-18 | 1 | 2010-02-19 |  | 2010-02-20 |  | 2010-03-02 |  | 2010-03-05 | 3 | 2010-03-15 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-03-15 |  | 2010-03-15 |  | 2010-03-18 |  | 2010-03-22 |  | 2010-03-22 | 132 | 2010-08-01 | 100 | 100 | Completed
32 | R/A | Pakize Isufaj | 1.2 | Amendment #1 modification of original contract |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-07-30 |  | 2010-07-30 |  | 2010-07-31 |  | 2010-08-01 |  | 2010-08-01 | 233 | 2011-03-22 | 100 | 100 | Completed
33 | R/A | Pakize Isufaj | 1.2 | Amendment #2 modification of original contract |  | 13200 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-15 |  | 2011-03-21 |  | 2011-03-25 |  | 2011-03-22 |  | 2011-03-22 |  | 2012-03-22 | 100 | 100 | Completed
34 | R/A | Pakize Isufaj | 1.2 | Amendment #3 modification of original contract |  | 10350 |  |  | 2012-03-13 |  | 2012-03-15 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-03-12 |  | 2012-03-13 |  | 2012-03-15 |  | 2012-03-22 |  | 2012-03-22 |  |  |  |  | Under Implementation
35 | P | C1.2/CS-IC/10-09 | 1.2 | Consultant - education finance 2 | 0 |  | IC | PRIOR | 2009-02-01 | 14 | 2009-02-15 | 7 | 2009-02-22 | 14 | 2009-03-08 | 7 | 2009-03-15 | 7 | 2009-03-22 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-03-29 | 14 | 2009-04-12 | 14 | 2009-04-26 | 7 | 2009-05-03 | 7 | 2009-05-10 |  | 2012-12-31
36 | R/A | Vjolca Sellimi | 1.2 |  |  | 10800 |  |  | 2009-02-08 |  | 2010-02-19 |  | 2010-02-17 |  | 2010-03-02 |  | 2010-03-05 |  | 2010-03-15 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-03-15 |  | 2010-03-15 |  | 2010-03-18 | 4 | 2010-03-22 | 0 | 2010-03-22 | 142 | 2010-08-11 | 100 | 100 | Completed
37 | R/A | Vjolca Sellimi | 1.2 | Amendment #1 modification of original contract |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-07-22 |  | 2010-07-22 |  | 2010-07-31 |  | 2010-08-11 |  | 2010-08-11 | 226 | 2011-03-25 | 100 | 100 | Completed
38 | R/A | Vjolca Sellimi | 1.2 | Amendment #2 modification of original contract |  | 10800 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-17 |  | 2011-03-21 |  | 2011-03-25 |  | 2011-03-25 |  | 2011-03-25 |  | 2012-03-22 | 100 | 100 | Completed
39 | R/A | Vjolca Sellimi | 1.2 | Amendment #3 modification of original contract |  | 8469 |  |  | 2012-03-13 |  | 2012-03-15 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-03-12 |  | 3//13 |  | 2012-03-15 |  | 2012-03-22 |  | 2012-03-22 |  |  |  |  | Under Implementation
40 | R/A | Vjolca Sellimi | 1.2 | Amendment # 4 modification of original contract |  |  |  |  | 2012-08-13 |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-08-05 |  | 2012-08-13
41 | P | C1.2/CS-IC/11-10 | 1.2 | Trainer for school financing level |  | 6000 | IC | PRIOR | 2011-05-23 | 14 | 2011-06-06 | 7 | 2011-06-13 | 14 | 2011-06-27 | 14 | 2011-07-11 | 14 | 2011-07-25 | 14 | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-08-01 | 14 | 2011-08-15 | 14 | 2011-08-29 | 7 | 2011-09-05 | 7 | 2011-10-12 | 171 | 2012-03-31
42 | R/A | Mehmet Simnica |  |  |  | 5000 |  |  | 2011-07-14 |  | 2011-07-15 |  | 2011-08-01 |  | 2011-08-15 |  | 2011-09-09 |  | 2011-09-13 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-09-20 |  | 2011-09-30 |  | 2011-10-11 |  | 2011-10-12 |  | 2011-10-12 |  | 2011-12-08 | 100 | 76 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated in his contract. Therefore, payment has been done per working days needed to complete the task.
43 | P | C1.2/CS-IC/11-11 | 1.2 | Trainer for school financing level |  | 6000 | IC | PRIOR | 2011-05-23 | 14 | 2011-06-06 | 7 | 2011-06-13 | 14 | 2011-06-27 | 14 | 2011-07-11 | 14 | 2011-07-25 | 14 | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-08-01 | 14 | 2011-08-15 | 14 | 2011-08-29 | 7 | 2011-09-05 | 7 | 2011-10-12 | 171 | 2012-03-31
44 | R/A | Mevlide Shamolli |  |  |  | 5000 |  |  | 2011-07-14 |  | 2011-07-15 |  | 2011-08-01 |  | 2011-08-15 |  | 2011-09-09 |  | 2011-09-13 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-09-20 |  | 2011-09-30 |  | 2011-10-11 |  | 2011-10-12 |  | 2011-10-12 |  | 2011-12-12 | 100 | 76 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated in his contract. Therefore, payment has been done per working days needed to complete the task.
45 | P | C1.2/CS-IC/11-12 | 1.2 | Trainer for school financing level |  | 6000 | IC | PRIOR | 2011-05-23 | 14 | 2011-06-06 | 7 | 2011-06-13 | 14 | 2011-06-27 | 14 | 2011-07-11 | 14 | 2011-07-25 | 14 | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-08-01 | 14 | 2011-08-15 | 14 | 2011-08-29 | 7 | 2011-09-05 | 7 | 2011-10-12 | 171 | 2012-03-31
46 | R/A | Jeton Kryeziu |  |  |  | 5000 |  |  | 2011-07-14 |  | 2011-07-15 |  | 2011-08-01 |  | 2011-08-15 |  | 2011-09-09 |  | 2011-09-13 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-09-20 |  | 2011-09-30 |  | 2011-10-11 |  | 2011-10-12 |  | 2011-10-12 |  | 2011-12-12 | 100 | 76 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated in his contract. Therefore, payment has been done per working days needed to complete the task.
47 | P | C1.2/CS-IC/11-13 | 1.2 | Trainer for school financing level |  | 6000 | IC | PRIOR | 2011-05-23 | 14 | 2011-06-06 | 7 | 2011-06-13 | 14 | 2011-06-27 | 14 | 2011-07-11 | 14 | 2011-07-25 | 14 | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-08-01 | 14 | 2011-08-15 | 14 | 2011-08-29 | 7 | 2011-09-05 | 7 | 2011-10-12 | 171 | 2012-03-31
48 | R/A | Jeton Gashi |  |  |  | 5000 |  |  | 2011-07-14 |  | 2011-07-15 |  | 2011-08-01 |  | 2011-08-15 |  | 2011-09-09 |  | 2011-09-13 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-09-20 |  | 2011-09-30 |  | 2011-10-11 |  | 2011-10-12 |  | 2011-10-12 |  | 2011-12-09 | 100 | 72 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated in his contract. Therefore, payment has been done per working days needed to complete the task.
49 | P | C1.2/CS-IC/11-14 | 1.2 | Trainer for school financing level |  | 6000 | IC | PRIOR | 2011-05-23 | 14 | 2011-06-06 | 7 | 2011-06-13 | 14 | 2011-06-27 | 14 | 2011-07-11 | 14 | 2011-07-25 | 14 | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-08-01 | 14 | 2011-08-15 | 14 | 2011-08-29 | 7 | 2011-09-05 | 7 | 2011-10-12 | 171 | 2012-03-31
50 | R/A | Aferdita Strellci |  |  |  | 5000 |  |  | 2011-07-14 |  | 2011-07-15 |  | 2011-08-01 |  | 2011-08-15 |  | 2011-09-09 |  | 2011-09-13 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-09-20 |  | 2011-09-30 |  | 2011-10-11 |  | 2011-10-12 |  | 2011-10-12 |  | 2011-12-13 | 100 | 72 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated in his contract. Therefore, payment has been done per working days needed to complete the task.
51 | P | C1.2/CS-IC/11-15 | 1.2 | Trainer for school procurement level |  | 6000 | IC | PRIOR | 2011-09-20 | 14 | 2011-10-04 | 7 | 2011-10-11 | 14 | 2011-10-25 | 14 | 2011-11-08 | 14 | 2011-11-22 | 14 | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-11-29 | 14 | 2011-12-13 | 14 | 2011-12-27 | 7 | 2012-01-03 | 7 | 2012-01-10 | 123 | 2012-05-12
52 | R/A | Fadil Veseli |  |  |  | 4000 |  |  | 2011-09-20 |  | 2011-10-18 |  | 2011-10-19 |  | 2011-11-02 |  | 2011-11-18 |  | 2011-12-01 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-12-06 |  | 2011-12-07 |  | 2011-12-12 |  | 2011-12-12 |  | 2011-12-12 |  | 2012-01-02 | 20 | 20 | Resign on Janaury 3,2012
53 | P | C1.2/CS-IC/11-16 | 1.2 | Trainer for school procurement level |  | 6000 | IC | PRIOR | 2011-09-20 | 14 | 2011-10-04 | 7 | 2011-10-11 | 14 | 2011-10-25 | 14 | 2011-11-08 | 14 | 2011-11-22 | 14 | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-11-29 | 14 | 2011-12-13 | 14 | 2011-12-27 | 7 | 2012-01-03 | 7 | 2012-01-10 | 123 | 2012-05-12
54 | R/A | Mirevete Gerguri |  |  |  | 4000 |  |  | 2011-09-20 |  | 2011-10-18 |  | 2011-10-19 |  | 2011-11-02 |  | 2011-11-18 |  | 2011-12-01 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-12-06 |  | 2011-12-07 |  | 2011-12-12 |  | 2011-12-12 |  | 2011-12-12 |  | 2012-03-06 | 100 | 85 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated
55 | P | C1.2/CS-IC/11-17 | 1.2 | Trainer for school procurement level |  | 6000 | IC | PRIOR | 2011-09-20 | 14 | 2011-10-04 | 7 | 2011-10-11 | 14 | 2011-10-25 | 14 | 2011-11-08 | 14 | 2011-11-22 | 14 | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-11-29 | 14 | 2011-12-13 | 14 | 2011-12-27 | 7 | 2012-01-03 | 7 | 2012-01-10 | 123 | 2012-05-12
56 | R/A | Fatmire M Morina |  |  |  | 4000 |  |  | 2011-09-20 |  | 2011-10-18 |  | 2011-10-19 |  | 2011-11-02 |  | 2011-11-18 |  | 2011-12-01 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-12-06 |  | 2011-12-07 |  | 2011-12-12 |  | 2011-12-12 |  | 2011-12-12 |  | 2012-02-29 | 100 | 93 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated
57 | P | C1.2/CS-IC/11-18 | 1.2 | Trainer for school procurement level |  | 6000 | IC | PRIOR | 2011-09-20 | 14 | 2011-10-04 | 7 | 2011-10-11 | 14 | 2011-10-25 | 14 | 2011-11-08 | 14 | 2011-11-22 | 14 | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-11-29 | 14 | 2011-12-13 | 14 | 2011-12-27 | 7 | 2012-01-03 | 7 | 2012-01-10 | 123 | 2012-05-12
58 | R/A | Vllaznim Reshani |  |  |  | 4000 |  |  | 2011-09-20 |  | 2011-10-18 |  | 2011-10-19 |  | 2011-11-02 |  | 2011-11-18 |  | 2011-12-01 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-12-06 |  | 2011-12-07 |  | 2011-12-12 |  | 2011-12-12 |  | 2011-12-12 |  | 2012-02-28 | 100 | 96 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated
59 | P | C1.2/CS-IC/11-19 | 1.2 | Trainer for school procurement level |  | 6000 | IC | PRIOR | 2011-09-20 | 14 | 2011-10-04 | 7 | 2011-10-11 | 14 | 2011-10-25 | 14 | 2011-11-08 | 14 | 2011-11-22 | 14 | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-11-29 | 14 | 2011-12-13 | 14 | 2011-12-27 | 7 | 2012-01-03 | 7 | 2012-01-10 | 123 | 2012-05-12
60 | R/A | Defrim Kuqi |  |  |  | 4000 |  |  | 2011-09-20 |  | 2011-10-18 |  | 2011-10-19 |  | 2011-11-02 |  | 2011-11-18 |  | 2011-12-01 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-12-06 |  | 2011-12-07 |  | 2011-12-12 |  | 2011-12-12 |  | 2011-12-12 |  | 2012-02-29 | 100 | 76 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated
61 | P | C1.2/CS-IC-12-01 | 1.2 | Education finance officer for operating at Help Desk |  | 6300 | IC | PRIOR | 2012-06-08 | 14 | 2012-06-22 | 7 | 2012-06-29 | 14 | 2012-07-13 | 14 | 2012-07-27 | 14 | 2012-08-10 | 14 | 2012-08-24 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2012-08-31 | 14 | 2012-09-14 | 14 | 2012-09-28 | 7 | 2012-10-05 | 7 | 2012-10-12 |  | 2012-11-17
62 | R/A | Bersant R. Grabanice |  |  |  | 1200 |  |  | 2012-06-06 |  | 2012-06-11 |  | 2012-06-11 |  | 2012-06-11 |  | 2012-07-02 |  | 2012-07-03 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-07-16 |  | 2012-07-16 |  | 2012-07-17 |  | 2012-07-17 |  | 2012-07-17 |  |  |  |  | Under Implementation
63 | P | No Number | 1.3 | Consultant - Manager of the SDGs | 46500 |  | IC | PRIOR | 2009-04-12 | 14 | 2009-04-26 | 7 | 2009-05-04 | 14 | 2009-05-18 | 7 | 2009-05-28 |  | 2009-06-10 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-06-12 | 14 | 2009-06-15 | 14 | 2009-06-20 | 7 | 2009-06-23 | 7 | 2009-06-25 |  | 2010-06-24
64 | R/A | Xhafer Ahmeti |  |  |  | 15600 |  |  | 2009-05-12 |  | 2009-05-27 | [9 empty] | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-05-25 |  | 2009-05-25 |  | 2009-05-27 |  | 2009-05-28 |  | 2009-05-01 | 244 | 2009-12-31 | 67 | 67 | Terminated on: 31-Dec-2009
65 | P | C1.3/CS-IC/09-02 | 1.3 | Consultant - Manager of the SDGs | 0 |  | IC | PRIOR | 2010-01-04 | 14 | 2010-01-18 | 7 | 2010-01-25 | 14 | 2010-02-08 | 7 | 2010-02-15 | 7 | 2010-02-22 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2010-03-01 | 14 | 2010-03-15 | 14 | 2010-03-29 | 7 | 2010-04-05 | 7 | 2011-05-11 |  | 2012-12-31
66 | R/A | Besim Kokollari |  |  |  | 14400 |  |  | 2010-02-10 |  | 2010-02-12 | 4 | 2010-02-26 | 14 | 2010-03-15 | 7 | 2010-03-22 | 28 | 2010-04-20 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-04-21 | 14 | 2010-05-05 | 1 | 2010-05-06 | 4 | 11--May-10 |  | 2010-05-11 | 365 | 2011-05-11 | 100 | 100 | Completed
67 | R/A | Besim Kokollari | 1.3 | Amendment #1 modification of original contract | 0 | 12817.5 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-04-21 |  | 2011-04-27 |  | 2011-05-05 |  | 2011-05-05 | 6 | 2011-05-11 |  | 2012-03-22 | 100 | 100 | Completed
68 | R/A | Besim Kokollari | 1.3 | Amendment #2 modification of original contract |  | 10800 |  |  | 2012-03-14 |  | 2012-03-16 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-03-13 |  | 2012-03-14 |  | 2012-03-16 |  | 2012-03-22 |  | 2012-03-22 |  |  |  |  | Under Implementation
69 | P | C1.3/CS-IC/09-02 | 1.3 | Consultant - SDG and MDG manuals | 0 |  | SSS | PRIOR | 2009-05-20 | 14 | 2009-06-03 | 7 | 2009-06-10 | 14 | 2009-06-24 | 7 | 2009-07-01 | 7 | 2009-07-08 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-07-15 | 14 | 2009-07-29 | 14 | 2009-08-12 | 7 | 2009-08-19 | 7 | 2009-08-26 | 365 | 2010-08-26
70 | R/A | Remzi Salihu |  |  |  | 7800 |  |  | 2009-05-20 |  | 2009-06-12 |  | NA |  | NA |  | NA |  | 2009-07-07 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-07-12 |  | 2009-07-12 |  | 2009-07-14 |  | 2009-07-15 |  | 2009-07-15 | 138 | 2009-11-30 | 92 | 92 | Completed
71 | P | C1.3/CS-QCBS/09-03 | 1.3 | Firm/NGO - school development grants implem. | 463600 |  | QCBS | PRIOR | 2009-05-20 | 14 | 2009-06-03 | 7 | 2009-06-10 | 45 | 2009-07-25 | 14 | 2009-08-08 | 14 | 2009-08-22 | 14 | 2009-09-05 | 14 | 2009-09-19 | 7 | 2009-09-26 | 45 | 2009-11-10 | 14 | 2009-11-24 | 14 | 2009-12-08 | 7 | 2009-12-15 | 7 | 2009-12-22 | 14 | 2010-01-05 | 14 | 2010-01-19 | 7 | 2010-01-26 | 7 | 2010-06-21 | 731 | 2012-10-21
72 | R/A | KEC, KOSOVO |  |  |  | 266935 |  |  | 2009-05-20 |  | 2009-06-11 |  | 2009-06-11 |  | 2009-07-13 |  | 2009-08-12 |  | 2009-08-19 |  | 2009-08-28 |  | 2009-09-01 |  | 2009-09-03 |  | 2009-10-05 |  | 2009-08-12 |  | 2009-08-19 |  | 2010-04-14 |  | 2010-05-26 |  | 2010-06-10 |  | 2010-06-11 |  | 2010-06-14 | 7 | 2010-06-21 |  | 2012-01-21 | 75 | 75 | Completed
73 | R/A | KEC, KOSOVO | 1,3 | Amendment #1 modification of original contract |  | 48400 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-01-16 |  | 2012-01-17 |  | 2012-01-30 |  | 2012-01-21 |  | 2012-01-21 |  | 2012-06-30 |  |  | Completed
74 | R/A | KEC, KOSOVO | 1.3 | Amendment # 2 modification of original contract |  | 11840 |  |  | 2012-06-28 |  | 2012-06-29 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-06-25 |  | 2012-06-28 |  | 2012-06-29 |  | 2012-06-29 |  | 2012-07-01 |  |  |  |  | Under Implementation
75 |  | COMPONENT 2. BUILDING INSTITUTIONS & MANAGEMENT CAPACITY IN PRIMARY & SECONDARY EDUCATION
76
77 |  | CONSULTANTS
78 | P | C2.1/CS-IC/09-01 | 2.1 | Consultant - teacher's devel. and licencing | 19900 |  | IC | PRIOR | 2008-05-25 | 14 | 2008-06-08 | 7 | 2008-06-15 | 14 | 2008-06-29 | 7 | 2008-07-06 | 7 | 2008-07-13 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2008-07-20 | 14 | 2008-08-03 | 14 | 2008-08-17 | 7 | 2008-08-24 | 7 | 2010-05-26 |  | 2013-06-30
79 | R/A | Blerim Saqipi |  |  |  | 11960 |  |  | 2008-05-25 |  | 2008-06-03 |  | 2008-07-04 |  | 2008-07-08 |  | 2008-07-11 |  | 2008-07-18 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2008-07-20 |  | 2008-07-20 |  | 2008-07-22 |  | 2008-08-01 |  | 2008-08-01 | 341 | 2009-07-08 | 100 | 100 | Completed
80 | R/A | Blerim Saqipi | 2.1 | Amendment #1 modification of original contract |  | 14950 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-07-05 |  | 2009-07-05 |  | 2009-07-01 |  | 2009-07-08 |  | 2009-06-15 | 115 | 2010-05-26 | 100 | 100 | Completed
81 | R/A | Blerim Saqipi | 2.1 | Amendment #2 modification of original contract |  | 20800 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-05-23 |  | 2010-05-23 |  | 2010-05-25 |  | 2010-05-26 |  | 2010-05-26 |  | 2012-06-30 | 87 | 87 | Under implementation
82 | R/A | Blerim Saqipi | 2.1 | Amendment #3 modification of original contract |  | 13407 |  |  | 2010-11-22 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-11-21 |  | 2010-11-22 |  | 2010-12-08 |  | 2010-12-10 |  | 2010-12-15 | 168 | 2011-06-01 | 100 | 100 | Completed
83 | R/A | Blerim Saqipi | 2.1 | Amendment #4 modification of original contract |  | 2616 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-05-27 |  | 2011-05-27 |  | 2011-05-30 |  | 2011-06-01 |  | 2011-06-01 | 60 | 2011-07-31 | 100 | 100 | Completed
84 | R/A | Blerim Saqipi | 2.1 | Amendment # 5 modification of original contract |  | 7800 |  |  | 2012-06-21 |  | 2012-06-22 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-06-20 |  | 2012-06-20 |  | 2012-06-22 |  | 2012-06-25 |  | 2012-07-01
85 | P | C2.1/CS-IC/09-02 | 2.1 | Consultant - teachers' professional devel. | 62700 |  | IC | PRIOR | 2008-03-03 | 14 | 2008-03-17 | 7 | 2008-03-24 | 14 | 2008-04-07 | 7 | 2008-04-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2008-04-21 | 14 | 2008-05-05 | 14 | 2008-05-19 | 7 | 2008-05-26 | 7 | 2008-06-02 | 90 | 2008-08-31
86 | R/A | Pilar Romaguez |  |  | 52300 |  |  |  | 2008-05-20 |  | 2008-05-22 |  | 2008-05-23 |  | 2008-06-01 |  | 2008-06-03 |  | 2008-06-03 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2008-06-10 |  | 2008-06-10 |  | 2008-06-12 |  | 2008-06-12 |  | 2008-06-12 | 141 | 2008-10-31 | 100 | 100 | Completed
87 | P | C2.1/CS-IC/09-03 | 2.1 | Consultant - teachers' career/advance. syst. |  |  | IC | PRIOR | 2009-04-03 | 14 | 2009-04-18 | 7 | 2009-04-25 | 14 | 2009-05-09 | 7 | 2009-05-16 |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-05-23 | 14 | 2009-06-08 | 14 | 2009-06-23 | 7 | 2009-06-30 | 7 | 2009-07-06 | 30 | 2009-11-15
88 | R/A | Pasi Ikonen |  |  | 24975.84 | [9 empty] | 2009-05-25 |  | 2009-05-27 |  | 2009-05-27 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-06-10 |  | 2009-06-24 |  | 2009-06-26 | 4 | 2009-06-30 | 0 | 2009-06-30 | 138 | 2009-11-15 |  |  | Completed
89 | R/A | Pasi Ikonen | 2.1 | Amendment #1 extending completion date |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-11-29 |  | 2009-11-29 |  | 2009-11-30 |  | 2009-11-15 | 0 | 2009-11-15 | 77 | 2010-01-31 | 100 | 83 | Completed
90 | P | C2.1/CS-IC/09-04 | 2.1 | Consultant - teachers' performance evaluation | 60600 |  | IC | PRIOR | 2009-04-10 | 14 | 2009-04-25 | 7 | 2009-05-02 | 14 | 2009-05-17 | 7 | 2009-05-24 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-06-01 | 14 | 2009-06-10 | 14 | 2009-06-20 | 7 | 2009-07-21 | 7 | 2009-07-28 | 30 | 2009-11-30
91 | R/A | Jorge Manzi |  |  | 32733 | [13 empty] | 2009-06-10 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-07-09 |  | 2009-07-12 |  | 2009-07-19 | 2 | 2009-07-21 |  | 2009-07-20 | 133 | 2009-11-30 |  |  | Completed
92 | R/A | Jorge Manzi |  | Amendment #1 extending completion date | [30 empty] | 2009-11-23 |  | 2009-11-24 |  | 2009-11-25 | 1 | 2009-11-26 | 4 | 2009-11-30 | 182 | 2010-05-31 |  |  | Completed
93 | R/A | Jorge Manzi |  | Amendment #2 extending completion date | [30 empty] | 2010-05-25 |  | 2010-05-25 |  | 2010-05-26 | 0 | 2010-05-26 | 0 | 2010-05-26 | 50 | 2010-07-15 | 100 |  | Completed
94 | P | C2.1/CS-IC/10-05 | 2.1 | Consultant - teachers' performance evaluation | 112900 | 82100 | IC | PRIOR | 2010-10-15 | 14 | 2010-10-29 | 7 | 2010-11-05 | 14 | 2010-11-19 | 14 | 2010-12-03 | 7 | 2010-12-10 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 120 | 2011-04-09 | 20 | 2011-04-29 | 14 | 2011-05-13 | 14 | 2011-05-27 | 7 | 2011-06-15 | 290 | 2013-03-31
95 | R/A | Nicole Saginor | 2.1 |  |  | 48400 |  |  | 2010-08-18 |  | 2010-08-25 |  | 2010-08-26 |  | 2010-09-10 |  | 2010-10-20 |  | 2010-10-25 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-04-20 |  | 2011-05-13 |  | 2011-05-23 |  | 2011-05-24 |  | 2011-06-15 |  | 2012-03-30 | 85 | 85 | Completed
96 | P | C2.1/CS-CQS/10-06 | 2.1 | Firm - teachers' licensing system database |  | 0 | CQS | PRIOR | 2010-04-12 | 14 | 2010-04-26 | 7 | 2010-05-03 | 14 | 2010-05-17 | 14 | 2010-05-31 |  | NA |  | NA |  | NA | 7 | 2010-06-07 | 14 | 2010-06-21 |  | NA |  | NA |  | NA | 7 | 2010-06-28 | 21 | 2010-07-19 | 14 | 2010-08-02 | 14 | 2010-08-16 | 7 | 2010-08-23 | 90 | 2010-11-21
97 | R/A
98 | R/A | Nicole Saginor | 2.1 |  |  | 43950 |  |  | 2012-03-13 |  | 2012-03-29 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-03-12 |  | 2012-03-12 |  | 2012-03-29 |  | 2012-03-30 |  | 2012-03-30 |  |  |  |  | Under implementation
99 | P | C2.1/CS-IC/11-07 - Prishtina region | 2.1 | Consultant for database population and logistical support on performance evaluation | 0 | 6400 | IC | PRIOR | 2011-05-30 | 14 | 2011-06-13 | 7 | 2011-06-20 | 14 | 2011-07-04 | 14 | 2011-07-18 | 7 | 2011-07-25 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-08-01 | 21 | 2011-08-22 | 14 | 2011-09-05 | 14 | 2011-09-19 | 7 | 2011-09-15 |  | 2012-07-31
100 | R/A | Edmond Krasniqi |  |  |  | 6000 |  |  | 2011-06-10 |  | 2011-06-15 |  | 2011-06-20 |  | 2011-06-22 |  | 2011-08-11 |  | 2011-08-25 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-08-26 |  | 2011-09-07 |  | 2011-09-11 |  | 2011-09-15 |  | 2011-09-15 |  | 2012-04-30 | 64 | 64 | Completed
101 | R/A | Edmond Krasniqi |  | Amendment #1 extending completion date |  |  |  |  | 2012-04-20 |  | 2012-04-26 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-04-19 |  | 2012-04-20 |  | 2012-04-26 |  | 2012-04-27 |  | 2012-04-27 |  |  |  |  | Completed
102 | R/A | Edmond Krasniqi |  | Amendment # 2 modification of original contract |  | 1875 |  |  | 2012-07-25 |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-07-23 |  | 2012-07-24 | [10 empty] | Under implementation
103 | P | C2.1/CS-IC/11-08 - Prizren region | 2.1 | Consultant for database population and logistical support on performance evaluation |  | 6400 | IC | PRIOR | 2011-05-30 | 14 | 2011-06-13 | 7 | 2011-06-20 | 14 | 2011-07-04 | 14 | 2011-07-18 | 7 | 2011-07-25 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-08-01 | 21 | 2011-08-22 | 14 | 2011-09-05 | 14 | 2011-09-19 |  | 2011-09-16 |  | 2012-07-31
104 | R/A | Kreshnik Shatri |  |  |  | 6000 |  |  | 2011-06-10 |  | 2011-06-15 |  | 2011-06-20 |  | 2011-06-22 |  | 2011-08-11 |  | 2011-08-25 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-08-26 |  | 2011-09-08 |  | 2011-09-15 |  | 2011-09-16 |  | 2011-09-16 |  | 2012-04-30 | 58 | 58 | Completed
105 | R/A | Kreshnik Shatri |  | Amendment #1 extending completion date |  |  |  |  | 2012-04-20 |  | 2012-04-26 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-04-19 |  | 2012-04-20 |  | 2012-04-26 |  | 2012-04-27 |  | 2012-04-27 |  |  |  |  | Completed
106 | R/A | Kreshnik Shatri |  | Amendment # 2 modification of original contract |  | 1875 |  |  | 2012-07-25 |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-07-23 |  | 2012-07-24 | [10 empty] | Under implementation
107 | P | C2.1/CS-IC/11-09 - Peja region | 2.1 | Consultant for database population and logistical support on performance evaluation |  | 6400 | IC | PRIOR | 2011-05-30 | 14 | 2011-06-13 | 7 | 2011-06-20 | 14 | 2011-07-04 | 14 | 2011-07-18 | 7 | 2011-07-25 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-08-01 | 21 | 2011-08-22 | 14 | 2011-09-05 | 14 | 2011-09-19 | 7 | 2011-09-16 |  | 2012-07-31
108 | R/A | Mentor Vokshi |  |  |  | 6000 |  |  | 2011-06-10 |  | 2011-06-15 |  | 2011-06-20 |  | 2011-06-22 |  | 2011-08-11 |  | 2011-08-25 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-08-26 |  | 2011-09-08 |  | 2011-09-15 |  | 2011-09-16 |  | 2011-09-16 |  | 2012-04-30 | 52 | 52 | Completed
109 | R/A | Mentor Vokshi |  | Amendment #1 extending completion date |  |  |  |  | 2012-04-20 |  | 2012-04-26 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-04-19 |  | 2012-04-20 |  | 2012-04-26 |  | 2012-04-27 |  | 2012-04-27 |  |  |  |  | Completed
110 | R/A | Mentor Vokshi |  | Amendment # 2 modification of original contract |  | 1875 |  |  | 2012-07-25 |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-07-23 |  | 2012-07-25 | [10 empty] | Under implementation
111 | P | C2.1/CS-IC/11-10 - Gjakova region | 2.1 | Consultant for database population and logistical support on performance evaluation |  | 6400 | IC | PRIOR | 2011-05-30 | 14 | 2011-06-13 | 7 | 2011-06-20 | 14 | 2011-07-04 | 14 | 2011-07-18 | 7 | 2011-07-25 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-08-01 | 21 | 2011-08-22 | 14 | 2011-09-05 | 14 | 2011-09-19 | 7 | 2011-09-16 |  | 2012-07-31
112 | R/A | Armend Bajrami |  |  |  | 6000 |  |  | 2011-06-10 |  | 2011-06-15 |  | 2011-06-20 |  | 2011-06-22 |  | 2011-08-11 |  | 2011-08-25 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-08-26 |  | 2011-09-08 |  | 2011-09-15 |  | 2011-09-16 |  | 2011-09-16 |  | 2012-04-30 | 80 | 80 | Completed
113 | R/A | Armend Bajrami |  | Amendment #1 extending completion date |  |  |  |  | 2012-04-20 |  | 2012-04-26 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-04-19 |  | 2012-04-20 |  | 2012-04-26 |  | 2012-04-27 |  | 2012-04-27 |  |  |  |  | Completed
114 | R/A | Armend Bajrami |  | Amendment # 2 modification of original contract |  | 1500 |  |  | 2012-07-25 |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-07-23 |  | 2012-07-24 | [10 empty] | Under implementation
115 | P | C2.1/CS-IC/11-11 - Ferizaj region | 2.1 | Consultant for database population and logistical support on performance evaluation |  | 6400 | IC | PRIOR | 2011-05-30 | 14 | 2011-06-13 | 7 | 2011-06-20 | 14 | 2011-07-04 | 14 | 2011-07-18 | 7 | 2011-07-25 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-08-01 | 21 | 2011-08-22 | 14 | 2011-09-05 | 14 | 2011-09-19 | 7 | 2011-09-16 |  | 2012-07-31
116 | R/A | Donika Rexhepi |  |  |  | 6000 |  |  | 2011-06-10 |  | 2011-06-15 |  | 2011-06-20 |  | 2011-06-22 |  | 2011-08-11 |  | 2011-08-25 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-08-26 |  | 2011-09-07 |  | 2011-09-15 |  | 2011-09-16 |  | 2011-09-16 |  | 2012-04-30 | 80 | 80 | Completed
117 | R/A | Donika Rexhepi |  | Amendment #1 extending completion date |  |  |  |  | 2012-04-20 |  | 2012-04-26 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-04-19 |  | 2012-04-20 |  | 2012-04-26 |  | 2012-04-27 |  | 2012-04-27 |  |  |  |  | Completed
118 | R/A | Donika Rexhepi |  | Amendment # 2 modification of original contract |  | 1500 |  |  | 2012-07-25 |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-07-23 |  | 2012-07-24 | [10 empty] | Under implementation
119 | P | C2.1/CS-IC/11-12 - Mitrovica region | 2.1 | Consultant for database population and logistical support on performance evaluation |  | 6400 | IC | PRIOR | 2011-06-10 | 14 | 2011-06-24 | 7 | 2011-07-01 | 14 | 2011-07-15 | 14 | 2011-07-29 | 7 | 2011-08-05 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-08-12 | 21 | 2011-09-02 | 14 | 2011-09-16 | 14 | 2011-09-30 | 7 | 2011-09-16 |  | 2012-07-31
120 | R/A | Zahir Ibishi |  |  |  | 6000 |  |  | 2011-06-10 |  | 2011-06-15 |  | 2011-06-20 |  | 2011-06-22 |  | 2011-08-11 |  | 2011-08-25 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-08-26 |  | 2011-09-08 |  | 2011-09-15 |  | 2011-09-16 |  | 2011-09-16 |  | 2012-04-30 | 80 | 80 | Completed
121 | R/A | Zahir Ibishi |  | Amendment #1 extending completion date |  |  |  |  | 2012-04-20 |  | 2012-04-26 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-04-19 |  | 2012-04-20 |  | 2012-04-26 |  | 2012-04-27 |  | 2012-04-27 |  |  |  |  | Completed
122 | R/A | Zahir Ibishi |  | Amendment # 2 modification of original contract |  | 1500 |  |  | 2012-07-25 |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-07-23 |  | 2012-07-24 | [10 empty] | Under implementation
123 | P | C2.1/CS-IC/11-13 - Gjilan region | 2.1 | Consultant for database population and logistical support on performance evaluation |  | 6400 | IC | PRIOR | 2011-05-30 | 14 | 2011-06-13 | 7 | 2011-06-20 | 14 | 2011-07-04 | 14 | 2011-07-18 | 7 | 2011-07-25 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-08-01 | 21 | 2011-08-22 | 14 | 2011-09-05 | 14 | 2011-09-19 | 7 | 2011-09-16 |  | 2012-07-31
124 | R/A | Agim Ramadani |  |  |  | 6000 |  |  | 2011-06-10 |  | 2011-06-15 |  | 2011-06-20 |  | 2011-06-22 |  | 2011-08-11 |  | 2011-08-25 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-08-26 |  | 2011-09-07 |  | 2011-09-15 |  | 2011-09-16 |  | 2011-09-16 |  | 2012-04-30 | 77 | 77 | Completed
125 | R/A | Agim Ramadani |  | Amendment #1 extending completion date |  |  |  |  | 2012-04-20 |  | 2012-04-26 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-04-19 |  | 2012-04-20 |  | 2012-04-26 |  | 2012-04-27 |  | 2012-04-27 |  |  |  |  | Completed
126 | R/A | Agim Ramadani |  | Amendment # 2 modification of original contract |  | 1875 |  |  | 2012-07-25 |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-07-23 |  | 2012-07-23 | [10 empty] | Under implementation
127 | P | C2.1/CS-IC/11-14 | 2.1 | Consultant on Teacher Development Policies Study | 0 | 50000 | IC | PRIOR | 2011-05-30 | 5 | 2011-06-04 | 5 | 2011-06-09 | 7 | 2011-06-16 | 14 | 2011-06-30 | 3 | 2011-07-03 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 2 | 2011-07-05 | 5 | 2011-07-10 | 3 | 2011-07-13 | 5 | 2011-07-18 | 10 | 2011-09-30 | 212 | 2012-05-31
128 | P | David Lynn |  |  |  | 47830 |  |  | 2011-06-10 |  | 2011-06-17 |  | 2011-06-20 |  | 2011-08-10 |  | 2011-08-18 |  | 2011-08-22 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-08-22 |  | 2011-09-23 |  | 2011-09-26 |  | 2011-09-26 |  | 2011-09-30 |  | 2012-02-29 | 83 | 83 | Completed
129 | R/A | David Lynn | [6 empty] | 2012-03-16 |  | 2012-03-16 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-03-16 |  | 2012-03-16 |  | 2012-03-16 |  | 2012-03-19 |  | 2012-03-01 |  |  |  |  | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete his task than originally in his contract.
130 | p | C2.1/CS-IC/11-15 | 2.1 | Consultant for the Managing the database process |  | 8000 | IC | PRIOR | 2011-06-10 | 14 | 2011-06-24 | 7 | 2011-07-01 | 7 | 2011-07-08 | 14 | 2011-07-22 | 7 | 2011-07-29 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-08-05 | 21 | 2011-08-26 | 14 | 2011-09-09 | 14 | 2011-09-23 | 7 | 2011-09-16 |  | 2012-07-31
131 | R/A | Mirlind Bruqi |  |  |  | 8000 |  |  | 2011-06-10 |  | 2011-06-23 |  | 2011-07-01 |  | 2011-07-11 |  | 2011-08-10 |  | 2011-08-25 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-08-26 |  | 2011-09-10 |  | 2011-09-15 |  | 2011-09-16 |  | 2011-09-16 |  | 2012-04-30 | 88 | 88 | Completed
132 | R/A | Mirlind Bruqi |  | Amendment #1 extending completion date |  |  |  |  | 2012-04-20 |  | 2012-04-26 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-04-19 |  | 2012-04-20 |  | 2012-04-26 |  | 2012-04-27 |  | 2012-04-27 |  |  |  |  | Completed
133 | P | C2.2/CS-SSS/10-02 | 2.2 | Consultant - curriculum unit and CACTI capacity | 0 |  | SSS | PRIOR | 2010-06-22 | 1 | 2010-06-23 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-06-24 | 1 | 2010-06-24 | 8 | 2010-07-02 | 3 | 2010-07-05 | 5 | 2010-07-10 | 255 | 2011-03-31 |  |  | Completed
134 | R/A | Camerron Harisson |  |  | 45243 | 33480 |  |  | 2010-06-22 | 1 | 2010-06-23 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-06-24 | 1 | 2010-06-24 | 8 | 2010-07-02 | 3 | 2010-07-02 | 5 | 2010-07-02 | 255 | 2011-03-31 | 100 | 100 | Completed
135 | P | C2.2/CS-IC/09-01 | 2.2 | Consultant - curriculum unit and CACTI capacity |  |  | IC | PRIOR | 2009-02-08 | 14 | 2009-02-22 | 7 | 2009-03-01 | 14 | 2009-03-15 | 7 | 2009-03-22 |  | NA |  | NA |  | NA | 7 | 2009-03-29 | 15 | 2009-04-13 |  | NA |  | NA | 2 | 2009-04-15 | 7 | 2009-04-20 | 14 | 2009-05-04 | 14 | 2009-05-18 | 7 | 2009-05-25 | 7 | 2009-06-01 | 60 | 2009-07-31 |  |  | Not planned
136 | R/A | Camerron Harisson |  |  | 56000 | [11 empty] | 2009-04-08 |  | 2009-04-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-05-01 |  | 2009-05-05 |  | 2009-05-13 | 16 | 2009-05-29 | 0 | 2009-05-29 | 60 | 2010-07-02 | 100 | 81 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete his task than originally in his contract. Therefore, payment has been done per working days needed to complete the task.
137 | P | C2.3/CS-IC/09-01 | 2.3 | Consultant - assessment Unit and MEST experts | 186100 | 140406 | IC | PRIOR | 2009-04-02 | 14 | 2009-04-16 | 7 | 2009-04-23 | 14 | 2009-05-07 | 7 | 2009-05-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-05-21 | 14 | 2009-06-04 | 14 | 2009-06-18 | 7 | 2009-06-25 | 7 | 2009-07-02 | 90 | 2009-12-30
138 | R/A | Kelvin Gregory |  |  | 75600 |  |  |  | 2009-02-25 |  | 2009-03-03 |  | 2009-03-03 |  | 2009-04-03 |  | 2009-04-03 |  | 2009-04-15 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-05-04 |  | 2009-05-05 |  | 2009-05-08 |  | 2009-06-29 | 0 | 2009-06-29 | 124 | 2009-10-31 | 100 | 73 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated in his contract. Therefore, payment has been done per working days needed to complete the task.
139 | P | C2.3/CS-IC/09-03 | 2.3 | Consultant - test administration study (intern.) | 46960 |  | IC | PRIOR | 2009-11-25 | 14 | 2009-12-09 | 7 | 2009-12-16 | 14 | 2009-12-30 | 7 | 2010-01-06 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2010-01-13 | 14 | 2010-01-27 | 14 | 2010-02-10 | 7 | 2010-02-17 | 7 | 2010-02-24 | 365 | 2011-02-24
140 | R/A | Steven Bakker |  |  |  | 51800 |  |  | 2009-12-10 | 14 | 2009-12-28 |  | 2010-01-04 |  | 2010-02-04 |  | 2010-03-16 |  | 2010-03-17 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-04-12 |  | 2010-04-13 | 14 | 2010-04-30 | 7 | 2010-05-05 | 0 | 2010-05-05 | 240 | 2010-12-31 | 100 | 100 | Completed
141 | P | C2.3/CS-IC/11-04 | 2.3 | Consultant - Matura reform |  | 50000 | IC | PRIOR | 2011-05-23 | 14 | 2011-06-06 | 7 | 2011-06-13 | 14 | 2011-06-27 | 7 | 2011-07-04 | 7 | 2011-07-11 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-07-18 | 14 | 2011-08-01 | 14 | 2011-08-15 | 7 | 2011-08-22 | 7 | 2011-09-01 | 242 | 2012-04-30
142 | R/A | Steven Bakker |  |  |  | 53150 |  |  | 2011-06-16 |  | 2011-06-17 |  | 2011-06-20 |  | 2011-07-01 |  | 2011-08-10 |  | 2011-08-17 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-08-17 |  | 2011-08-18 |  | 2011-08-24 |  | 2011-08-26 |  | 2011-09-01 |  | 2012-03-09 | 100 | 95 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated
143 | P | C2.3/CS-SSS/12-01 | 2.3 | Supporting the Assessment Reform in Kosovo |  | 29000 | SSS | PRIOR | 2012-06-07 | 14 | 2012-06-11 | 7 | 2012-06-18 | 14 | 2012-07-02 | 7 | 2012-07-09 | 7 | 2012-07-16 |  | 2012-07-16 |  | 2012-07-16 |  | 2012-07-16 |  | 2012-07-16 |  | 2012-07-16 |  | 2012-07-16 |  | 2012-07-16 | 7 | 2012-07-23 | 14 | 2012-08-06 | 14 | 2012-06-21 | 7 | 2012-06-28 | 7 | 2012-07-05 |  | 2013-04-30
144 | R/A | Steven Bakker |  |  |  | 28800 |  |  | 2012-06-07 |  | 2012-06-11 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-06-13 |  | 2012-06-18 |  | 2012-06-21 |  | 2012-07-09 |  | 2012-07-09 |  |  |  |  | Under implementation
145 | P | C2.3/CS-IC-11-05 | 2.3 | IC on Capacity Building for External Assessment in Kosovo |  | 50000 | IC | PRIOR | 2011-05-23 | 14 | 2011-06-06 | 7 | 2011-06-13 | 14 | 2011-06-27 | 7 | 2011-07-04 | 7 | 2011-07-11 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-07-18 | 14 | 2011-08-01 | 14 | 2011-08-15 | 7 | 2011-08-22 | 7 | 2011-08-29 | 306 | 2012-12-31
146 | R/A | Kelvin Gregory |  |  |  | 43650 |  |  | 2011-08-23 |  | 2011-10-17 |  | 2011-10-19 |  | 2011-10-26 |  | 2011-11-02 |  | 2011-11-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-11-14 |  | 2012-02-02 |  | 2012-02-03 |  | 2012-02-06 |  | 2012-02-06 |  | 2012-06-30 | 0 | 0 | Completed
147 | R/A | Kelvin Gregory |  | Amendment #1 extending completion date |  |  |  |  | 2012-05-16 |  | 2012-05-18 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-05-15 |  | 2012-05-16 |  | 2012-05-18 |  | 2012-05-21 |  | 2012-05-21 |  |  |  |  | Under implementation
148 | P | C2.3/CS-IC-11-06 | 2.3 | Consultant Mother Tongue and Modern Foreign Language Exams |  | 21000 | IC | PRIOR | 2011-10-14 | 14 | 2011-10-28 | 7 | 2011-11-04 | 14 | 2011-11-18 | 7 | 2011-11-25 | 7 | 2011-12-02 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-12-09 | 14 | 2011-12-23 | 14 | 2012-01-06 | 7 | 2012-01-13 | 7 | 2011-11-16 | 136 | 2012-03-31
149 | R/A | Ivane Mindadze |  |  |  | 10150 |  |  | 2011-10-14 |  | 2011-10-17 |  | 2011-10-18 |  | 2011-10-26 |  | 2011-11-02 |  | 2011-11-04 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-11-07 |  | 2011-11-11 |  | 2011-11-15 |  | 2011-11-16 |  | 2011-11-16 |  | 2012-03-08 | 76 | 76 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated
150 | P | C2.3/CS-IC-11-07 | 2.3 | Consultant for Supporting the Item Bank Development in Kosovo External Assessment |  | 24000 | IC | PRIOR | 2011-10-14 | 14 | 2011-10-28 | 7 | 2011-11-04 | 14 | 2011-11-18 | 7 | 2011-11-25 | 7 | 2011-12-02 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-12-09 | 14 | 2011-12-23 | 14 | 2012-01-06 | 7 | 2012-01-13 | 7 | 2011-11-23 | 159 | 2012-04-30 |  |  | Under Implementation
151 | R/A | David Tchankotadze |  |  |  | 12520 |  |  | 2011-10-14 |  | 2011-10-17 |  | 2011-10-19 |  | 2011-10-26 |  | 2011-11-02 |  | 2011-11-10 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-11-11 |  | 2011-11-17 |  | 2011-11-22 |  | 2011-11-23 |  | 2011-11-23 |  | 2012-03-21 | 46 | 46 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated
152 | P | C2.4/CS-IC/09-03 | 2.4 | Consultant - EMIS TOR and Training Needs Assitance. | 31000 |  | IC | PRIOR | 2009-11-20 | 14 | 2009-12-04 | 7 | 2009-12-11 | 14 | 2009-12-25 | 7 | 2010-01-01 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2010-01-08 | 14 | 2010-01-22 | 14 | 2010-02-05 | 7 | 2010-02-12 | 7 | 2010-02-19 | 90 | 2010-05-20
153 | R/A | Mircea Enache |  |  |  | 23560 |  |  | 2009-10-05 |  | 2009-10-16 |  | 2009-10-16 |  | 2009-11-30 |  | 2009-12-07 |  | 2009-12-08 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-12-08 |  | 2009-12-08 |  | 2009-12-11 |  | 2009-12-14 | 1 | 2009-12-15 | 197 | 2010-06-30 |  |  | Completed
154 | R/A | Mircea Enache | 2.4 | Amendment #1 extending completion date |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-06-14 |  | 2010-06-15 |  | 2010-06-17 | 8 | 2010-06-25 | 0 | 2010-06-25 | 67 | 2010-08-31 | 100 | 100 | Completed
155 | P | C2.4/CS-IC/09-04 | 2.4 | IT officer to support EMIS Department | 35676 |  | IC | PRIOR | 2009-09-25 | 14 | 2009-10-10 | 7 | 2009-10-12 | 14 | 2009-11-02 | 7 | 2009-11-26 |  | 2009-12-10 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-12-10 | 14 | 2009-12-12 | 14 | 2009-12-15 | 7 | 2009-12-15 | 7 | 2009-12-15 |  | 2013-06-30
156 | R/A | Bersant Krasniqi |  |  |  | 6000 |  |  | 2009-09-15 |  | 2009-09-19 |  | 2009-09-25 |  | 2009-11-15 |  | 2009-12-03 |  | 2009-12-08 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-12-08 |  | 2009-12-11 |  | 2009-12-12 | 3 | 2009-12-15 | 0 | 2009-12-15 | 237 | 2010-08-09 | 100 | 100 | Completed
157 | R/A | Bersant Krasniqi |  | Amendment #1 modification of original contract |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-07-21 |  | 2010-07-22 |  | 2010-07-31 |  | 2010-08-09 | 0 | 2010-08-09 | 128 | 2010-12-15 | 100 | 100 | Completed
158 | R/A | Bersant Krasniqi |  | Amendment #2 extending completion date |  | 13013.4 |  |  | 2010-12-06 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-12-06 |  | 2010-12-07 |  | 2010-12-14 |  | 2010-12-15 |  | 2010-12-15 |  | 2012-06-26 | 80 | 80 | Under Implementation
159 | R/A | Bersant Krasniqi |  | Amendment # 3 extending completion date |  | 8400 |  |  | 2012-06-18 |  | 2012-06-26 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-06-15 |  | 2012-06-18 |  | 2012-06-26 |  | 2012-06-26 |  | 2012-07-01
160 | P | C2.4/CS-IC/10-05 | 2.4 | Consultant to support the upgrade of EMIS |  | 31980 | SSS | PRIOR | 2010-08-19 | 14 | 2010-09-02 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2010-09-09 | 14 | 2010-09-23 | 14 | 2010-10-07 | 7 | 2010-10-14 | 7 | 2011-09-05 | 117 | 2011-12-31
161 | R/A | Mircea Enache |  |  |  | 31980 |  |  | 2010-08-19 |  | 2010-08-27 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-08-29 |  | 2010-08-30 |  | 2010-09-03 |  | 2010-09-03 |  | 2010-09-05 |  | 31-Dec-11 | 100 | 100 | Completed
162 | R/A | Mircea Enache |  | Amendment #1 modification of original contract |  | 10000 |  |  | 2011-12-15
163 | P | C2.5/CS-SSS/09-01 | 2.5 | National firm to draft project action plan | 20300 |  | SSS | PRIOR | 2008-05-20 | 14 | 2008-06-03 | 7 | 2008-06-10 | 14 | 2008-06-24 | 7 | 2008-07-01 | 7 | 2008-07-08 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2008-07-15 | 14 | 2008-07-29 | 14 | 2008-08-12 | 7 | 2008-08-19 | 7 | 2008-08-26 | 30 | 2008-09-25
164 | R/A | Kosova Education Center KEC |  |  |  | 12780 | [6 empty] | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | [7 empty] | 2008-06-20 |  | 2008-06-20 | 38 | 2008-07-28 | 100 | 100 | Completed
165 | P | No Number | 2.5 | Project coordinator | 71300 |  | IC | PRIOR |  | 14 |  | 7 |  | 14 |  | 7 |  | 7 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 |  | 14 |  | 14 |  | 7 |  | 7
166 | R/A | Xhafer Ahmeti |  |  |  | 15600 | [14 empty] | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | [7 empty] | 2008-03-10 | 0 | 2008-03-10 | 365 | 2009-03-10 |  |  | Completed | Not planned
167 | R/A | Xhafer Ahmeti | 2.5 | Amendment #1 modification of original contract |  | 885 | [6 empty] | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | [7 empty] | 2009-03-11 | 0 | 2009-03-11 | 20 | 2009-03-31 |  |  | Completed
168 | R/A | Xhafer Ahmeti | 2.5 | Amendment #2 modification of original contract |  | 1300 | [6 empty] | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | [7 empty] | 2009-04-01 | 0 | 2009-04-01 | 29 | 2009-04-30 | 100 | 73 | Completed
169 | P | C2.5/CS-IC/09-02 | 2.5 | Project coordinator | 0 |  | IC | PRIOR | 2009-02-16 | 14 | 2009-03-02 | 7 | 2009-03-09 | 14 | 2009-03-23 | 7 | 2009-03-30 | 7 | 2009-04-06 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-04-13 | 14 | 2009-04-27 | 14 | 2009-05-11 | 7 | 2009-05-18 | 7 | 2010-05-12 | 780 | 2012-12-31
170 | R/A | Edita Alo |  |  |  | 26400 | [6 empty] | 2009-03-09 |  | 2009-03-10 |  | 2009-04-06 |  | 2009-04-27 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-04-25 |  | 2009-04-25 |  | 2009-04-27 |  | 2009-05-12 | 1 | 2009-05-12 | 364 | 2010-05-11 | 100 | 100 | Completed
171 | R/A | Edita Alo | 2.5 | Amendment #1 modification of original contract |  | 56393.33 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-05-09 |  | 2010-05-10 |  | 2010-05-12 | 0 | 2010-05-12 | 0 | 2010-05-12 | 82 | 2010-08-02 | 100 | 100 | Completed
172 | R/A | Edita Alo | 2.5 | Amendment # 2 modification of original contract |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-07-22 |  | 2010-07-22 |  | 2010-08-02 | 0 | 2010-08-02 |  | 2012-06-30 | 100 | 100 | Completed
173 | R/A | Edita Alo | 2.5 | Amendment #3 modification of original contract |  | 13200 |  |  | 2012-06-18 |  | 2012-06-20 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-06-15 |  | 2012-06-18 |  | 2012-06-20 |  | 2012-06-21 |  | 2012-07-01 |  |  |  |  | Under Implementation
174 | P | C2.5/CS-IC/09-03 | 2.5 | Financial manager | 61100 |  | IC | PRIOR | 2008-08-28 | 14 | 2008-09-11 | 7 | 2008-09-18 | 14 | 2008-10-02 | 7 | 2008-10-09 | 7 | 2008-10-16 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2008-10-23 | 14 | 2008-11-06 | 14 | 2008-11-20 | 7 | 2008-11-27 | 7 | 2010-10-15 | 624 | 2012-06-30
175 | R/A | Gazmend Bajra |  |  |  | 27600 | [8 empty] | 2008-07-03 | [5 empty] | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | [7 empty] | 2008-10-06 |  | 2008-10-15 | 365 | 2009-10-15 | 100 | 100 | Completed
176 | R/A | Gazmend Bajra | 2.5 | Amendment #1 modification of original contract |  | 2070 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-10-02 |  | 2009-10-02 |  | 2009-10-03 |  | 2009-10-15 |  | 2009-10-15 | 365 | 2010-10-15 | 100 | 100 | Completed
177 | R/A | Gazmend Bajra | 2.5 | Amendment #2 modification of original contract |  | 27111.25 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-10-05 |  | 2010-10-06 |  | 2010-10-08 |  | 2010-10-14 |  | 2010-10-15 |  | 2012-06-30 | 100 | 100 | Completed
178 | R/A | Gazmend Bajra | 2.5 | Amendment #3 modification of original contract |  | 793 |  |  | 2012-06-19 |  | 2012-06-20 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-06-15 |  | 2012-06-19 |  | 2012-06-20 |  | 2012-06-21 |  | 2012-06-01 |  | 2012-06-30 | 100 | 100 | Completed
179 | P | C2.5/CS-IC/12-02 | 2.5 | Financial manager |  | 9000 | IC | PRIOR | 2012-06-13 | 14 | 2012-06-27 | 7 | 2012-07-04 | 14 | 2012-07-18 | 7 | 2012-07-25 | 7 | 2012-08-01 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2012-08-08 | 14 | 2012-08-22 | 14 | 2012-09-05 | 7 | 2012-09-12 | 1 | 2012-06-19 |  | 2013-06-30
180 | R/A | Mirjeta Hysa |  |  |  | 7200 |  |  | 2012-06-13 |  | 2012-06-13 |  | 2012-06-13 |  | 2012-06-14 |  | 2012-06-15 |  | 2012-05-15 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-05-15 |  | 2012-05-15 |  | 2012-05-15 |  | 2012-05-19 |  | 2012-06-19 |  |  |  |  | Under Implementation
181 | P | No number | 2.5 | Procurement Officer | 49000 |  | IC | PRIOR | 2008-07-09 | 14 | 2008-07-23 | 7 | 2008-07-30 | 14 | 2008-08-13 | 7 | 2008-08-20 | 7 | 2008-08-27 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2008-09-03 | 14 | 2008-09-17 | 14 | 2008-10-01 | 7 | 2008-10-08 | 7 | 2008-10-15 | 365 | 2009-10-15
182 | R/A | Vlora Kuqi |  |  |  | 13800 | [10 empty] | 2008-07-03 |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | [7 empty] | 2008-10-06 |  | 2008-10-15 | 365 | 2009-10-15 | 100 | 100 | Completed
183 | P | C2.5/CS-IC/09-04 | 2.5 | Procurement Officer | 0 |  | IC | PRIOR | 2009-10-11 | 14 | 2009-10-25 | 7 | 2009-11-01 | 14 | 2009-11-15 | 7 | 2009-11-22 | 7 | 2009-11-29 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-12-06 | 14 | 2009-12-20 | 14 | 2010-01-03 | 7 | 2010-01-10 | 7 | 2011-08-01 | 334 | 2012-12-31
184 | R/A | Luan Asllani | 2.5 |  |  | 10800 |  |  | 2009-10-11 |  | 2009-10-25 |  | 2009-10-25 |  | 2009-11-11 |  | 2010-01-20 |  | 2010-01-21 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-01-22 |  | 2010-01-22 |  | 2010-01-27 |  | 2010-02-03 | 0 | 2010-02-03 | 365 | 2011-02-03 | 100 | 100 | Completed
185 | R/A | Luan Asllani | 2.5 | Amendment #1 modification of original contract |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA | N | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-07-14 |  | 2010-07-14 |  | 2010-08-11 |  | 2010-08-12 |  | 2010-08-12 | 175 | 2011-02-03 | 100 | 100 | Completed
186 | R/A | Luan Asllani | 2.5 | Amendment #2 modification of original contract |  | 5400 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-01-20 |  | 2011-01-20 |  | 2011-01-21 |  | 2011-02-01 |  | 2011-02-01 | 180 | 2011-07-31 | 100 | 100 | Completed
187 | R/A | Luan Asllani | 2.5 | Amendment #3 modification of original contract | 0 | 11550 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-07-15 |  | 2011-07-20 |  | 2011-08-03 |  | 2011-08-03 |  | 2011-08-01 |  | 2012-06-30 | 100 | 100 | Completed
188 | R/A | Luan Asllani | 2.5 | Amendment #4 modification of original contract |  | 6300 |  |  | 2012-06-18 |  | 2012-06-20 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-06-15 |  | 2012-06-15 |  | 2012-06-20 |  | 2012-06-21 |  | 2012-07-01 |  | 2012-08-31 |  |  | Completed
189 | P | C2.5/CS-IC/09-05 | 2.5 | Administrative assistant | 40800 |  | IC | PRIOR | 2009-04-18 | 14 | 2009-05-02 | 7 | 2009-05-09 | 14 | 2009-05-23 | 7 | 2009-05-30 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-06-06 | 14 | 2009-06-20 | 14 | 2009-07-04 | 7 | 2009-07-11 | 7 | 2010-07-15 | 716 | 2012-12-31
190 | R/A | Altin Ademi |  |  |  | 6000 | [10 empty] | 2009-06-21 |  | 2009-06-23 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-07-12 |  | 2009-07-12 |  | 2009-07-14 |  | 2009-07-15 | 0 | 2009-07-15 | 365 | 2010-07-15 | 100 | 100 | Completed
191 | R/A | Altin Ademi | 2.5 | Amendment #1 modification of original contract |  | 1000 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-02-21 |  | 2010-02-22 |  | 2010-02-22 |  | 2010-02-22 | 0 | 2010-02-22 | 143 | 2010-07-15 | 100 | 100 | Completed
192 | R/A | Altin Ademi | 2.5 | Amendment #2 modification of original contract |  | 16450 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-07-15 |  | 2010-07-15 |  | 2010-07-15 |  | 2010-07-15 |  | 2010-07-15 |  | 2012-06-30 | 100 | 100 | Completed
193 | R/A | Altin Ademi | 2.5 | Amendment #3 modification of original contract |  | 4200 |  |  | 2012-06-18 |  | 2012-06-20 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-06-15 |  | 2012-06-18 |  | 2012-06-20 |  | 2012-06-21 |  | 2012-07-01 |  |  |  |  | Under Implementation
194 | P | No Number | 2.5 | Consultant - implementation adviser | 55700 |  | IC | PRIOR | 2008-05-25 | 14 | 2008-06-08 | 7 | 2008-06-15 | 14 | 2008-06-29 | 7 | 2008-07-06 | 7 | 2008-07-13 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2008-07-20 | 14 | 2008-08-03 | 14 | 2008-08-17 | 7 | 2008-08-24 | 7 | 2008-08-31 | 426 | 2009-10-31
195 | R/A | Vas Demetriou |  |  | 54194 |  |  |  | 2008-06-25 |  | 2008-07-01 | [5 empty] | 2008-07-16 |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2008-07-30 |  | 2008-07-30 |  | 2008-07-31 |  | 2008-08-22 | 1 | 2008-08-23 | 122 | 2008-12-23 | 100 | 100 | Completed
196 | R/A | Vas Demetriou | 2.5 | Amendment #1 extending completion date |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-02-17 |  | 2009-02-17 |  | 2009-02-18 |  | 2008-12-23 | 0 | 2008-12-23 | 262 | 2009-09-11 | 100 | 100 | Completed
197 | R/A | Vas Demetriou | 2.5 | Amendment #2 extending completion date |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-09-07 |  | 2009-09-07 |  | 2009-09-08 |  | 2009-09-11 |  | 2009-06-30 | 123 | 2009-10-31 | 100 | 100 | Completed
198 | P | C2.5/CS-LCS/09-08 | 2.5 | Firm - project accounts audit (external) | 64600 |  | LSC | PRIOR | 2010-12-31 | 14 | 2011-01-14 | 7 | 2011-01-21 | 15 | 2011-02-05 | 14 | 2011-02-19 |  | NA |  | NA |  | NA | 7 | 2011-02-26 | 15 | 2011-03-13 |  | NA |  | NA |  | NA | 7 | 2011-03-20 | 14 | 2011-04-03 | 21 | 2011-04-24 | 14 | 2011-05-08 | 7 | 2011-05-15 | 90 | 2011-08-13
199 | R/A | ERNST & YOUNG | 2.5 |  |  | 1000 | [39 empty] | 100 | 100 | Completed
200 | R/A | KPMG | 2.5 | Firm - project accounts audit (external) |  | 1700 | [39 empty] | 100 | 100 | Completed
201 | R/A | KPMG | 2.5 | Firm - project accounts audit (external) |  | 1700
202 | P | C2.5/CS-LCS/11-10 | 2.5 | Firm - project accounts audit (external) | 0 | 25600 | LSC | PRIOR | 2012-09-01 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA
203 | R/A | Ficadex Albania LTD |  | Audit for period Jan.- Dec.2011 |  | 1688 | [39 empty] | 100 | 100 | Completed
204 | p | C2.5/CS-SSS/12-01 | 2.5 | Short Term Procurement Specialist |  | 3500 | SSS | PRIOR | 2012-04-23 | 14 | 2012-05-07 | 7 | 2012-05-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-04-22 | 1 | 2012-04-23 | 14 | 2012-05-07 | 1 | 2012-05-08 | 1 | 2012-05-09 |  | 2012-06-30
205 | R/A | Aleksandar Najdovski |  |  |  | 3450 |  |  | 2012-04-23 |  | 2012-04-26 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-04-26 | 1 | 2012-04-26 |  | 2012-04-27 |  | 2012-04-30 |  | 2012-04-30 |  | 2012-05-15 |  |  | Completed
206 | R/A | Aleksandar Najdovski |  | Amendment #1 extending completion date |  |  |  |  | 2012-05-15 |  | 2012-05-15 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-05-15 |  | 2012-05-15 |  | 2012-05-15 |  | 2012-05-15 |  | 2012-05-15 |  | 2012-06-28 |  |  | Completed
207 |  | 3. CREATING CONDITIONS TO INTRODUCE EFFICIENT DESIGNS IN KOSOVO'S SCHOOLS
208
209 |  | CONSULTANTS
210 | P | C2.5/CS-IC/09-07 | 3 | Consultant - implementation adviserfor component 3 | 0 |  |  | PRIOR | 2009-10-09 | 14 | 2009-10-23 | 7 | 2009-10-30 | 14 | 2009-11-13 | 14 | 2009-11-27 | 7 | 2009-12-04 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 14 | 2009-12-18 | 14 | 2010-01-01 | 7 | 2010-01-08 | 7 | 2010-01-15 | 531 | 2011-06-30
211 | R/A | Vas Demetriou |  |  |  | 45120 | SSS |  | 2009-10-01 | 14 | 2009-10-09 | 7 | NA | 14 | NA |  | NA |  | 2009-10-09 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-10-12 |  | 2009-10-13 |  | 2009-10-13 |  | 2009-10-15 | 16 | 2009-11-01 | 425 | 2010-12-31 |  |  | Completed
212 | R/A | Vas Demetriou | 3 | Amendment #1 extending completion date |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-12-16 |  | 2010-12-17 |  | 2010-12-22 |  | 2010-12-23 | 8 | 2010-12-31 | 181 | 2011-06-30 | 100 | 60 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated in his contract. Therefore, payment has been done per working days needed to complete the task.
213 | P | C3.1/CS-SSS/11-01 | 3.1 | Implementation adviser for component 3 |  | 27540 | SSS | PRIOR | 2011-08-03 | 14 | 2011-08-17 | 7 | 2011-08-24 | 14 | 2011-09-07 | 14 | 2011-09-21 | 7 | 2011-09-28 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2011-10-05 | 14 | 2011-10-19 | 14 | 2011-11-02 | 7 | 2011-11-09 | 7 | 2011-09-01 | 668 | 2013-06-30
214 | R/A | Vas Demetriou |  |  |  | 37840 |  |  | 2011-08-03 |  | 2011-08-17 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-08-18 |  | 2011-08-18 |  | 2011-08-25 |  | 2011-08-26 |  | 2011-09-01 |  | 2012-06-30 | 30 | 0 | Completed
215 | R/A | Vas Demetriou |  | Amendment #1 extending completion date |  |  |  |  | 2012-06-15 |  | 2012-06-20 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-06-14 |  | 2012-06-14 |  | 2012-06-20 |  | 2012-06-21 |  | 2012-07-01 |  |  |  |  | Under Implementation
216 | P | C3.1/CS-CQS/09-01 | 3.1 | Firm - school mapping and investment planning | 166700 |  | CQS | PRIOR | 2008-12-07 | 14 | 2008-12-21 | 7 | 2008-12-28 | 14 | 2009-01-11 | 14 | 2009-01-25 |  | NA |  | NA |  | NA | 7 | 2009-02-01 | 14 | 2009-02-15 |  | NA |  | NA |  | NA | 7 | 2009-02-22 | 21 | 2009-03-15 | 14 | 2009-03-29 | 14 | 2009-04-12 | 7 | 2009-04-19 | 256 | 2009-12-31
217 | R/A | TELOS |  |  |  | 136400 |  |  | 2009-12-05 |  | 2009-12-17 |  | 2008-12-19 |  | 2009-01-16 |  | 2009-03-03 |  | 2009-03-03 |  | 2009-03-09 |  |  |  | 2009-03-10 |  | 2009-04-10 |  | 2009-04-19 |  | 2009-05-13 |  | 2009-05-13 |  | 2009-05-15 |  | 2009-05-20 |  | 2009-05-28 |  | 2009-05-29 | 4 | 2009-06-01 | 133 | 2009-10-12 |  |  | Completed
218 | R/A | TELOS | 3.1 | Amendment #1 extending completion date |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-08-26 |  | 2009-08-27 |  | 2009-08-27 |  | 2009-08-15 | 0 | 2009-08-15 | 83 | 2009-11-06 |  |  | Completed
219 | R/A | TELOS | 3.1 | Amendment #2 extending completion date |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-11-04 |  | 2009-11-05 |  | 2009-11-05 |  | 2009-11-05 | 0 | 2009-11-05 | 56 | 2009-12-31 | 100 | 95 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated in his contract. Therefore, payment has been done per working days needed to complete the task.
220 | P | C3.1/CS-CQS/09-02 | 3.1 | Firm - inventory taking for 1100 schools | 287400 |  | CQS | PRIOR | 2009-07-09 | 14 | 2009-07-23 | 7 | 2009-07-30 | 14 | 2009-08-13 | 14 | 2009-08-27 |  | NA |  | NA |  | NA | 7 | 2009-09-03 | 14 | 2009-09-17 |  | NA |  | NA |  | NA | 7 | 2009-09-24 | 21 | 2009-10-15 | 14 | 2009-10-29 | 14 | 2009-11-12 | 7 | 2009-11-19 | 407 | 2010-12-31
221 | R/A | CMC |  |  |  | 202280 |  |  | 2009-08-10 |  | 2009-09-11 |  | 2009-08-05 |  | 2009-08-17 |  | 2009-09-30 |  | 2009-10-06 |  | 2009-10-15 |  | 2009-10-25 |  | 2009-10-26 |  | 2009-11-09 | [7 empty] | 2009-11-18 |  | 2009-11-18 |  | 2009-12-18 |  | 2009-12-23 | 11 | 2010-01-04 | 168 | 2010-06-21 |  |  | Combined Areas A and B
222 | R/A | CMC | 3.1 | Amendment #1 extending completion date |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-07-17 |  | 2010-07-17 |  | 2010-06-18 |  | 2010-06-21 | 0 | 2010-06-21 | 91 | 2010-09-20 |  |  | Completed
223 | R/A | CMC | 3.1 | Amendment # 2 extending completion date |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-09-14 |  | 2010-09-14 |  | 2010-09-16 |  | 2010-09-20 | 11 | 2010-10-01 | 91 | 2010-12-31 | 100 | 100 | Completed
224 | P | C3.1/CS-IC/09-04 | 3.1 | Consultant - Manager for 3.1 activities (national) | 41200 |  | IC | PRIOR | 2009-04-13 | 14 | 2009-04-27 | 7 | 2009-05-04 | 14 | 2009-05-18 | 7 | 2009-05-25 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-06-01 | 14 | 2009-06-15 | 14 | 2009-06-29 | 7 | 2009-07-06 | 7 | 2009-07-13 | 362 | 2010-07-10
225 | R/A | Merita Behluli |  |  |  | 16200 |  |  | 2009-01-08 |  |  |  | 2009-01-10 |  | 2009-01-19 |  | 2009-06-23 |  | 2009-06-25 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-07-02 |  | 2009-07-04 |  | 2009-07-09 |  | 2009-07-10 | 0 | 2009-07-10 | 227 | 2010-02-22 |  |  | Completed
226 | R/A | Merita Behluli | 3.1 | Amendment #1 modification of original contract |  | 1300 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-02-21 |  | 2010-02-22 |  | 2010-02-23 |  | 2010-02-22 | 0 | 2010-02-22 | 138 | 2010-07-10 | 100 | 96 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated in his contract. Therefore, payment has been done per working days needed to complete the task.
227 | P | C3.1/CS-SSS/10-05 | 3.1 | Consultant for Priority 3 Activities |  | 16500 | SSS | PRIOR | 2010-07-01 | 14 | 2010-07-15 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2010-07-22 | 14 | 2010-08-05 | 14 | 2010-08-19 | 14 | 2010-09-02 | 7 | 2011-08-01 | 334 | 2013-06-30
228 | R/A | Merita Behluli |  |  |  | 16500 |  |  | 2010-07-01 |  | 2010-07-22 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-07-22 |  | 2010-07-22 |  | 2010-07-23 |  | 2010-08-01 | 0 | 2010-08-01 | 364 | 2011-07-31 | 100 | 100 | Completed
229 | R/A | Merita Behluli | 3.1 | Amendment #1 modification of original contract |  | 13970 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-07-23 |  | 2011-07-28 |  | 2011-08-04 |  | 2011-08-05 |  | 2011-08-01 |  | 2012-06-30 | 90 | 90 | Completed
230 | R/A | Merita Behluli | 3.1 | Amendment #1 modification of original contract |  | 7150 |  |  | 2012-06-28 |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-06-07 |  | 2012-06-27 |  | 2012-06-29 |  | 2012-06-29 |  | 2012-07-01 |  |  |  |  | Under Implementation
231 | P | C3.2/CS-CQS/09-01 | 3.2 | Firm - school standards and norms & manual | 167500 |  | CQS | PRIOR | 2008-12-07 | 14 | 2008-12-21 | 7 | 2008-12-28 | 14 | 2009-01-11 | 14 | 2009-01-25 |  | NA |  | NA |  | NA | 7 | 2009-02-01 | 14 | 2009-02-15 |  | NA |  | NA |  | NA | 7 | 2009-02-22 | 21 | 2009-03-15 | 14 | 2009-03-29 | 14 | 2009-04-12 | 7 | 2009-04-19 | 90 | 2009-12-21
232 | R/A | EME |  |  |  | 100538 | [24 empty] | 2009-05-27 |  |  |  | 2009-07-02 |  | 2009-07-18 |  | 2009-07-20 |  | 2009-07-21 | 0 | 2009-07-21 | 289 | 2010-05-06 | 60 | 60 | Terminated on: 6-May-2010
233 | P | C3.2/CS-SSS/10-02 | 3.2 | School standards and norms & manual |  | 40000 | SSS | PRIOR | 2010-05-15 | 14 | 2010-05-29 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2010-06-05 | 21 | 2010-06-26 | 14 | 2010-07-10 | 14 | 2010-07-24 | 7 | 2010-07-31 | 183 | 2011-01-30
234 | R/A | Daniel Dupety | 3.2 |  |  | 38760 |  |  | 2010-06-01 |  | 2010-06-08 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-06-08 |  | 2010-06-10 |  | 2010-06-11 |  | 2010-06-15 | 0 | 2010-06-15 | 168 | 2010-11-30 |  |  | Completed
235 | R/A | Daniel Dupety | 3.2 | Amendment #1 extending completion date |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-12-12 |  | 2010-12-12 |  | 2010-11-30 |  | 2010-11-30 | 0 | 2010-11-30 | 61 | 2011-01-30 | 100 | 93 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated in his contract. Therefore, payment has been done per working days needed to complete the task.
236 | P | C3.3/CS-QCBS/09-01 | 3.3 | Firm - design and supervision of model schools | 572400 | 450000 | QCBS | PRIOR | 2010-07-26 | 14 | 2010-08-09 | 7 | 2010-08-16 | 45 | 2010-09-30 | 14 | 2010-10-14 | 14 | 2010-10-28 | 14 | 2010-11-11 | 14 | 2010-11-25 | 7 | 2010-12-02 | 45 | 2011-01-16 | 14 | 2011-01-30 | 14 | 2011-02-13 | 7 | 2011-02-20 | 7 | 2011-02-27 | 14 | 2011-03-13 | 14 | 2011-03-27 | 7 | 2011-04-03 | 7 | 2011-04-01 | 456 | 2013-05-31
237 | R/A | Urban plus |  |  |  | 178921 |  |  | 2009-07-01 |  | 2009-07-22 |  | 2009-07-24 |  | 2009-08-24 |  | 2009-10-02 |  | 2009-12-03 |  | 2010-08-20 |  | 2010-08-25 |  | 2010-08-26 |  | 2010-10-01 |  | 2010-10-15 |  | 2010-12-09 |  | 2010-12-20 |  | 2011-03-28 |  | 2011-03-29 |  | 2011-03-31 |  | 2011-04-01 | 1 | 2011-04-01 |  | 2012-06-30 | 52 | 52 | Completed
238 | R/A | Urban plus | 3.3 | Amendment #1 extending completion date |  |  |  |  | 2012-03-14 |  | 2012-03-16 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-03-13 |  | 2012-03-13 |  | 2012-03-16 |  | 2012-03-22 |  | 2012-03-22 |  |  |  |  | Under Implementation
239 |  | COMPONENT 4. FINANCING MECHANISMS FOR HIGHER EDUCATION
240 |  | CONSULTANTS
241 | P | C4.1/CS-IC/09-01 | 4.1 | Consultant - higher education legisl. & sustain. | 69800 |  | IC | PRIOR | 2009-02-02 | 14 | 2009-02-16 | 7 | 2009-02-23 | 14 | 2009-03-09 | 7 | 2009-03-16 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-03-23 | 14 | 2009-04-06 | 14 | 2009-04-20 | 7 | 2009-04-27 | 7 | 2009-05-04 | 50 | 2009-12-30
242 | R/A | Steve Bristow |  |  |  | 54500 |  |  | 2008-12-10 |  | 2008-12-19 | [5 empty] | 2009-04-08 |  | 2009-04-08 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-04-20 |  | 2009-04-28 |  | 2009-05-01 |  | 2009-05-01 | 7 | 2009-05-08 | 145 | 2009-09-30 | 100 | 99 | Completed
243 | P | No Number | 4.1 | Consultant - local counterpart of intern. Cons. | 6768 |  | IC | PRIOR | 2009-04-11 | 14 | 2009-04-25 | 7 | 2009-05-02 | 14 | 2009-05-16 | 7 | 2009-05-23 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-05-30 | 14 | 2009-06-13 | 14 | 2009-06-27 | 7 | 2009-07-04 | 7 | 2009-07-11 | 60 | 2009-12-12
244 | R/A | Jehona Lushaku |  |  |  | 4800 |  |  | 2008-12-05 |  | 2008-12-12 |  | 2009-06-06 |  | 2009-06-10 |  | 2009-06-17 |  | 2009-06-18 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-06-22 |  | 2009-07-03 |  | 2009-07-07 |  | 2009-07-08 | 2 | 2009-07-10 | 155 | 2009-12-12 | 50 | 50 | Terminated on: 12-Dec-09
245 | P | C4.1/CS-IC/09-02 | 4.1 | Consultant - local counterpart of intern. Cons. | 14100 |  | SSS | PRIOR | 2010-01-10 | 14 | 2010-01-24 | 7 | 2010-01-31 | 14 | 2010-02-14 | 7 | 2010-02-21 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2010-02-28 | 14 | 2010-03-14 | 14 | 2010-03-28 | 7 | 2010-04-04 | 7 | 2010-01-20 | 70 | 2010-03-31
246 | R/A | Blerim Saqipi |  |  |  | 2600 |  |  | 2010-01-10 |  | 2010-01-13 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-01-15 |  | 2010-01-16 |  | 2010-01-19 |  | 2010-01-20 | 0 | 2010-01-20 | 70 | 2010-03-31 | 100 | 100 | Completed
247 | P | C4.1/CS-IC/09-04 | 4.1 | Consultant - evaluation of EPIP II | 0 |  | IC | PRIOR | 2009-08-15 | 14 | 2009-08-29 | 7 | 2009-09-05 | 14 | 2009-09-19 | 7 | 2009-09-26 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-10-03 | 14 | 2009-10-17 | 14 | 2009-10-31 | 7 | 2009-11-07 | 7 | 2009-11-14 |  | 2009-12-10 |  |  | Not planned
248 | R/A | Tom Guegon |  |  |  | 13026 |  |  | 2009-08-05 |  | 2009-08-11 |  |  |  | 2009-09-22 |  | 2009-10-01 |  | 2009-10-03 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-10-03 |  | 2009-10-05 |  | 2009-10-15 |  | 2009-10-19 | 1 | 2009-10-20 | 51 | 2009-12-10 | 100 | 93 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated in his contract. Therefore, payment has been done per working days needed to complete the task.
249 | P | C4.1/CS-IC/09-05 | 4.1 | Consultant - SMD Grants (EPIP II) procurement |  | 62780 | IC | PRIOR | 2009-08-15 | 14 | 2009-08-29 | 7 | 2009-09-05 | 14 | 2009-09-19 | 7 | 2009-09-26 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-10-03 | 14 | 2009-10-17 | 14 | 2009-10-31 | 7 | 2009-11-07 | 7 | 2009-11-14 | 412 | 2010-12-31
250 | R/A | Alexandar Najdovski | [6 empty] | 2009-08-10 |  | 2009-08-20 |  | 2009-08-22 |  | 2009-09-07 |  | 2009-09-08 |  | 2009-09-10 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-09-11 |  | 2009-09-13 |  | 2009-09-17 |  | 2009-10-01 | 4 | 2009-10-05 | 10 | 2009-10-15 | 100 | 100 | Completed
251 | R/A | Alexandar Najdovski | 4.1 | Amendment #1 modification of original contract |  | 20550 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-10-14 |  | 2009-10-15 |  | 2009-10-19 |  | 2009-10-15 | 0 | 2009-10-05 | 87 | 2009-12-31 | 100 | 100 | Completed
252 | R/A | Alexandar Najdovski | 4.1 | Amendment #2 modification of original contract |  | 30900 |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-01-14 |  | 2010-01-15 |  | 2010-01-19 |  | 2009-12-30 | 2 | 2010-01-01 | 364 | 2010-12-31 | 100 | 100 | Completed
253 | P | C4.1/CS-IC/11-05 | 4.1 | Consultant for the implementation of higher education legislation (international) |  | 30000 | IC | PRIOR | 2011-11-01 | 14 | 2011-11-15 | 7 | 2011-11-22 | 14 | 2011-12-06 | 7 | 2011-12-13 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 3 | 2011-12-16 | 5 | 2011-12-21 | 5 | 2011-12-26 | 3 | 2011-12-29 | 1 | 2011-12-30 | 153 | 2012-06-30
254 | R/A | Stephen l. Bristow |  |  |  | 22940 |  |  | 2011-10-27 |  | 2011-11-09 |  | 2011-11-25 |  | 2011-12-07 |  | 2012-01-12 |  | 2012-01-27 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-01-27 |  | 2012-02-01 |  | 2012-02-03 |  | 2012-02-03 |  | 2012-02-03 |  | 2012-05-22 |  |  | Completed
255 | R/A | Stephen l. Bristow |  | Amendment #1 extending completion date |  |  |  |  | 2012-05-21 |  | 2012-05-22 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2012-05-15 |  | 2012-05-18 |  | 2012-05-22 |  | 2012-05-23 |  | 2012-05-23 |  | 2012-06-30 | 92 | 92 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated
256 | P | C4.2/CS-IC/09-02 | 4.2 | Consultant - higher educ. financial sustainability | 69800 |  | IC | PRIOR | 2009-05-15 | 14 | 2009-05-29 | 7 | 2009-06-05 | 14 | 2009-06-19 | 7 | 2009-06-26 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA | 7 | 2009-07-03 | 14 | 2009-07-17 | 14 | 2009-07-31 | 7 | 2009-08-07 | 7 | 2009-08-14 | 366 | 2010-08-15
257 | R/A | Sigurd Hoellinger | 4.2 |  |  | 66725 |  |  | 2008-12-10 |  | 2008-12-19 |  |  |  | 2009-03-30 |  | 2009-04-06 |  | 2009-05-06 |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2009-06-10 |  | 2009-07-20 |  | 2009-07-28 |  | 2009-09-04 | 0 | 2009-09-04 | 133 | 2010-01-15 |  |  | Completed
258 | R/A | Sigurd Hoellinger | 4.2 | Amendment #1 extending completion date |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-01-18 |  | 2010-01-18 |  | 2010-01-19 |  | 2010-01-15 | 0 | 2010-01-15 | 75 | 2010-03-31 |  |  | Completed
259 | R/A | Sigurd Hoellinger | 4.2 | Amendment #2 extending completion date |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-03-23 |  | 2010-03-23 |  | 2010-03-24 |  | 2010-03-31 | 0 | 2010-03-31 | 61 | 2010-05-31 |  |  | Completed
260 | R/A | Sigurd Hoellinger | 4.2 | Amendment #3 extending completion date |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-05-24 |  | 2010-05-24 |  | 2010-05-25 |  | 2010-05-31 | 0 | 2010-05-31 | 30 | 2010-06-30 |  |  | Completed
261 | R/A | Sigurd Hoellinger | 4.2 | Amendment #4 extending completion date |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2010-08-28 |  | 2010-08-28 |  | 2010-06-29 |  | 2010-07-02 | 0 | 2010-07-02 | 44 | 2010-08-15 | 100 | 92 | The Consultant has completed his task and has been paid for the work completed. However, less days were needed by the consultant to complete this task than what was originally stated in his contract. Therefore, payment has been done per working days needed to complete the task.
Legend:
Green color under column A (line number) denotes ongoing activities
Orange color denotes activities to start
QCBS = Quality and Cost-based Selection (in accordance with sections 2.1 - 2.28 of the Guidelines)
FBC = Fixed Budget Selection (in accordance with section 3.5 of the Guidelines)
LCS = Least-Cost Selection (in accordance with section 3.6 of the Guidelines)
CQS = Selection Based on consultants' Qualifications (in accordance with section 3.7 of the Guidelines)
IC = Selection of Individual Consultants (in accordance with sections 5.1 - 5.4 of the Guidelines)
SSS = Single Source Selection in accordance with sections 3.09 - 3.13 of the Guidelines
NA = Not Applicable
OTHER = Direct expenditures
Notes:
a/ Interval for preparation/clearance (days); working document PP only
b/ Number of days to execute the contract; working document PP only | Fees for participation in PISA. This is not a procurement activity but it is keep in the PP for completeness
c/ Estimates include price contingencies
d/ Status: P=Planned (original scope and estimate); R/A=Revised or Actual
Prior Review:
All QCBS contracts, first two CQS contracts, and first two IC contracts irrespective of cost
All contracts with firms estimated to cost US$ 50,000 or more
All contracts with individual consultants (IC) estimated to cost US$ 25,000 or more
All Single source selection contracts
Formulas:
WB "No Objection" = [Prep of TOR]+[Int. /a]
WB "No Objection" = [Negot. /Draft Contract]+[Int. /a]
EOI/ Advert. Date = [WB "No Objection"]+[Int. /a]
Subm. of EOI = [EOI/ Advert. Date]+[Int. /a]
Eval. Of EOI/SL = [Subm. of EOI]+[Int. /a]
Invitation for Neg. = [Eval. Of EOI/SL]+[Int. /a]
Invitation for Neg. = [Sub. Of Proposals]+[Int. /a]
Negot. /Draft Contract = [Invitation for Neg.]+[Int. /a]
Negot. /Draft Contract = [WB "No Objection"]+[Int. /a]
Contract Signature = [WB "No Objection"]+[Int. /a]
Start = [Contract Signature]+[Int. /a]
Compl. = [Start]+[Exec. /b]
Compl. = [Exec. /b]+[Start]
Issue of RFP/Inv. = [Eval. Of EOI/SL]+[Int. /a]
Issue of RFP/Inv. = [WB "No Objection"]+[Int. /a]
Sub. Of Proposals = [Issue of RFP/Inv.]+[Int. /a]
Prep. Of RFP = [WB "No Objection"]+[Int. /a]
Tech. Eval. = [Sub. Of Proposals]+[Int. /a]
Open. Of Fin. Proposals = [WB "No Objection"]+[Int. /a]
Open. Of Fin. Proposals = [Sub. Of Proposals]+[Int. /a]
Note on G102: Kashmira H. Daruwalla: UPDATE DATES. THIS COMPONENT HAS BEEN MOVED TO WORKS&GOODS, SINCE HAS A TRESHOLD OF 35.000 Euros AND NEED TO BE PURCHASED UNDER THE GOODS PROCUDRES. By Luan.
Note on E208: luana: Procurement procedures manged by Ministry of Finance and Economy

## Training
Ln. # | Status P R/A d/ | Contract Reference # Standard Prefix "KOS-IDEP/H3420/" removed from below listings | Comp. | Activity Description | 2012-10-16 14:49 |  | WB Review | Schedule (dd-Mmm-yy) | [8 empty] | Comments | Procure- ment Accounts
[5 empty] | Appraisal Estimates P (planned) Enter New Estimates in EUR Under R/A Rows below |  |  | Preparation of Plan Logistics and Budget | Int. /a | WB "No Objection" | Int. /a | Start | Exec. /b | Compl. | Pysical Progress % | Payment to vendor %
Procurement Steps (1-19)
[5 empty] | USD | EUR |  | 1 |  | 2 |  | 3 |  | 4
1 |  | COMPONENT 1. STRENGTHENING ORGANIZATION & FINANCING OF EDUCATION SYSTEM
2
3 |  | TRAINING
4 | P | W/C1.1/10-01 | 1.1 | Workshops on new legislation | 0 |  | PRIOR | 2008-01-01 | 14 | 2008-01-15 | 14 | 2008-01-29 | 30 | 2008-02-28 |  |  |  | STU
5 | R/A |  |  |  |  | 13043.2 | [6 empty] | 3 |  | 100 | 100 | implemented
* 6 | P | WC1.1/11-02 | 1.1 | In support of new legistlation at municipal. |  | 2500 | PRIOR | 2012-07-01 | 14 | 2012-07-15 | 14 | 2012-07-29 | 2 | 2012-07-31
7 | R/A
8 | P | T/C1.2/10-01 | 1.2 | Study visit on education finance (UK) | 30500 |  | PRIOR | 2008-11-01 | 14 | 2008-11-15 | 14 | 2008-11-29 | 30 | 2008-12-29 |  |  |  | STU
9 | R/A |  |  |  |  | 16576 | [5 empty] | 2008-11-14 | 4 | 2008-11-22 | 100 | 100 | implemented
10 | P | W/C1.2/09-04 | 1.2 | Workshop For The 3 Pilot Municipalties |  |  | PRIOR | 2009-08-20 | 14 | 2009-09-03 | 14 | 2009-09-17 | 2 | 2009-11-19
11 | R/A |  |  |  |  | 1750 |  | 2009-08-20 |  | 2009-08-25 |  | 2009-08-29 | 2 | 2009-08-30 | 100 | 100 | implemented
12 | P | T/C1.2/10-02 | 1.2 | Training - implementation of financing formula, Albania | 0 | 30000 | PRIOR | 2010-10-04 | 14 | 2010-10-18 | 14 | 2010-11-01 | 120 | 2011-03-01 |  |  |  | STU
13 | R/A |  |  |  |  | 6348.81 |  | 2010-06-25 |  | 2010-06-29 |  | 2010-07-08 |  | 2010-07-11 | 100 | 100 | implemented
14 | P | W/C1.2/09-03 | 1.2 | 10 Workshop's for financing formula |  |  | PRIOR | 2009-10-29 | 14 | 2009-11-12 | 14 | 2009-11-26 | 90 | 2010-02-24
15 | R/A |  |  |  |  | 14700 |  | 2009-10-29 |  | 2009-11-01 |  | 2009-11-03 |  | 2010-02-05 | 100 | 100 | implemented
16 | P | W/C1.2/11-01 | 1.2 | Workshop Education budget planning in municipalities |  | 5000 | PRIOR | 2011-10-20 | 14 | 2011-11-03 | 14 | 2011-11-17 | 4 | 2011-11-21
17 | R/A |  |  |  |  | 310 |  | 2011-10-20 |  | 2011-10-24 |  | 2011-10-24 |  | 2011-10-24 | 100 | 100 | implemented
18 | P | W/C1.2/11-02 | 1.2 | Additional Training Aids for Finance |  | 1000 | PRIOR | 2011-11-11 | 14 | 2011-11-25 | 14 | 2011-12-09 | 4 | 2011-12-13
19 | R/A |  |  |  |  | 310 |  | 2011-11-11 |  | 2011-11-15 |  | 2011-11-16 |  | 2011-11-16 | 100 | 100 | implemented
20 | P | W/C1.2/12-01 | 1.2 | Conference on Reforming the education Financing mechanisms |  | 10000 | PRIOR | 2012-01-09 | 14 | 2012-01-23 | 14 | 2012-02-06 | 4 | 2012-02-10
21 | R/A |  |  |  |  | 0 |  | 2012-05-03 |  | 2012-05-09
22 | P | W/C1.3/11-03 | 1.3 | Workshop, for SGAB |  | 486 | PRIOR | 2011-02-09 | 14 | 2011-02-23 | 14 | 2011-03-09 | 1 | 2011-03-10
23 | R/A |  |  |  |  | 352 |  | 2011-02-09 |  | 2011-02-09 |  | 2011-02-21 | 0 | 2011-02-21 | 100 | 100 | implemented
24 | P | W/C1.3/11-04 | 1.3 | Workshop for SDG, Grant agreement signing ceremony |  | 1320 | PRIOR | 2011-03-10 | 14 | 2011-03-24 | 14 | 2011-04-07 | 1 | 2011-04-08
25 | R/A |  |  |  |  | 445 |  | 2011-03-10 |  | 2011-03-14 |  | 2011-03-21 | 0 | 2011-03-21 | 100 | 100 | implemented
26
27 | P | Component 1. Subtotals |  |  | 30500 | 50306
28 | R/A |  |  |  | 0 | 53835.01
29
30 |  | COMPONENT 2. BUILDING INSTITUTIONS & MANAGEMENT CAPACITY IN PRIMARY & SECONDARY EDUCATION
31
32 |  | TRAINING
33 | P | T/C2.1/11-01 | 2.1 | Performance evaluation of teachers and licencing |  |  | PRIOR | 2008-01-01 | 14 | 2008-01-15 | 14 | 2008-01-29 | 30 | 2008-02-28
34 | R/A |  |  |  |  | 8464.7 | [8 empty] | 100 | 100 | implemented
35 | P | T/C2.1/11-02 | 2.1 | Study visit - Teacher Performance Assessment | 25396 | 20000 | PRIOR | 2011-07-01 | 14 | 2011-07-15 | 14 | 2011-07-29 | 1 | 2011-07-30 |  |  |  | WOR
36 | R/A |  |  |  |  | 26998 |  | 2011-08-23 |  | 2011-08-25 |  | 2011-09-26 |  | 2011-09-30 | 100 | 100 | implemented
37 | P | W/C2.1/11-03 | 2.1 | Workshops - Teacher Performance/lincencing | 0 | 3000 | PRIOR | 2011-10-03 | 14 | 2011-10-17 | 14 | 2011-10-31 | 1 | 2011-11-01 |  |  |  | WOR
38 | R/A |  |  |  |  | 682 |  | 2011-10-03 | 1 | 2011-10-03 |  | 2011-10-06 | 7 | 2011-10-13 | 100 | 100 | implemented
39 | p | W/C2.1/11-04 | 2.1 | Workshop - Teacher Licencing |  | 10000 | PRIOR | 2011-12-19 | 14 | 2012-01-02 | 14 | 2012-01-16 | 1 | 2012-01-17
40 | R/A |  |  |  |  | 1680 |  | 2011-12-06 |  | 2011-12-12 |  | 2011-12-13 |  | 2011-12-15 | 100 | 100
41 | R/A |  |  |  |  | 1320 |  | 2012-01-13
42 | P | W/C2.1/09-04 | 2.1 | Workshop - Teacher Licencing |  |  | PRIOR | 2009-01-01 | 14 | 2009-01-15 | 14 | 2009-01-29 | 30 | 2009-02-28
43 | R/A |  |  |  |  | 1727.8 | [8 empty] | 100 | 100 | implemented
44 | p | W/C2.3/10-01 | 2.3 | Assessment & examinations |  |  | PRIOR | 2008-01-01 | 14 | 2008-01-15 | 14 | 2008-01-29 | 2 | 2008-01-31
45 | RA |  |  |  |  | 9426.7 | [8 empty] | 100 | 100
46 | P | W/C2.3/11-03 | 2.3 | Training on assessment |  | 3000 | PRIOR | 2011-10-11 | 14 | 2011-10-25 | 14 | 2011-11-08 | 1 | 2011-11-09
47 | RA |  |  |  |  | 880 |  | 2011-10-11 |  | 2011-11-10 |  | 2011-10-13 |  | 2011-10-14 | 100 | 100
48 | RA |  |  | Workshop for Assemssement Unit |  | 1144 |  | 2012-01-13
49 | P | W/C2.3/11-04 | 2.3 | Workshop on the Test and Design |  | 2000 |  | 2011-11-11 | 14 | 2011-11-25 | 14 | 2011-12-09 | 7 | 2011-12-16
50 | R/A |  |  |  |  | 880 |  | 2011-11-11 |  | 2011-11-15 |  | 2011-11-24 |  | 2011-11-25 | 100 | 100 | implemented
51 | R/A |  |  | Test Item development |  | 900 |  | 2012-02-27 |  | 2012-03-06 |  | 2012-03-07 |  | 2012-03-08 | 100 | 100 | implemented
51 | P | W/C2.3/11-04 | 2.3 | Conference Vision for the Matura 2015 in Kosovo |  | 25100 | PRIOR | 2011-11-04 | 14 | 2011-11-18 | 14 | 2011-12-02 | 2 | 2011-12-04 |  |  | Not planned
52 | R |  |  |  |  | 25100 |  | 2011-11-04 |  | 2011-11-11 |  | 2011-11-21 |  | 2011-11-22 | 100 | 100 | implemented
53 | P | T/C2.3/11-01 | 2.3 | Study visit on assessment |  | 20000 | PRIOR | 2012-07-01 | 14 | 2012-07-15 | 40 | 2012-08-24 | 30 | 2012-09-23
54 | R/A
55 | P | T/C2.3/11-02 | 2.3 | Participat​ion in the ECA education Conference |  | 5630.8 | PRIOR | 2011-09-06 | 14 | 2011-09-20 | 14 | 2011-10-04 | 2 | 2011-10-06 |  |  | Not planned
56 | R | [6 empty] | 2011-09-06 |  | 2011-09-20 |  | 2011-10-23 |  | 2011-10-27 | 100 | 100
57 | P | T/2.3/11-03 | 2.3 | Study Visit on Teacher Professional Development(Slovenia) |  | 3691 | PRIOR | 2011-11-15 | 14 | 2011-11-29 | 14 | 2011-12-13 | 2 | 2011-12-15
58 | R/A | [6 empty] | 2011-11-15 |  | 2011-11-17 | [6 empty] | Not planned
59 | P | T/2.3/12-04 | 2.3 | Training for Matura test Administrators |  | 25700 | PRIOR | 2012-04-03 | 14 | 2012-04-17 | 14 | 2012-05-01 | 2 | 2012-05-03
60 | R/A |  |  |  |  | 25700 |  | 2012-04-03 |  | 2012-04-17
61 | P | W/2.3/12-05 | 2.3 | Confernce for AU teacher performance assessment |  | 15000 | PRIOR | 2012-07-01 | 14 | 2012-07-15 | 14 | 2012-07-29 | 2 | 2012-07-31
62 | R/A
63 | P | T/C2.4/10-01 | 2.4 | Study visits - EMIS staff (7 participants) | 29700 | 44496 | PRIOR | 2010-01-15 | 14 | 2010-01-29 | 14 | 2010-02-12 | 30 | 2010-03-14 |  |  |  | STU
64 | R/A |  |  |  |  | 7980 |  | 2010-07-20 |  | 2010-07-23 |  | 2010-08-10 |  | 2010-08-13 | 100 | 100 | implemented
65 | P | T/C2.5/10-06 | 2.5 | Project Confferences | 0 |  | PRIOR | 2008-01-01 | 14 | 2008-01-15 | 14 | 2008-01-29 | 30 | 2008-02-28 |  |  |  | STU
66 | R/A |  |  |  |  | 5426.5
67 | P | T/C2.5/09-01 | 2.5 | Procurement training in Skopje |  |  | PRIOR | 2009-03-30 | 14 | 2009-04-13 | 14 | 2009-04-27 | 3 | 2009-04-30
68 | R/A |  |  |  |  | 639 |  | 2009-03-30 |  | 2009-03-31 |  | 2009-04-07 | 3 | 2009-04-10 | 100 | 100 | Implemented
69 | P | T/C2.5/10-02 | 2.5 | Procurement training | 3500 |  | PRIOR | 2010-01-15 | 14 | 2010-01-29 | 14 | 2010-02-12 | 30 | 2010-03-14 |  |  |  | STU
70 | R/A |  |  |  |  | 1300 |  | 2010-04-19 |  | 2010-05-14 |  | 2010-05-31 |  | 2010-06-04 | 100 | 100 | Implemented
71 | P | T/C2.5/10-04 | 2.5 | Procurement training |  | 1307 | PRIOR | 2010-10-05 | 14 | 2010-10-19 | 14 | 2010-11-02 | 30 | 2010-12-02
72 | R/A |  |  |  |  | 1281 |  | 2010-10-06 |  | 2010-10-10 |  | 2010-10-18 |  | 2010-10-22 | 100 | 100 | Implemented
73 | P | T/C2.5/10-03 | 2.5 | Staff Professional Development | 11216.86 | 9000 | PRIOR | 2012-01-09 | 14 | 2012-01-23 | 14 | 2012-02-06 | 1 | 2012-02-07 |  |  |  | STU
74 | R/A |  |  | Disbursment & FM training, Tirana 12.13.03.2012 |  | 907 |  | 2012-02-21 |  | 2012-03-06 |  | 2012-03-12 |  | 2012-03-13 | 100 | 100 | implemented
75 | P | T/C2.5/10-05 | 2.5 | Financal management training |  | 1164 | PRIOR | 2010-12-22 | 14 | 2011-01-05 | 14 | 2011-01-19 | 5 | 2011-01-24
76 | R/A |  |  |  |  | 956 |  | 2010-12-22 |  | 2011-01-10 |  | 2010-01-19 |  | 2010-01-21 | 100 | 100 | implemented
77
78 | P | Component 2. Subtotals |  |  | 69812.86 | 189088.8
79 | R/A |  |  |  | 0 | 97692.7
80
81 |  | COMPONENT 3. CREATING CONDITIONS TO INTRODUCE EFFICIENT DESIGNS IN KOSOVO'S SCHOOLS
82
83 |  | TRAINING
84 | P | T/C3.1/10-01 | 3.1 | School Mapping | 0 |  | PRIOR | 2008-01-01 | 14 | 2008-01-15 | 14 | 2008-01-29 | 30 | 2008-02-28 |  |  |  | STU
85 | R/A |  |  |  |  | 22564 |  |  |  | 2009-09-07 |  |  |  |  | 100 | 100 | implemented
86 | P | T/C3.1/10-02 | 3.1 | Safeguards training | 0 |  | PRIOR | 2008-01-01 | 14 | 2008-01-15 | 14 | 2008-01-29 | 30 | 2008-02-28 |  |  |  | STU
87 | R/A |  |  |  |  | 3034.9 | [8 empty] | 100 | 100 | implemented
88 | P | T/C3.1/10-03 | 3.1 | School mapping, investement planning and inventory taking | 0 |  | PRIOR | 2008-01-01 | 14 | 2008-01-15 | 14 | 2008-01-29 | 30 | 2008-02-28 |  |  |  | STU
89 | R/A |  |  |  |  | 1590 | [8 empty] | 100 | 100 | implemented
90 | P | T/C3.1/10-04 | 3.2 | Standards and Norms on School Design | 0 |  | PRIOR | 2008-01-01 | 14 | 2008-01-15 | 14 | 2008-01-29 | 30 | 2008-02-28 |  |  |  | STU
91 | R/A |  |  |  |  | 2475 | [8 empty] | 100 | 100 | implemented
92 | P | T/C3.2/10-01 | 3.2 | Overseas study visit on school design | 0 | 15000 | PRIOR | 2010-09-20 | 14 | 2010-10-04 | 14 | 2010-10-18 | 30 | 2010-11-17 |  |  |  | STU
93 | R/A |  |  |  |  | 12214 |  | 2010-09-20 |  | 2010-09-24 |  | 2010-10-11 | 6 | 2010-10-17 | 100 | 100 | Implemented
94 | P | W/3.2/12-02 | 3.2 | Public presentation of School Design manual in municipaities | 0 | 500 | PRIOR | 2012-07-01 | 14 | 2012-07-15 | 14 | 2012-07-29 | 30 | 2012-08-28 |  |  |  | STU
95 | R/A |  |  |  |  | 0
96 | P | W/3.2/12-03 | 3.2 | Conference on School Buildings and Standards | 0 | 10000 | PRIOR | 2012-07-01 | 14 | 2012-07-15 | 14 | 2012-07-29 | 30 | 2012-08-28 |  |  |  | STU
97 | R/A |  |  |  |  | 0
98 | P | W/3.3/12-01 | 3.3 | Study visit for ID |  | 5000 | PRIOR | 2012-06-18 | 14 | 2012-07-02 | 14 | 2012-07-16 | 2 | 2012-07-18
99 | R/A |  |  |  |  | 2976.65 |  | 2012-06-18
100 | P | Component 3. Subtotals |  |  | 0 | 30500
101 | R/A |  |  |  | 0 | 44854.55
102
103 |  | COMPONENT 4. FINANCING MECHANISMS FOR HIGHER EDUCATION
104
105 |  | TRAINING
106 | P | T/C4.1/10-01 | 4.1 | Workshop on Higher Education Legislation | 0 | 1684 | PRIOR | 2010-07-19 | 14 | 2010-08-02 | 14 | 2010-08-16 | 30 | 2010-09-15 |  |  |  | STU
107 | R/A |  |  |  |  | 1684.7 | [5 empty] | 2010-07-28 |  | 2010-07-28 | 100 | 100 | Implemented
108 | P | T/C4.1/10-01 | 4.1 | Workshop on Higher Education Legislation | 0 | 5000 | PRIOR | 2012-03-01 | 14 | 2012-03-15 | 14 | 2012-03-29 | 1 | 2012-03-30 |  |  |  | STU
109 | R/A |  |  |  |  | 0
110 | P | W/C4.2/10-02 | 4.2 | Workshop on Higer Education |  |  | PRIOR | 2010-06-05 | 14 | 2010-06-19 | 14 | 2010-07-03 | 1 | 2010-07-04
111 | R/A |  |  |  |  | 1369 |  | 2010-06-05 |  | 2010-06-10 |  | 2010-08-03 | 1 | 2010-08-03 | 100 | 100 | Implemented
112 | P | T/C4.2/11-01 | 4.2 | Workshop on Financing of Higher Education | 0 | 2000 | PRIOR | 2012-03-01 | 14 | 2012-03-15 | 14 | 2012-03-29 | 1 | 2012-03-30 |  |  |  | STU
113 | R/A |  |  |  | 0
114 | P | Component 4. Subtotals |  |  | 0 | 8684
115 | R/A |  |  |  | 0 | 3053.7
|  |  |  | Database Subtotals Tool | 200625.72 | 981729.52
* on going activities
Formulas:
WB "No Objection" = [Preparation of Plan Logistics and Budget]+[Int. /a]
Start = [WB "No Objection"]+[Int. /a]
Compl. = [Start]+[Exec. /b]

## Grants
Ln. # | Status P R/A d/ | Contract Reference # Standard Prefix "KOS-IDEP/H3420/" removed from below listings | Comp. | Description | Estim. No. of Lots | 2012-10-16 14:49 |  | Proc. Method | WB Review | Schedule (dd-Mmm-yy) | [20 empty] | Comments | Procure- ment Accounts
[6 empty] | Appraisal Estimates P (planned) Enter New Estimates in EUR Under R/A Rows below |  |  |  | Prep. of Doc. | Int. /a | WB "No Objection" | Int. /a | Advert- izing | Int. /a | Issue of Documents | Int. /a | Sub- mission of Bids | Int. /a | Evalu- ation & Recomm. | Int. /a | WB "No Objection" | Int. /a | Contract Award | Int. /a | Contract Signature | Int. /a | Start | Exec. /b | Comple- tion
Procurement Steps (1-11)
[6 empty] | USD | EUR |  |  | 1 |  | 2 |  | 3 |  | 4 |  | 5 |  | 6 |  | 7 |  | 8 |  | 9 |  | 10 |  | 11
1 |  | COMPONENT 1. STRENGTHENING ORGANIZATION & FINANCING OF EDUCATION SYSTEM CAPACITY IN PRIMARY & SECONDARY EDUCATION
2
3 |  | GRANTS
4 |  | Municipal Grants (15)
5 | P | C1.2/MG#1 | 1.2 | 1. Kacanik | 1 | 35000 | 16200 | MNL | Post | 2009-10-05 | 14 | 2009-10-19 |  | NA | 3 | 2009-10-22 | 14 | 2009-11-05 | 7 | 2009-11-12 | 14 | 2009-11-26 | 2 | 2009-11-28 | 7 | 2009-12-05 | 7 | 2009-12-12 | 30 | 2010-01-11 |  | MDG
6 | R/A |  |  |  |  | 0 | 16197
7 | P | C1.2/MG#2 | 1.2 | 2. Gjilan | 1 | 35000 | 21200 | MNL | Post | 2009-10-05 | 14 | 2009-10-19 |  | NA | 3 | 2009-10-22 | 14 | 2009-11-05 | 7 | 2009-11-12 | 14 | 2009-11-26 | 2 | 2009-11-28 | 7 | 2009-12-05 | 7 | 2009-12-12 | 30 | 2010-01-11 |  | MDG
8 | R/A |  |  |  |  | 0 | 17353.5
9 | P | C1.2/MG#3 | 1.2 | 3. Istog | 1 | 35000 | 10890 | MNL | Post | 2009-10-05 | 14 | 2009-10-19 |  | NA | 3 | 2009-10-22 | 14 | 2009-11-05 | 7 | 2009-11-12 | 14 | 2009-11-26 | 2 | 2009-11-28 | 7 | 2009-12-05 | 7 | 2009-12-12 | 30 | 2010-01-11 |  | MDG
10 | R/A |  |  |  |  | 0 | 0
2 | P | C1.2/MG#4 | 1.2 | 4. Other | 1 | 0 |  | MNL | Post | 2010-01-15 | 14 | 2010-01-29 |  | NA | 3 | 2010-02-01 | 14 | 2010-02-15 | 7 | 2010-02-22 | 14 | 2010-03-08 | 2 | 2010-03-10 | 7 | 2010-03-17 | 7 | 2010-03-24 | 30 | 2010-04-23 |  | MDG
3 | R/A |  |  |  |  | 0 | 0
4 | P | C1.2/MG#5 | 1.2 | 5. etc | 1 | 0 |  | MNL | Post | 2010-01-15 | 14 | 2010-01-29 |  | NA | 3 | 2010-02-01 | 14 | 2010-02-15 | 7 | 2010-02-22 | 14 | 2010-03-08 | 2 | 2010-03-10 | 7 | 2010-03-17 | 7 | 2010-03-24 | 30 | 2010-04-23 |  | MDG
5 | R/A |  |  |  |  | 0 | 0
6 | P | C1.2/MG#6 | 1.2 | 6. | 1 | 0 |  | MNL | Post | 2010-01-15 | 14 | 2010-01-29 |  | NA | 3 | 2010-02-01 | 14 | 2010-02-15 | 7 | 2010-02-22 | 14 | 2010-03-08 | 2 | 2010-03-10 | 7 | 2010-03-17 | 7 | 2010-03-24 | 30 | 2010-04-23 |  | MDG
7 | R/A |  |  |  |  | 0 | 0
8 | P | C1.2/MG#7 | 1.2 | 7. | 1 | 0 |  | MNL | Post | 2010-01-15 | 14 | 2010-01-29 |  | NA | 3 | 2010-02-01 | 14 | 2010-02-15 | 7 | 2010-02-22 | 14 | 2010-03-08 | 2 | 2010-03-10 | 7 | 2010-03-17 | 7 | 2010-03-24 | 30 | 2010-04-23 |  | MDG
9 | R/A |  |  |  |  | 0 | 0
10 | P | C1.2/MG#8 | 1.2 | 8. | 1 | 0 |  | MNL | Post | 2010-01-15 | 14 | 2010-01-29 |  | NA | 3 | 2010-02-01 | 14 | 2010-02-15 | 7 | 2010-02-22 | 14 | 2010-03-08 | 2 | 2010-03-10 | 7 | 2010-03-17 | 7 | 2010-03-24 | 30 | 2010-04-23 |  | MDG
11 | R/A |  |  |  |  | 0 | 0
3 | P | C1.2/MG#9 | 1.2 | 9. | 1 | 0 |  | MNL | Post | 2010-01-15 | 14 | 2010-01-29 |  | NA | 3 | 2010-02-01 | 14 | 2010-02-15 | 7 | 2010-02-22 | 14 | 2010-03-08 | 2 | 2010-03-10 | 7 | 2010-03-17 | 7 | 2010-03-24 | 30 | 2010-04-23 |  | MDG
4 | R/A |  |  |  |  | 0 | 0
5 | P | C1.2/MG#10 | 1.2 | 10. | 1 | 0 |  | MNL | Post | 2010-01-15 | 14 | 2010-01-29 |  | NA | 3 | 2010-02-01 | 14 | 2010-02-15 | 7 | 2010-02-22 | 14 | 2010-03-08 | 2 | 2010-03-10 | 7 | 2010-03-17 | 7 | 2010-03-24 | 30 | 2010-04-23 |  | MDG
6 | R/A |  |  |  |  | 0 | 0
7 | P | C1.2/MG#11 | 1.2 | 11, | 1 | 0 |  | MNL | Post | 2010-01-15 | 14 | 2010-01-29 |  | NA | 3 | 2010-02-01 | 14 | 2010-02-15 | 7 | 2010-02-22 | 14 | 2010-03-08 | 2 | 2010-03-10 | 7 | 2010-03-17 | 7 | 2010-03-24 | 30 | 2010-04-23 |  | MDG
8 | R/A |  |  |  |  | 0 | 0
9 | P | C1.2/MG#12 | 1.2 | 12. | 1 | 0 |  | MNL | Post | 2010-01-15 | 14 | 2010-01-29 |  | NA | 3 | 2010-02-01 | 14 | 2010-02-15 | 7 | 2010-02-22 | 14 | 2010-03-08 | 2 | 2010-03-10 | 7 | 2010-03-17 | 7 | 2010-03-24 | 30 | 2010-04-23 |  | MDG
10 | R/A |  |  |  |  | 0 | 0
11 | P | C1.2/MG#13 | 1.2 | 13. | 1 | 0 |  | MNL | Post | 2010-01-15 | 14 | 2010-01-29 |  | NA | 3 | 2010-02-01 | 14 | 2010-02-15 | 7 | 2010-02-22 | 14 | 2010-03-08 | 2 | 2010-03-10 | 7 | 2010-03-17 | 7 | 2010-03-24 | 30 | 2010-04-23 |  | MDG
12 | R/A |  |  |  |  | 72206.3018 | 56346
4 | P | C1.2/MG#14 | 1.2 | 14. | 1 | 0 |  | MNL | Post | 2010-01-15 | 14 | 2010-01-29 |  | NA | 3 | 2010-02-01 | 14 | 2010-02-15 | 7 | 2010-02-22 | 14 | 2010-03-08 | 2 | 2010-03-10 | 7 | 2010-03-17 | 7 | 2010-03-24 | 30 | 2010-04-23 |  | MDG
5 | R/A |  |  |  |  | 4639.3389 | 3191.76
6 | P | C1.2/MG#15 | 1.2 | 15. | 1 | 0 |  | MNL | Post | 2010-01-15 | 14 | 2010-01-29 |  | NA | 3 | 2010-02-01 | 14 | 2010-02-15 | 7 | 2010-02-22 | 14 | 2010-03-08 | 2 | 2010-03-10 | 7 | 2010-03-17 | 7 | 2010-03-24 | 30 | 2010-04-23 |  | MDG
7 | R/A |  |  |  |  | 0 | 0
11 | P | Subtotal Municipal Grants |  |  | 15 | 105000 | 48290
12 | R/A |  |  |  | 0 | 0 | 33550.5
13 |  | First round, Primary School Grants
14 | P | C1.3/SDG/01 | 1.3 | Gjon Serreçi | 1 |  | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
15 | R/A |  |  |  |  | 0 | 10000 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
16 | P | C1.3/SDG/02 | 1.3 | Ahmet Hoxha | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
17 | R/A |  |  |  |  | 0 | 10000 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
18 | P | C1.3/SDG/03 | 1.3 | Naim Frasheri | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
19 | R/A |  |  |  |  | 0 | 9605 |  |  | 2011-05-01 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
20 | P | C1.3/SDG/04 | 1.3 | Dituria - Ferizaj | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
21 | R/A |  |  |  |  | 0 | 6180 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
22 | P | C1.3/SDG/05 | 1.3 | Ali Hadri | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
23 | R/A |  |  |  |  | 0 | 6140 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
24 | P | C1.3/SDG/06 | 1.3 | Ismail Luma | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
25 | R/A |  |  |  |  | 0 | 8725 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
26 | P | C1.3/SDG/07 | 1.3 | Zenel Hajdini | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
27 | R/A |  |  |  |  | 0 | 10000 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
28 | P | C1.3/SDG/08 | 1.3 | Haradin Bajrami (Jeronim de Rada) | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
29 | R/A |  |  |  |  | 0 | 10000 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
30 | P | C1.3/SDG/09 | 1.3 | Bajram Curri | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
31 | R/A |  |  |  |  | 0 | 10000 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
32 | P | C1.3/SDG/10 | 1.3 | F.Guri dhe V.Qaka | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
33 | R/A |  |  |  |  | 0 | 13661 |  |  | 2011-05-01 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
32 | P | C1.3/SDG/11 | 1.3 | Dituria - Kaqanik | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
33 | R/A |  |  |  |  | 0 | 5825 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
34 | P | C1.3/SDG/14 | 1.3 | Sh. F. Kabashi | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
35 | R/A |  |  |  |  | 0 | 5100 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
36 | P | C1.3/SDG/15 | 1.3 | Ardhmeria | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
37 | R/A |  |  |  |  | 0 | 5335 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
38 | P | C1.3/SDG/16 | 1.3 | Zenun Cocaj | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
39 | R/A |  |  |  |  | 0 | 8040 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
40 | P | C1.3/SDG/17 | 1.3 | Izvor | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
41 | R/A |  |  |  |  | 0 | 5435 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
42 | P | C1.3/SDG/18 | 1.3 | Zef Lush Marku | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
43 | R/A |  |  |  |  | 0 | 8130 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
44 | P | C1.3/SDG/19 | 1.3 | Nazmi Buduri | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
45 | R/A |  |  |  |  | 0 | 8040 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
46 | P | C1.3/SDG/22 | 1.3 | Drita | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
47 | R/A |  |  |  |  | 0 | 5210 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
48 | P | C1.3/SDG/23 | 1.3 | K. I Manastirit | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
49 | R/A |  |  |  |  | 0 | 8940 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
50 | P | C1.3/SDG/24 | 1.3 | Ilmi Bahtijari | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
51 | R/A |  |  |  |  | 0 | 9395 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
52 | P | C1.3/SDG/25 | 1.3 | Fetah Sylejmani | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
53 | R/A |  |  |  |  | 0 | 8075 |  |  | 2011-05-01 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
54 | P | C1.3/SDG/26 | 1.3 | Haxhi Ymer Lutfiu | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
55 | R/A |  |  |  |  | 0 | 4436.91 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
56 | P | C1.3/SDG/27 | 1.3 | Vellazerimi | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
57 | R/A |  |  |  |  | 0 | 7815 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
58 | P | C1.3/SDG/28 | 1.3 | Zef Lush Marku - Bregoc | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
59 | R/A |  |  |  |  | 0 | 9615 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
60 | P | C1.3/SDG/29 | 1.3 | Nimon Ferizi | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
61 | R/A |  |  |  |  | 0 | 5385 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
62 | P | C1.3/SDG/30 | 1.3 | Fehmi Agani | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
63 | R/A |  |  |  |  | 0 | 8075 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
64 | P | C1.3/SDG/31 | 1.3 | Ganimer Terbeshi | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
65 | R/A |  |  |  |  | 0 | 6085 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
66 | P | C1.3/SDG/32 | 1.3 | 7 Shtatori | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
67 | R/A |  |  |  |  | 0 | 5225 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
68 | P | C1.3/SDG/33 | 1.3 | Fan Noli | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
69 | R/A |  |  |  |  | 0 | 5510 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
70 | P | C1.3/SDG/34 | 1.3 | Rilindja | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
71 | R/A |  |  |  |  | 0 | 4435 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
72 | P | C1.3/SDG/35 | 1.3 | Mustafe Ibishi | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
73 | R/A |  |  |  |  | 0 | 8185 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
74 | P | C1.3/SDG/36 | 1.3 | Jusf Gervalla | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
75 | R/A |  |  |  |  | 0 | 6695 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
76 | P | C1.3/SDG/38 | 1.3 | 7 Shtatori - Rahovec | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
77 | R/A |  |  |  |  | 0 | 5755 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
78 | P | C1.3/SDG/40 | 1.3 | Rifat Berisha | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
79 | R/A |  |  |  |  | 0 | 6290 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
80 | P | C1.3/SDG/41 | 1.3 | Vesel Pagarusha | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
81 | R/A |  |  |  |  | 0 | 6285 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
82 | P | C1.3/SDG/42 | 1.3 | Ismet Jashari Kumanova | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
83 | R/A |  |  |  |  | 0 | 5265 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
84 | P | C1.3/SDG/43 | 1.3 | Tafil Kelmendi | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
85 | R/A |  |  |  |  | 0 | 5685 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
86 | P | C1.3/SDG/44 | 1.3 | Bajram Curri - Drenoc | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
87 | R/A |  |  |  |  | 0 | 6450 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
88 | P | C1.3/SDG/46 | 1.3 | Xhemajl Kada | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
89 | R/A |  |  |  |  | 0 | 8425 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
90 | P | C1.3/SDG/47 | 1.3 | 7 Shtatori - Vitomirice | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
91 | R/A |  |  |  |  | 0 | 9340 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
92 | P | C1.3/SDG/48 | 1.3 | Deshmoret e Kombit | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
93 | R/A |  |  |  |  | 0 | 8945 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
94 | P | C1.3/SDG/49 | 1.3 | Skenderbeu | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
95 | R/A |  |  |  |  | 0 | 6900 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
96 | P | C1.3/SDG/50 | 1.3 | Ndre Mjeda | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
97 | R/A |  |  |  |  | 0 | 8560 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
98 | P | C1.3/SDG/51 | 1.3 | Avni Rrustemi | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
99 | R/A |  |  |  |  | 0 | 7450 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
100 | P | C1.3/SDG/52 | 1.3 | Fan Noli - Lluk I Bregut | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
101 | R/A |  |  |  |  | 0 | 6975 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
102 | P | C1.3/SDG/53 | 1.3 | Emin Duraku | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
103 | R/A |  |  |  |  | 0 | 9000 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
104 | P | C1.3/SDG/54 | 1.3 | Ali Krasniqi | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
105 | R/A |  |  |  |  | 0 | 8425 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
106 | P | C1.3/SDG/55 | 1.3 | Azem Bejta | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
107 | R/A |  |  |  |  | 0 | 6730 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
108 | P | C1.3/SDG/56 | 1.3 | Tre Deshmoret | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
109 | R/A |  |  |  |  | 0 | 8945 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
110 | P | C1.3/SDG/57 | 1.3 | Ate Gjergj Fishta | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
111 | R/A |  |  |  |  | 0 | 4675 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
112 | P | C1.3/SDG/58 | 1.3 | Drita - Gramqel | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
113 | R/A |  |  |  |  | 0 | 7365 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
114 | P | C1.3/SDG/59 | 1.3 | Heronjt e Dukagjinit | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
115 | R/A |  |  |  |  | 0 | 5265 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
116 | P | C1.3/SDG/60 | 1.3 | Faik Konica | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
117 | R/A |  |  |  |  | 0 | 4715 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
118 | P | C1.3/SDG/61 | 1.3 | Esat Mekuli | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
119 | R/A |  |  |  |  | 0 | 4510 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
120 | P | C1.3/SDG/62 | 1.3 | Rexhep Kadrijaj | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
121 | R/A |  |  |  |  | 0 | 5500 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
122 | P | C1.3/SDG/64 | 1.3 | Avni Rrustemi - Mramuer | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
123 | R/A |  |  |  |  | 0 | 7155 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
124 | P | C1.3/SDG/65 | 1.3 | Nexhmi Mustafa | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
125 | R/A |  |  |  |  | 0 | 7180 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
126 | P | C1.3/SDG/66 | 1.3 | Tefik Canga | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
127 | R/A |  |  |  |  | 0 | 6565 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
128 | P | C1.3/SDG/67 | 1.3 | Pjeter Bogdani | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
129 | R/A |  |  |  |  | 0 | 10000 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
130 | P | C1.3/SDG/68 | 1.3 | Sami Frasheri | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
131 | R/A |  |  |  |  | 0 | 7710 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
132 | P | C1.3/SDG/70 | 1.3 | Jahe Hasani | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
133 | R/A |  |  |  |  | 0 | 5370 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
134 | P | C1.3/SDG/71 | 1.3 | Luigj Gurakuqi | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
135 | R/A |  |  |  |  | 0 | 9680 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
136 | P | C1.3/SDG/72 | 1.3 | Drita - Majac | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
137 | R/A |  |  |  |  | 0 | 9790 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
138 | P | C1.3/SDG/73 | 1.3 | Laura Scotti | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
139 | R/A |  |  |  |  | 0 | 4805 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
140 | P | C1.3/SDG/74 | 1.3 | Lismir | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
141 | R/A |  |  |  |  | 0 | 4755 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
142 | P | C1.3/SDG/75 | 1.3 | Naim Frasheri - Bresnice | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
143 | R/A |  |  |  |  | 0 | 7180 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
144 | P | C1.3/SDG/76 | 1.3 | Migjeni | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
145 | R/A |  |  |  |  | 0 | 7450 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
146 | P | C1.3/SDG/77 | 1.3 | Knez Llazar | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
147 | R/A |  |  |  |  | 0 | 10000 |  |  | 2011-05-01 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
148 | P | C1.3/SDG/78 | 1.3 | Aferdita | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
149 | R/A |  |  |  |  | 0 | 7030 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
150 | P | C1.3/SDG/79 | 1.3 | Bajram Curri - Shurdhan | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
151 | R/A |  |  |  |  | 0 | 4630 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
152 | P | C1.3/SDG/80 | 1.3 | Fetah Qerimi | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
153 | R/A |  |  |  |  | 0 | 5690 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
154 | P | C1.3/SDG/81 | 1.3 | Liria | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
155 | R/A |  |  |  |  | 0 | 5435 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
156 | P | C1.3/SDG/82 | 1.3 | Kadri Zeka | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
157 | R/A |  |  |  |  | 0 | 6480 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
158 | P | C1.3/SDG/83 | 1.3 | Sadri Misini | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
159 | R/A |  |  |  |  | 0 | 6885 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
160 | P | C1.3/SDG/84 | 1.3 | Asdreni | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
161 | R/A |  |  |  |  | 0 | 6095 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
162 | P | C1.3/SDG/86 | 1.3 | Hysen Terpeza | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
163 | R/A |  |  |  |  | 0 | 6010 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
164 | P | C1.3/SDG/87 | 1.3 | Vellezerit Gervalla | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
165 | R/A |  |  |  |  | 0 | 8470 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
166 | P | C1.3/SDG/88 | 1.3 | Deshmoret e 5 Prillit | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
167 | R/A |  |  |  |  | 0 | 7095 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
168 | P | C1.3/SDG/90 | 1.3 | Gjon Serreci - Mogille | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
169 | R/A |  |  |  |  | 0 | 5980 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
170 | P | C1.3/SDG/91 | 1.3 | Deshmoret e Qendreses | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
171 | R/A |  |  |  |  | 0 | 5485 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
172 | P | C1.3/SDG/92 | 1.3 | Desjmoret e Drenices | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
173 | R/A |  |  |  |  | 0 | 5140 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
174 | P | C1.3/SDG/93 | 1.3 | Xheve Lladrovci | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
175 | R/A |  |  |  |  | 0 | 5435 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
176 | P | C1.3/SDG/94 | 1.3 | Shote Galica | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
177 | R/A |  |  |  |  | 0 | 6480 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
178 | P | C1.3/SDG/96 | 1.3 | Abedin Rexha | 1 | 0 | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
179 | R/A |  |  |  |  | 0 | 6180 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
180 | P | C1.3/SDG/98 | 1.3 | Habib Jusufi | 1 |  | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
181 | R/A | [5 empty] | 5345 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
182 | P | C1.3/SDG/99 | 1.3 | Jusuf Rexha | 1 |  | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
183 | R/A | [5 empty] | 6115 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
184 | P | C1.3/SDG/100 | 1.3 | Sefedin Smakolli | 1 |  | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
185 | R/A | [5 empty] | 5625 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
186 | P | C1.3/SDG/101 | 1.3 | Trepca | 1 |  | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
187 | R/A | [5 empty] | 7620 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
188 | P | C1.3/SDG/102 | 1.3 | Bedri Gjinaj | 1 |  | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
189 | R/A | [5 empty] | 7165 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
190 | P | C1.3/SDG/104 | 1.3 | Azem Bejta - Dubovc | 1 |  | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
191 | R/A | [5 empty] | 6090 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
192 | P | C1.3/SDG/105 | 1.3 | Bajram Curri - Dumnice | 1 |  | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
193 | R/A | [5 empty] | 6255 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
194 | P | C1.3/SDG/106 | 1.3 | Gj.K. Skenderbeu | 1 |  | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
195 | R/A | [5 empty] | 7350 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
196 | P | C1.3/SDG/107 | 1.3 | Adem Voca | 1 |  | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
197 | R/A | [5 empty] | 5075 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
198 | P | C1.3/SDG/108 | 1.3 | Emin Duraku - Novolane | 1 |  | 10000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGP
199 | R/A | [5 empty] | 6555 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
SECOND ROUND PRIMARY SCHOOL
200 | P | C1.3/SDG/111 | 1.3 | Dardania | 1 |  | 10000 | MNL | Post | 2012-01-16 | 14 | 2012-01-30 |  | NA | 3 | 2012-02-02 | 14 | 2012-02-16 | 7 | 2012-02-23 | 14 | 2012-03-08 | 2 | 2012-03-10 | 7 | 2012-03-17 | 7 | 2012-03-24 | 30 | 2012-04-23 |  | SDGP
201 | R/A | [5 empty] | 5005 |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
202 | P | C1.3/SDG/112 | 1.3 | K. Kristoforidhi | 1 |  | 10000 | MNL | Post | 2012-01-16 | 14 | 2012-01-30 |  | NA | 3 | 2012-02-02 | 14 | 2012-02-16 | 7 | 2012-02-23 | 14 | 2012-03-08 | 2 | 2012-03-10 | 7 | 2012-03-17 | 7 | 2012-03-24 | 30 | 2012-04-23 |  | SDGP
203 | R/A | [5 empty] | 6585 |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
204 | P | C1.3/SDG/113 | 1.3 | Fehmi Agani | 1 |  | 10000 | MNL | Post | 2012-01-16 | 14 | 2012-01-30 |  | NA | 3 | 2012-02-02 | 14 | 2012-02-16 | 7 | 2012-02-23 | 14 | 2012-03-08 | 2 | 2012-03-10 | 7 | 2012-03-17 | 7 | 2012-03-24 | 30 | 2012-04-23 |  | SDGP
205 | R/A | [5 empty] | 6180 |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
206 | P | C1.3/SDG/114 | 1.3 | Shtjefen Gjeqovi | 1 |  | 10000 | MNL | Post | 2012-01-16 | 14 | 2012-01-30 |  | NA | 3 | 2012-02-02 | 14 | 2012-02-16 | 7 | 2012-02-23 | 14 | 2012-03-08 | 2 | 2012-03-10 | 7 | 2012-03-17 | 7 | 2012-03-24 | 30 | 2012-04-23 |  | SDGP
207 | R/A | [5 empty] | 8125 |  |  |  |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
208 | P | C1.3/SDG/115 | 1.3 | Abdullah Shabani | 1 |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
209 | R/A | [5 empty] | 8565
210 | P | C1.3/SDG/116 | 1.3 | G. Luma |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
211 | R/A | [5 empty] | 5110
212 | P | C1.3/SDG/117 | 1.3 | Sharski Odredi |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
213 | R/A | [5 empty] | 8510
214 | P | C1.3/SDG/118 | 1.3 | Sezai Surroi |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
215 | R/A | [5 empty] | 7495
216 | P | C1.3/SDG/119 | 1.3 | Mic Sokoli |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
217 | R/A | [5 empty] | 6165
218 | P | C1.3/SDG/120 | 1.3 | Haziz Tolaj |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
219 | R/A | [5 empty] | 7275
220 | P | C1.3/SDG/121 | 1.3 | Luigj Gurakuqi |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
221 | R/A | [5 empty] | 8030
222 | P | C1.3/SDG/123 | 1.3 | Sadri Duhla |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
223 | R/A | [5 empty] | 10000
224 | P | C1.3/SDG/124 | 1.3 | Deshmoret e Tivarit |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
225 | R/A | [5 empty] | 8000
226 | P | C1.3/SDG/125 | 1.3 | Sahban Spahiu |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
227 | R/A | [5 empty] | 9444.89
228 | P | C1.3/SDG/126 | 1.3 | Ferhat Binishi |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
229 | R/A | [5 empty] | 6260
230 | P | C1.3/SDG/127 | 1.3 | Ukshin Miftari |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
231 | R/A | [5 empty] | 6050
232 | P | C1.3/SDG/128 | 1.3 | Qemajl Bakia |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
233 | R/A | [5 empty] | 5850
234 | P | C1.3/SDG/130 | 1.3 | Pataqan I ulet |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
235 | R/A | [5 empty] | 5510
236 | P | C1.3/SDG/131 | 1.3 | 4 Deshmoret |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
237 | R/A | [5 empty] | 7835
238 | P | C1.3/SDG/132 | 1.3 | Afrim Buqaj |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
239 | R/A | [5 empty] | 5710
240 | P | C1.3/SDG/133 | 1.3 | Deshmoret e fshatit Bubavec |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
241 | R/A | [5 empty] | 6000
242 | P | C1.3/SDG/134 | 1.3 | Gjergj Kastrioti |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
243 | R/A | [5 empty] | 7850
244 | P | C1.3/SDG/136 | 1.3 | Ramiz Sadiku |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
245 | R/A | [5 empty] | 7505
246 | P | C1.3/SDG/137 | 1.3 | Jusuf Gervalla |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
247 | R/A | [5 empty] | 7095
248 | P | C1.3/SDG/138 | 1.3 | Nena Tereze |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
249 | R/A | [5 empty] | 8025
250 | P | C1.3/SDG/139 | 1.3 | Shkendija |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
251 | R/A | [5 empty] | 10000
252 | P | C1.3/SDG/140 | 1.3 | Ganimete Terbeshi |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
253 | R/A | [5 empty] | 6515
254 | P | C1.3/SDG/142 | 1.3 | Mitrush Kurteli |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
255 | R/A | [5 empty] | 7875
256 | P | C1.3/SDG/143 | 1.3 | Xhavit Ahmeti |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
257 | R/A | [5 empty] | 10000
258 | P | C1.3/SDG/144 | 1.3 | Zahir Pajaziti |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
259 | R/A | [5 empty] | 8560
260 | P | C1.3/SDG/145 | 1.3 | Kadri Kadriu |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
261 | R/A | [5 empty] | 7750
262 | P | C1.3/SDG/147 | 1.3 | Daut Bogujevci |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
263 | R/A | [5 empty] | 6850
264 | P | C1.3/SDG/148 | 1.3 | Bajram Curri |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
265 | R/A | [5 empty] | 9705
266 | P | C1.3/SDG/149 | 1.3 | Fazli Grajcevci |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
267 | R/A | [5 empty] | 7685
268 | P | C1.3/SDG/150 | 1.3 | Gradjevinsko Saobracajna Skola |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
269 | R/A | [5 empty] | 7767
270 | P | C1.3/SDG/152 | 1.3 | Vehbi Ibrahimi |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
271 | R/A | [5 empty] | 5055
272 | P | C1.3/SDG/153 | 1.3 | Esat Berisha |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
273 | R/A | [5 empty] | 5600
274 | P | C1.3/SDG/154 | 1.3 | Fan Noli |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
275 | R/A | [5 empty] | 10000
276 | P | C1.3/SDG/155 | 1.3 | Kenan Halimi |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
277 | R/A | [5 empty] | 6590
278 | P | C1.3/SDG/156 | 1.3 | Halil Alidema |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
279 | R/A | [5 empty] | 9520
280 | P | C1.3/SDG/157 | 1.3 | Ali Gashi |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
281 | R/A | [5 empty] | 6090
282 | P | C1.3/SDG/158 | 1.3 | 28 Nentori |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
283 | R/A | [5 empty] | 5896
284 | P | C1.3/SDG/159 | 1.3 | Shaban Jashari |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
285 | R/A | [5 empty] | 10000
286 | P | C1.3/SDG/160 | 1.3 | Shote Galica |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
287 | R/A | [5 empty] | 9035
288 | P | C1.3/SDG/161 | 1.3 | Fazli Grajcevci |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
289 | R/A | [5 empty] | 10000
290 | P | C1.3/SDG/163 | 1.3 | Lumni Surdulli |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
291 | R/A | [5 empty] | 5790
292 | P | C1.3/SDG/164 | 1.3 | SHMU 2 |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
293 | R/A | [5 empty] | 10000
294 | P | C1.3/SDG/165 | 1.3 | Mihaliq |  |  | 10000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGP
295 | R/A | [5 empty] | 5290
THIRD ROUND PRIMARY SCHOOL
296 | P | C1.3/SDG/166 | 1.3 | Tefik Canga |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
297 | R/A | [5 empty] | 10000
298 | P | C1.3/SDG/167 | 1.3 | SH.m.f.u. Tern |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
299 | R/A | [5 empty] | 6805
300 | P | C1.3/SDG/168 | 1.3 | A. Bajrami |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
301 | R/A | [5 empty] | 4825
302 | P | C1.3/SDG/169 | 1.3 | Zenel Hajdini |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
303 | R/A | [5 empty] | 9830
304 | P | C1.3/SDG/170 | 1.3 | Sinan Thaci |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
305 | R/A | [5 empty] | 4835
306 | P | C1.3/SDG/171 | 1.3 | Fatmir Berisha |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
307 | R/A | [5 empty] | 7825
308 | P | C1.3/SDG/172 | 1.3 | 7 Marsi |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
309 | R/A | [5 empty] | 7330
310 | P | C1.3/SDG/173 | 1.3 | Iliria |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
311 | R/A | [5 empty] | 5155
312 | P | C1.3/SDG/174 | 1.3 | Shkendija |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
313 | R/A | [5 empty] | 7410
314 | P | C1.3/SDG/175 | 1.3 | Svetlost, Krusheva |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
315 | R/A | [5 empty] | 4350
316 | P | C1.3/SDG/176 | 1.3 | Durak Ahmeti |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
317 | R/A | [5 empty] | 6600
318 | P | C1.3/SDG/177 | 1.3 | Luigj Gurakuqi |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
319 | R/A | [5 empty] | 4950
320 | P | C1.3/SDG/178 | 1.3 | Mark Zef Prenaj |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
321 | R/A | [5 empty] | 4950
322 | P | C1.3/SDG/179 | 1.3 | Heronjt e Kosoves |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
323 | R/A | [5 empty] | 6585
324 | P | C1.3/SDG/180 | 1.3 | Liria |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
325 | R/A | [5 empty] | 6285
326 | P | C1.3/SDG/181 | 1.3 | Eqrem Qabej |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
327 | R/A | [5 empty] | 6015
328 | P | C1.3/SDG/182 | 1.3 | Ganimete Terbeshi |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
329 | R/A | [5 empty] | 6460
330 | P | C1.3/SDG/183 | 1.3 | Hasan Prishitna |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
331 | R/A | [5 empty] | 5080
332 | P | C1.3/SDG/184 | 1.3 | Afrim Krasniqi |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
333 | R/A | [5 empty] | 5240
334 | P | C1.3/SDG/185 | 1.3 | Rilindja |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
335 | R/A | [5 empty] | 6375
336 | P | C1.3/SDG/186 | 1.3 | Hill Mosi |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
337 | R/A | [5 empty] | 5895
338 | P | C1.3/SDG/187 | 1.3 | Vaso Pashe Shkodrani |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
339 | R/A | [5 empty] | 8685
340 | P | C1.3/SDG/188 | 1.3 | Martin Camaj |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
341 | R/A | [5 empty] | 8520
342 | P | C1.3/SDG/189 | 1.3 | Ardhemrija |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
343 | R/A | [5 empty] | 4920
344 | P | C1.3/SDG/190 | 1.3 | Isa Boletini |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
345 | R/A | [5 empty] | 6985
346 | P | C1.3/SDG/191 | 1.3 | Gjergj Fishta |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
347 | R/A | [5 empty] | 10000
348 | P | C1.3/SDG/192 | 1.3 | Asim Vokshi |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
349 | R/A | [5 empty] | 9040
350 | P | C1.3/SDG/193 | 1.3 | Shefki Kuleta |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
351 | R/A | [5 empty] | 8380
352 | P | C1.3/SDG/194 | 1.3 | Mihail Grameno |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
353 | R/A | [5 empty] | 10000
354 | P | C1.3/SDG/195 | 1.3 | Liria |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
355 | R/A | [5 empty] | 7290
356 | P | C1.3/SDG/196 | 1.3 | Nazim Hikmet |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
357 | R/A | [5 empty] | 8285
358 | P | C1.3/SDG/197 | 1.3 | Nuhi Berisha |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
359 | R/A | [5 empty] | 4410
360 | P | C1.3/SDG/198 | 1.3 | Idriz Seferi |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
361 | R/A | [5 empty] | 4070
362 | P | C1.3/SDG/199 | 1.3 | Skender Emerllahu |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
363 | R/A | [5 empty] | 6555
364 | P | C1.3/SDG/200 | 1.3 | Dositej Obradovic |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
365 | R/A | [5 empty] | 6285
366 | P | C1.3/SDG/201 | 1.3 | Mehdi Sylejman Bytyqi |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
367 | R/A | [5 empty] | 4795
368 | P | C1.3/SDG/202 | 1.3 | Minatori |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
369 | R/A | [5 empty] | 4520
370 | P | C1.3/SDG/203 | 1.3 | Liria |  |  | 10000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGP
371 | R/A | [5 empty] | 7445
372 | P | Subtotal School Development Grants - primary |  |  |  |  | 1830321
373 | R/A | [5 empty] | 1272845.8
374 |  | First round, Secondary School Grants
375 | P | C1.3/SDG/10 | 1.3 | F. Guri V.Caka | 1 | 0 | 15000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGS
376 | R/A | [5 empty] | 13661 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
377 | P | C1.3/SDG/12 | 1.3 | Dardania | 1 | 0 | 15000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGS
378 | R/A |  |  |  |  | 0 | 8610 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
379 | P | C1.3/SDG/13 | 1.3 | K. I Manastirit - Firaje | 1 | 0 | 15000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGS
380 | R/A |  |  |  |  | 0 | 6912 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
381 | P | C1.3/SDG/20 | 1.3 | Gjimnazi II Gjuhersor | 1 | 0 | 15000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGS
382 | R/A | [5 empty] | 14100 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
383 | P | C1.3/SDG/21 | 1.3 | Jeta e Re | 1 | 0 | 15000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGS
384 | R/A | [5 empty] | 15000 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
385 | P | C1.3/SDG/37 | 1.3 | 12 Maji | 1 | 0 | 15000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGS
386 | R/A | [5 empty] | 10806 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
387 | P | C1.3/SDG/39 | 1.3 | Lasgush Poradeci | 1 |  | 15000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGS
388 | R/A | [5 empty] | 11995 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
389 | P | C1.3/SDG/45 | 1.3 | Shaban Spahija | 1 |  | 15000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGS
390 | R/A | [5 empty] | 15000 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
391 | P | C1.3/SDG/63 | 1.3 | Gj. Sami Frasheri | 1 |  | 15000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGS
392 | R/A | [5 empty] | 15000 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
393 | P | C1.3/SDG/69 | 1.3 | Aleksander Xhuvani | 1 |  | 15000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGS
394 | R/A | [5 empty] | 15000 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
395 | P | C1.3/SDG/85 | 1.3 | Veliko Rapotovo | 1 |  | 15000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGS
396 | R/A | [5 empty] | 8740 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
397 | P | C1.3/SDG/89 | 1.3 | Shkolla e Mesme e Mjekesise | 1 | 0 | 15000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGS
398 | R/A |  |  |  |  | 0 | 7641 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
399 | P | C1.3/SDG/95 | 1.3 | Gj,K. Skenderbeu | 1 | 0 | 15000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGS
400 | R/A |  |  |  |  | 0 | 15000 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
401 | P | C1.3/SDG/97 | 1.3 | Anton Cetta | 1 | 0 | 15000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGS
402 | R/A |  |  |  |  | 0 | 15000 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
403 | P | C1.3/SDG/103 | 1.3 | Arkitekt Sinani | 1 | 0 | 15000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGS
404 | R/A |  |  |  |  | 0 | 13549 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
405 | P | C1.3/SDG/109 | 1.3 | Eqrem Qabej | 1 | 0 | 15000 | MNL | Post | 2011-03-14 | 14 | 2011-03-28 |  | NA | 3 | 2011-03-31 | 14 | 2011-04-14 | 7 | 2011-04-21 | 14 | 2011-05-05 | 2 | 2011-05-07 | 7 | 2011-05-14 | 7 | 2011-05-21 | 30 | 2011-06-20 |  | SDGS
406 | R/A |  |  |  |  | 0 | 15000 |  |  | 2011-02-14 |  | NA |  | NA |  | NA |  | NA |  | NA |  | 2011-03-08 |  | 2011-03-16 |  | 2011-03-16 | 0 | 2011-03-16 | 122 | 2011-07-16
SECOND ROUND - SECONDARY SCHOOLS
407 | P | C1.3/SDG/110 | 1.3 | Pjeter Bogdani | 1 | 0 | 15000 | MNL | Post | 2012-01-16 | 14 | 2012-01-30 |  | NA | 3 | 2012-02-02 | 14 | 2012-02-16 | 7 | 2012-02-23 | 14 | 2012-03-08 | 2 | 2012-03-10 | 7 | 2012-03-17 | 7 | 2012-03-24 | 30 | 2012-04-23 |  | SDGS
408 | R/A |  |  |  |  | 0 | 13885
409 | P | C1.3/SDG/122 | 1.3 | Gani Cavdarbashi | 1 | 0 | 15000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGS
410 | R/A |  |  |  |  | 0 | 15000
411 | P | C1.3/SDG/129 | 1.3 | Hysni Zajmi | 1 | 0 | 15000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGS
412 | R/A |  |  |  |  | 0 | 15000
413 | P | C1.3/SDG/135 | 1.3 | Odhise Pakali | 1 | 0 | 15000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGS
414 | R/A |  |  |  |  | 0 | 9650
415 | P | C1.3/SDG/141 | 1.3 | Eqrem Qabej | 1 | 0 | 15000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGS
416 | R/A |  |  |  |  | 0 | 11634
417 | P | C1.3/SDG/146 | 1.3 | Isa Boletini | 1 | 0 | 15000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGS
418 | R/A |  |  |  |  | 0 | 15000
419 | P | C1.3/SDG/151 | 1.3 | Arberia | 1 | 0 | 15000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGS
420 | R/A |  |  |  |  | 0 | 12912
421 | P | C1.3/SDG/162 | 1.3 | Frang Bardhi | 1 | 0 | 15000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGS
422 | R/A |  |  |  |  | 0 | 15000
423 | P | C1.3/SDG/110 | 1.3 |  | 1 | 0 | 15000 | MNL | Post | 2012-01-16 | 30 | 2012-02-15 |  | NA | 30 | 2012-03-16 | 20 | 2012-04-05 | 10 | 2012-04-15 | 15 | 2012-04-30 | 10 | 2012-05-10 | 7 | 2012-05-17 | 7 | 2012-05-24 | 130 | 2012-10-01 |  | SDGS
424 | R/A | [5 empty] | 0
THIRD ROUND - SECONDARY SCHOOLS
425 | P | C1.3/SDG/ | 1.3 | SH.M.L | 1 | 0 | 15000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGS
426 | R/A | [5 empty] | 8432
427 | P | C1.3/SDG/ | 1.3 | Sh. E mesme ekonomike | 1 | 0 | 15000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGS
428 | R/A | [5 empty] | 6899
429 | P | C1.3/SDG/ | 1.3 | Fehmi Lladrovci | 1 | 0 | 15000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGS
430 | R/A | [5 empty] | 15000
431 | P | C1.3/SDG/ | 1.3 | Hamez Jashari | 1 | 0 | 15000 | MNL | Post | 2012-05-07 | 30 | 2012-06-06 |  | NA | 30 | 2012-07-06 | 20 | 2012-07-26 | 10 | 2012-08-05 | 15 | 2012-08-20 | 10 | 2012-08-30 | 7 | 2012-09-06 | 7 | 2012-09-13 | 130 | 2013-01-21 |  | SDGS
432 | R/A | [5 empty] | 12762
433 | P | Subtotal School Development Grants - Secondary |  |  |  |  | 435000
434 | R/A | [5 empty] | 352188
435
436 |  | Component 1. Totals (Grants) |  |  | 15 | 105000 | 2313611
437 |  |  |  |  | 0 | 0 | 1658584.3
|  |  |  | Database Subtotals Tool | 15 | 181845.6407 | 141378.26
Formulas:
WB "No Objection" = [Prep. of Doc.]+[Int. /a]
WB "No Objection" = [Evalu- ation & Recomm.]+[Int. /a]
Issue of Documents = [WB "No Objection"]+[Int. /a]
Sub- mission of Bids = [Issue of Documents]+[Int. /a]
Evalu- ation & Recomm. = [Sub- mission of Bids]+[Int. /a]
Contract Award = [WB "No Objection"]+[Int. /a]
Contract Signature = [Contract Award]+[Int. /a]
Start = [Contract Signature]+[Int. /a]
Comple- tion = [Start]+[Exec. /b]

## Operational Expenditures
Ln. # | Status P R/A d/ | Contract Reference # Standard Prefix "KOS-IDEP/H3420/" removed from below listings | Comp. | Description | 2012-10-16 14:49 |  | Proc. Method | WB Review | Schedule (dd-Mmm-yy) | [6 empty] | Comments | Procure- ment Accounts
[5 empty] | Appraisal Estimates P (planned) Enter New Estimates in EUR Under R/A Rows below |  |  |  | Prep. of Doc. | Int. /a | WB "No Objection" | Int. /a | Start | Exec. /b | Comple- tion
Procurement Steps (1-11)
[5 empty] | USD | EUR |  |  | 1 |  | 2 |  | 10 |  | 11
1 |  | COMPONENT 2. BUILDING INSTITUTIONS & MANAGEMENT CAPACITY IN PRIMARY & SECONDARY EDUCATION
2
3 |  | OPERATIONAL EXPENDITURES
4 | P |  | 2.5 | Pension contributions for local consultants | 0 | 8190 | NA | Post | 2011-04-20 | [7 empty] | OPER
5 | R/A
6 | P |  | 2.5 | Translation services | 0 | 30000 | NA | Post | 2011-04-20 | [7 empty] | OPER
7 | R/A |  |  |  | 0
6 | P |  | 2.5 | Phone cards |  | 5750 | NA | Post | 2011-04-20 | [7 empty] | OPER
7 | R/A |  |  |  | 0 | 0
8 | P |  | 2.5 | Fuel |  | 4500 | NA | Post | 2011-04-20 | [7 empty] | OPER
9 | R/A |  |  |  | 0 | 0
10 | P |  | 2.5 | Vehicle maintenance |  |  | NA | Post | 2011-04-20 | [7 empty] | OPER
11 | R/A |  |  |  | 0 | 0
12 | P |  | 2.5 | Advertisements |  | 680 | NA | Post | 2011-04-20 | [7 empty] | OPER
13 | R/A |  |  |  | 0 | 0
14 | P |  | 2.5 | Hospitality |  | 2710 | NA | Post | 2011-04-20 | [7 empty] | OPER
15 | R/A |  |  |  | 0 | 0
16 | P |  | 2.5 | Office supplies & consumables |  | 3756 | NA | Post | 2011-04-20 | [7 empty] | OPER
17 | R/A |  |  |  | 0 | 0
18
19 | P | Component 2. Subtotals |  |  | 0 | 55586
20 | R/A |  |  |  | 0 | 0
= R/A Revised/Actuals
Cell turns red if planned date has passed
Cell turns normal again if cell for R/A (revised/actual) date is filled in.
Notes:
a/ Interval for preparation or clearance (in days); working document PP only
b/ Number of days to execute the contract; working document PP only
c/ Estimates include price contingencies
d/ Status: P=Planned (original scope and estimate); R/A=Revised or Actual
|  |  |  | Database Subtotals Tool | 0

## Financial Management
Ln. # | Consultant Contractor/Supplier or Activity | Comp. | Activity | Amounts Allocated in XDR Component Level Only | Appraisal Estimate USD COSTAB Tables | Appraisal Estimate | Obligations (Contracts Signed & Other Direct Expenditures) |  | Payments WA #1 Please update rates as per WA |  |  | Payments WA #2 Please update rates as per WA |  |  | Payments WA #3 Please update rates as per WA |  |  | Payments WA #4 Please update rates as per WA |  |  | Payments under WA #5 Please update rates as per WA |  |  | Payments under WA #6 Please update rates as per WA |  |  | Payments under Direct Payments Please update rates as per WA |  |  | Payments under WA #7 Please update rates as per WA |  |  | Payments under WA #8 Please update rates as per WA |  |  | Payments under WA #9 Please update rates as per WA |  |  | Payments under WA #10 Please update rates as per WA |  |  | Payments under WA #11 Please update rates as per WA |  |  | Payments under WA #12 Please update rates as per WA |  |  | Payments under WA #13 Please update rates as per WA |  |  | Payments under WA #14 Please update rates as per WA |  |  | Payments under WA #15 Please update rates as per WA |  |  | Payments under WA #16 Please update rates as per WA |  |  | Payments under WA #17 Please update rates as per WA |  |  | Payments under WA #18 Please update rates as per WA |  |  | Payments under WA #19 Please update rates as per WA |  |  | Cumulative Amounts Paid To date |  |  | Amounts Unpaid To Date Please use current rates |  |  | Total Commitments To Date |  |  | Estimate for Uncommitted Items Please use current rates |  |  | Total Requirement USD | Total Requirement EUR | Total Requirement XDR | Surplus or Deficit XDR | Comments
[6 empty] | 0.88113 | USD | EUR | 1.3047 | Enter EUR Values | 0.88258 | 1.4102 | Enter EUR Values | 0.91092 | 1.4724 | Enter EUR Values | 0.92829 | 1.4336 | Enter EUR Values | 0.91829 | 1.2941 | Enter EUR Values | 0.87 | 1.2284 | Enter EUR Values | 0.83257089008 | 1.3259 | Enter EUR Values | 0.86392 | 1.294 | Enter EUR Values | 0.87 | 1.294 | Enter EUR Values | 0.87 | 1.294 | Enter EUR Values | 0.87 | 1.294 | Enter EUR Values | 0.87 | 1.294 | Enter EUR Values | 0.87 | 1.294 | Enter EUR Values | 0.87 | 1.294 | Enter EUR Values | 0.87 | 1.294 | Enter EUR Values | 0.87 | 1.294 | Enter EUR Values | 0.87 | 1.294 | Enter EUR Values | 0.87 | 1.294 | Enter EUR Values | 0.87 | 1.294 | Enter EUR Values | 0.87 | 1.294 | Enter EUR Values | 0.87 | USD | EUR | XDR Equivalent | 1.2698 | 0.78753 | 0.85638 | USD | EUR | Equivalent XDR | 1.2698 | Insert Estimate in this colmn. | 0.85638
[6 empty] | USD to EUR ↑ |  |  | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ | EUR to USD ↑ |  | EUR to XDR ↑ |  |  |  | EUR to USD ↑ | USD to EUR ↑ | EUR to XDR ↑ |  |  |  | EUR to USD ↑ |  | EUR to XDR ↑
[6 empty] | EUR |  |  | USD |  | XDR | USD |  | XDR | USD |  | XDR | USD |  | XDR | USD |  | XDR | USD |  | XDR | USD |  | XDR | USD |  | XDR | USD |  | XDR | USD |  | XDR | USD |  | XDR | USD |  | XDR | USD |  | XDR | USD |  | XDR | USD |  | XDR | USD |  | XDR | USD |  | XDR | USD |  | XDR | USD |  | XDR | USD |  | XDR |  |  |  | USD | EUR | XDR |  |  |  | USD | EUR | XDR
A | B | C | D | E | F | F | G | H | I | J | K | L | M | N | O | P | Q | R | S | T | U | V | W | X | Y | Z | AA | AB | AC | AD | AE | AF | AG | AH | AI | AJ | AK | AL | AJ | AK | AL | AJ | AK | AL | AJ | AK | AL | AJ | AK | AL | AJ | AK | AL | AJ | AK | AL | AJ | AK | AL | AJ | AK | AL | AJ | AK | AL | AJ | AK | AL | AM | AN | AO | AP | AQ | AR | AS | AT | AU | AV | AW | AX | AY | AZ | BA | BB
|  |  |  | Value | Value & Formula | Value & Formula | Value | Value | J*I$3 | Value | J*J$3 | M*L$3 | Value | M*M$3 | P*O$3 | Value | P*P$3 | S*R$3 | Value | S*S$3 | V*U$3 | Value | V*V$3 | Y*X$3 | Value | Y*Y$3 | AB*AA$3 | Value | AB*AB$3 | AE*AD$3 | Value | AE*AE$3 | AH*AG$3 | Value | AH*AH$3 | AK*AJ$3 | Value | AK*AK$3 | AK*AJ$3 | Value | AK*AK$3 | AK*AJ$3 | Value | AK*AK$3 | AK*AJ$3 | Value | AK*AK$3 | AK*AJ$3 | Value | AK*AK$3 | AK*AJ$3 | Value | AK*AK$3 | AK*AJ$3 | Value | AK*AK$3 | AK*AJ$3 | Value | AK*AK$3 | AK*AJ$3 | Value | AK*AK$3 | AK*AJ$3 | Value | AK*AK$3 | AK*AJ$3 | Value | AK*AK$3 | U+X+AA+AD +AG+AJ | J+M+P+S +V+Y+AB +AE+AH+AK | K+N+Q+T+W +Z+AC+AF +AI+AL | G-AM (pink) Greem cells are EUR to USD | H-AN (yellow) Pink cells are USD to EUR | AQ/AR$3 EUR to XDR | AM+AP | AN+AQ | AO+AR | AW*AV$3 | Value | AW*AX$3 | AS+AV | AT+AW | AU+AX | E-BA305 At Component Level Only
1 | COMPONENT 1. STRENGTHENING ORGANIZATION & FINANCING OF EDUCATION SYSTEM
2
3 | CONSULTANTS
4 | Dennis Farrington | 1.1 | Legal framework |  | 92600 | 72000 |  | 72000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 41289.1163 | 28800 | 26446.7932 | 18634.3202 | 14400 | 12528.0001 | 17689.6799 | 14400 | 11989.0208 | 0 |  | 0 | 0 |  | 0 | 18634.32 | 14400 | 12528 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 96247.4365 | 72000 | 63491.8141 | 0 | 0 | 0 | 96247.4365 | 72000 | 63491.8141 | 0 | 0 | 0 | 96247.4365 | 72000 | 63491.8141 |  | contracted
5 | Dennis Farrington | 1.1 | Implementation of new legislation |  | 0 | 27040 |  | 27040 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 5183.7184 | 4005.81 | 3485.0547 | 22036.6492 | 17029.21 | 14815.4127 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 27220.3676 | 21035.02 | 18300.4674 | 7625.1236 | 6004.98 | 5142.5268 | 34845.4912 | 27040 | 23442.9942 | 38094 | 30000 | 25691.31 | 72939.4912 | 57040 | 49134.3042
6 | Rosalind Levacic | 1.2 | Financing formula |  | 107500 | 44496.03 | 64099 | 44496.03 | 26719.8459 | 20480.47 | 18075.5651 | 0 |  | 0 | 16331.8744 | 11092.01 | 10296.6131 | 9250.1097 | 6452.14 | 5924.9449 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 10519.5007 | 8129.13 | 7072.3431 | 19871.7683 | 15356.26 | 13359.9462 | 12062.1118 | 9321.21 | 8109.4527 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 94755.2108 | 70831.22 | 62838.8651 | 0 | 0 | 0 | 94755.2108 | 70831.22 | 62838.8651 | 30656.2108 | 0 | 0 | 125411.4215 | 70831.22 | 62838.8651 |  | Completed
7 | Rosalind Levacic | 1.2 | Financing formula |  | 0 | 91960 |  | 91960 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 8374.3282 | 6471.41 | 5630.1267 | 13663.2877 | 11122.38 | 9260.1698 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 5116.6737 | 3954 | 3439.98 | 3411.4781 | 2636.28 | 2293.5636 | 0 |  | 0 | 4372.5691 | 3378.98 | 2939.7126 | 3813.8242 | 2947.2 | 2564.064 | 18874.0428 | 14585.25 | 12689.1675 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 57626.2037 | 45095.5 | 38816.7842 | 59508.5421 | 46864.5 | 40133.6799 | 117134.7458 | 91960 | 78950.4642 | 0 | 0 | 0 | 117134.7458 | 91960 | 78950.4642 |  | Contracted
8 | Prism Research | 1.2 | Baseline survey |  | 0 | 24674 |  | 24674 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 15964.6948 | 12337 | 10733.19 | 15964.6948 | 12337 | 10733.19 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 31929.3897 | 24674 | 21466.38 | 0 | 0 | 0 | 31929.3897 | 24674 | 21466.38 | 0 |  | 0 | 31929.3897 | 24674 | 21466.38 |  | Contracted
9 | Besnik Limaj | 1.2 | Data analysis |  | 6800 | 6400 |  | 6400 | 0 |  | 0 | 0 |  | 0 | 5654.0156 | 3840 | 3564.6374 | 0 |  | 0 | 3312.768 | 2560 | 2227.2 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 8966.7837 | 6400 | 5791.8375 | 0 | 0 | 0 | 8966.7837 | 6400 | 5791.8375 | 0 |  | 0 | 8966.7837 | 6400 | 5791.8375 |  | Completed
10 | Edi Bunjaku | 1.2 | Training materials analyst |  | 0 | 1300 |  | 1300 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1682.265 | 1300 | 1131 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1682.265 | 1300 | 1131 | 0 | 0 | 0 | 1682.265 | 1300 | 1131 | 0 |  | 0 | 1682.265 | 1300 | 1131 |  | Completed
11 | Pakize Isufaj | 1.2 | Finance expert for Help Desk-1 |  | 0 | 5374 |  | 5374 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3865.3274 | 2987 | 2598.69 | 2211.21 | 1800 | 1498.6276 | 0 |  | 0 | 759.6203 | 587.01 | 510.6987 | 4270.365 | 3300 | 2871 | 0 |  | 0 | 4092.6919 | 3162.7 | 2751.549 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 15199.2146 | 11836.71 | 10230.5653 | -8206.3492 | -6462.71 | -5534.5162 | 6992.8655 | 5374 | 4696.0491 | 0 |  | 0 | 6992.8655 | 5374 | 4696.0491 |  | Completed
12 | Hysni Maxharraj | 1.2 | Finance expert for Help Desk-2 |  | 0 | 4787 |  | 4787 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3865.3274 | 2987 | 2598.69 | 2211.21 | 1800 | 1498.6276 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 6076.5374 | 4787 | 4097.3176 | 0 | 0 | 0 | 6076.5374 | 4787 | 4097.3176 | 0 |  | 0 | 6076.5374 | 4787 | 4097.3176 |  | Completed
13 | Pakize Isufaj | 1.2 | Head of Help Desk |  | 0 | 13200 |  | 13200 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3341.2371 | 2582 | 2246.34 | 0 |  | 0 | 5693.82 | 4400 | 3828 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4092.6919 | 3162.7 | 2751.549 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 13127.749 | 10144.7 | 8825.889 | 3879.6199 | 3055.3 | 2616.4886 | 17007.369 | 13200 | 11442.3776 | 0 | 0 | 0 | 17007.369 | 13200 | 11442.3776 |  | Contracted
14 | Pakize Isufaj | 1.2 | Head of Help Desk |  | 0 | 23550 |  | 23550 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 4092.6919 | 3162.7 | 2751.549 | 4448.0381 | 3437.3 | 2990.451 | 4448.0381 | 3437.3 | 2990.451 | 0 |  | 0 | 4270.365 | 3300 | 2871 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 17259.1331 | 13337.3 | 11603.451 | 12968.0865 | 10212.7 | 8745.9214 | 30227.2195 | 23550 | 20349.3724 | 0 | 0 | 0 | 30227.2195 | 23550 | 20349.3724
15 | Vjolca Sellimi | 1.2 | Education Finance Expert 2 |  | 0 | 10800 |  | 10800 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2734.3276 | 2113 | 1838.31 | 3493.935 | 2700 | 2349 | 4658.58 | 3600 | 3132 | 3353.7894 | 2591.7 | 2254.779 | 0 |  | 0 | 3634.7665 | 2808.83 | 2443.6821 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 17875.3985 | 13813.53 | 12017.7711 | -3826.5804 | -3013.53 | -2580.7178 | 14048.8181 | 10800 | 9437.0533 | 0 | 0 | 0 | 14048.8181 | 10800 | 9437.0533 |  | Contracted
16 | Vjolca Sellimi | 1.2 | Education Finance Expert 2 |  | 0 | 19269 |  | 19269 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 3353.7894 | 2591.7 | 2254.779 | 0 |  | 0 | 3634.0806 | 2808.3 | 2443.221 | 3353.7894 | 2591.7 | 2254.779 | 3493.935 | 2700 | 2349 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 13835.5944 | 10691.7 | 9301.779 | 10891.4555 | 8577.3 | 7345.4024 | 24727.0499 | 19269 | 16647.1814 | 0 | 0 | 0 | 24727.0499 | 19269 | 16647.1814
17 | Mehmet Simnica | 1.2 | Trainer on school financing |  | 0 | 3800 |  | 3800 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 4917.39 | 3800 | 3306 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4917.39 | 3800 | 3306 | 0 | 0 | 0 | 4917.39 | 3800 | 3306 | 1269.8 | 1000 | 856.377 | 6187.19 | 4800 | 4162.377
18 | Mevlide Shamolli | 1.2 | Trainer on school financing |  | 0 | 3800 |  | 3800 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 4917.39 | 3800 | 3306 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4917.39 | 3800 | 3306 | 0 | 0 | 0 | 4917.39 | 3800 | 3306 | 1269.8 | 1000 | 856.377 | 6187.19 | 4800 | 4162.377
19 | Jeton Kryeziu | 1.2 | Trainer on school financing |  | 0 | 3800 |  | 3800 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 4917.39 | 3800 | 3306 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4917.39 | 3800 | 3306 | 0 | 0 | 0 | 4917.39 | 3800 | 3306 | 1269.8 | 1000 | 856.377 | 6187.19 | 4800 | 4162.377
20 | Jeton Gashi | 1.2 | Trainer on school financing |  | 0 | 3600 |  | 3600 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 4658.58 | 3600 | 3132 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4658.58 | 3600 | 3132 | 0 | 0 | 0 | 4658.58 | 3600 | 3132 | 1269.8 | 1000 | 856.377 | 5928.38 | 4600 | 3988.377
21 | Aferdita Strellci | 1.2 | Trainer on school financing |  | 0 | 3600 |  | 3600 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 4658.58 | 3600 | 3132 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4658.58 | 3600 | 3132 | 0 | 0 | 0 | 4658.58 | 3600 | 3132 | 1269.8 | 1000 | 856.377 | 5928.38 | 4600 | 3988.377
22 | Fadil Veseli | 1.2 | Trainer on school procurement |  | 0 | 4000 |  | 4000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1035.24 | 800 | 696 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1035.24 | 800 | 696 | 4063.36 | 3200 | 2740.4064 | 5098.6 | 4000 | 3436.4064 | 2539.6 | 2000 | 1712.754 | 7638.2 | 6000 | 5149.1604
23 | Mirvete Gerguri | 1.2 | Trainer on school procurement |  | 0 | 4000 |  | 4000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4348.008 | 3360 | 2923.2 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4348.008 | 3360 | 2923.2 | 812.672 | 640 | 548.0813 | 5160.68 | 4000 | 3471.2813 | 2539.6 | 2000 | 1712.754 | 7700.28 | 6000 | 5184.0353
24 | Fatmire M Morina | 1.2 | Trainer on school procurement |  | 0 | 4000 |  | 4000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4787.985 | 3700 | 3219 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4787.985 | 3700 | 3219 | 380.94 | 300 | 256.9131 | 5168.925 | 4000 | 3475.9131 | 2539.6 | 2000 | 1712.754 | 7708.525 | 6000 | 5188.6671
25 | Vllaznim Reshani | 1.2 | Trainer on school procurement |  | 0 | 4000 |  | 4000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4969.152 | 3840 | 3340.8 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4969.152 | 3840 | 3340.8 | 203.168 | 160 | 137.0203 | 5172.32 | 4000 | 3477.8203 | 2539.6 | 2000 | 1712.754 | 7711.92 | 6000 | 5190.5743
26 | Defrim Kuqi | 1.2 | Trainer on school procurement |  | 0 | 4000 |  | 4000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3933.912 | 3040 | 2644.8 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3933.912 | 3040 | 2644.8 | 1219.008 | 960 | 822.1219 | 5152.92 | 4000 | 3466.9219 | 2539.6 | 2000 | 1712.754 | 7692.52 | 6000 | 5179.6759
27 | Bersant R. Grabanica | 1.2 | Education finance officer for operating at Help Desk |  | 0 | 6300 |  | 1200 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 1523.76 | 1200 | 1027.6524 | 1523.76 | 1200 | 1027.6524 | 0 | 0 | 0 | 1523.76 | 1200 | 1027.6524
28 | Xhafer Ahmeti | 1.3 | Task Manager of the SDG component |  | 46500 | 10400 |  | 10400 | 0 |  | 0 | 0 |  | 0 | 3828.2397 | 2600 | 2413.5566 | 5591.2345 | 3900 | 3581.3366 | 5046.7951 | 3900 | 3393 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 14466.2693 | 10400 | 9387.8932 | 0 | 0 | 0 | 14466.2693 | 10400 | 9387.8932 | 0 |  | 0 | 14466.2693 | 10400 | 9387.8932 |  | Completed
29 | Besim Kokollari | 1,3 | Task Manager of the SDG component |  | 0 | 14400 |  | 14400 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1108.975 | 856.98 | 745.5726 | 4658.58 | 3600 | 3132 | 6211.44 | 4800 | 4176 | 4462.1432 | 3448.2 | 2999.934 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 16441.1382 | 12705.18 | 11053.5066 | 2152.0824 | 1694.82 | 1451.4049 | 18593.2206 | 14400 | 12504.9115 | 0 | 0 | 0 | 18593.2206 | 14400 | 12504.9115 |  | Contracted
30 | Besim Kokollari | 1,3 | Task Manager of the SDG component |  | 0 | 23618 |  | 23618 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 4462.1432 | 3448.2 | 2999.934 | 4855.0168 | 3751.8 | 3264.066 | 4855.0168 | 3751.8 | 3264.066 | 4462.2726 | 3448.3 | 3000.021 | 4658.58 | 3600 | 3132 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 23293.0294 | 18000.1 | 15660.087 | 7133.6094 | 5617.9 | 4811.0403 | 30426.6388 | 23618 | 20471.1273 | 0 | 0 | 0 | 30426.6388 | 23618 | 20471.1273
30 | Local staff | 1.2 | Pension contributions |  | 0 | 2360 |  | 2360 | 0 |  | 0 | 0 |  | 0 | 191.412 | 130 | 120.6778 | 279.5617 | 195 | 179.0668 | 638.8725 | 493.7 | 429.519 | 221.121 | 180 | 149.8628 | 0 |  | 0 | 397.2086 | 306.95 | 267.0465 | 621.144 | 480 | 417.6 | 828.192 | 640 | 556.8 | 414.096 | 320 | 278.4 | 414.096 | 320 | 278.4 | 828.192 | 640 | 556.8 | 828.192 | 640 | 556.8 | 414.096 | 320 | 278.4 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 6076.1839 | 4665.65 | 4069.3729 | -2927.7144 | -2305.65 | -1974.5056 | 3148.4695 | 2360 | 2094.8673 | 0 | 0 | 0 | 3148.4695 | 2360 | 2094.8673
31 | ?? | 1.2 | Other services |  | 0 | 3381.77 |  | 3381.77 | 0 |  | 0 | 0 |  | 0 | 2411.791 | 1638 | 1520.5407 | 2227.5478 | 1553.76 | 1426.8045 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 245.8824 | 190.01 | 165.3087 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4885.2213 | 3381.77 | 3112.6539 | 0 | 0 | 0 | 4885.2213 | 3381.77 | 3112.6539 | 0 | 0 | 0 | 4885.2213 | 3381.77 | 3112.6539
32 | Remzi Salihu | 1.2 & 1.3 | Consultant on SDG and MDG |  | 0 | 7150 |  | 7150 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 7233.7396 | 5590 | 4863.3 | 1916.382 | 1560 | 1298.8106 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 9150.1216 | 7150 | 6162.1106 | 0 | 0 | 0 | 9150.1216 | 7150 | 6162.1106 | 0 |  | 0 | 9150.1216 | 7150 | 6162.1106 |  | Completed
33 | KEC | 1.3 | Consultant to manage MDGs and SDGs |  | 463600 | 266935 |  | 266935 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 53091.3686 | 40040.25 | 34591.4952 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 103628.171 | 80080.5 | 69670.035 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 156719.5396 | 120120.75 | 104261.5302 | 186424.7346 | 146814.25 | 125728.347 | 343144.2743 | 266935 | 229989.8772 | 0 |  | 0 | 343144.2743 | 266935 | 229989.8772 |  | Evaluated
34 | KEC | 1.3 | Amendment #1 modification of original contract |  | #REF! | 60240 |  | 60240 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 103628.171 | 80080.5 | 69670.035 | 12526.404 | 9680 | 8421.6 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 116154.575 | 0 | 78091.635 | 76492.752 | 60240 | 51588.1505 | 192647.327 | 60240 | 129679.7855 | 0 |  | 0 | 192647.327 | 60240 | 129679.7855 |  | contracted
35 | Alexandar Najdovski | 1.3 | Procurement Supervision of SMD Grants (EPIP II) (international) |  | 0 | 20550 |  | 20550 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3988.9092 | 3082.5 | 2681.775 | 27151.816 | 22102.5 | 18401.8981 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 31140.7252 | 25185 | 21083.6731 | -5885.523 | -4635 | -3969.3074 | 25255.2022 | 20550 | 17114.3657 | 0 |  | 0 | 25255.2022 | 20550 | 17114.3657
36 | Subtotal CONSULTANTS |  |  |  | #REF! | 798784.8 | 64099 | 793684.8 | 26719.8459 | 20480.47 | 18075.5651 | 0 | 0 | 0 | 28417.3328 | 19300.01 | 17916.0256 | 58637.5701 | 40900.9 | 37558.9459 | 54960.3876 | 42471.61 | 36950.3009 | 65064.7066 | 52964.88 | 44097.0173 | 53091.3686 | 40040.25 | 34591.4952 | 35071.4466 | 27102.08 | 23578.8096 | 69197.0721 | 53473.26 | 46521.7362 | 29454.1438 | 22761.21 | 19802.2527 | 17439.3942 | 13476.6 | 11724.642 | 119362.3697 | 92239.38 | 80248.2606 | 13766.0133 | 10637.93 | 9254.9991 | 42207.2265 | 32616.38 | 28376.2506 | 125983.8036 | 97356.21 | 84699.9027 | 83899.033 | 64834.46 | 56405.9802 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 823271.7143 | 540895.13 | 549802.1837 | 354432.7472 | 279124.86 | 239036.1102 | 1177704.4616 | 820019.99 | 788838.294 | 87797.2108 | 45000 | 38536.965 | 1265501.6723 | 865019.99 | 827375.259
37 | [10 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
37 | Goods | [24 empty] | 0
A: 38; B: Hardsoft Integration; C: 1.2; D: Developing the Software for Municipal-to School Budget Allocation; F: 40540; F: 49235; H: 49235; Z: 0; AK: 49325; AM: 0; AN: 49325; AO: 0; AP: -114.282; AQ: -90; AR: -77.0739; AS: -114.282; AT: 49235; AU: -77.0739; AV: 0; AW: 0; AX: 0; AY: -114.282; AZ: 49235; BA: -77.0739 | contracted
39 | Blendi | 1.2 | Printing of brochures for the buxheting and financing of schools |  | 5113 | 3900 |  | 3900 | [17 empty] | 0 | [16 empty] | 3900 | [25 empty] | 0 | 3900 | 0 | 0 | 0 | 0 | 0 | 3900 | 0 | 0 |  | 0 | 0 | 3900 | 0
40 | Hardsoft Systems | 1.2 | Hardware for server for school finance |  | 0 | 36970 |  | 36970 | [17 empty] | 0 |  | 36970 | [14 empty] | 0 | [25 empty] | 0 | 36970 | 0 | 0 | 0 | 0 | 0 | 36970 | 0 | 0 |  | 0 | 0 | 36970 | 0
41 | JV Interadria and telefoniku | 1.3 | IT equipment for SDG |  | 0 | 0 |  | 0 | [17 empty] | 0 |  | 0 | [14 empty] | 0 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
42 | ? | 1.3 | Teaching aids for SDG |  | 0 | 0 |  | 0 | [17 empty] | 0 |  | 0 | [14 empty] | 0 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
43 | Korabi | 1.3 | Purchasing of books for SDG |  | 0 | 0 |  | 0 | [17 empty] | 0 |  | 0 | [14 empty] | 0 | [11 empty] | 14331.4 | [13 empty] | 0 | 14331.4 | 0 | -18198.0117 | -14331.4 | -12273.0813 | -18198.0117 | 0 | -12273.0813 | 0 |  | 0 | -18198.0117 | 0 | -12273.0813
44 | Star graf | 1.3 | Purchasing of music Instruments for SDG |  | 0 | 0 |  | 0 | [17 empty] | 0 |  | 0 | [14 empty] | 0 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
41 | ? | 1.3 | IT equipment for SDG for Round III |  | 0 | 0 |  | 0 | [17 empty] | 0 |  | 0 | [14 empty] | 0 | [25 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
45 | SubTotal Goods |  |  |  | 40540 | 90105 |  | 90105 | [17 empty] | 0 | [16 empty] | 3900 |  |  | 0 | [8 empty] | 63656.4 | [13 empty] | 0 | 104526.4 | 0 | -18312.2937 | -14421.4 | -12350.1553 | -18312.2937 | 90105 | -12350.1553 | 0 | 0 | 0 | -18312.2937 | 90105 | -12350.1553
46 | TRAINING | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
47 | Workshop | 1.1 | Legal framework |  | 0 | 13043.2 |  | 13043.2 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 16730.3844 | 12928.7 | 11247.9691 | 0 |  | 0 | 0 |  | 0 | 148.1687 | 114.5 | 99.615 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 16878.5532 | 13043.2 | 11347.5841 | 0 | 0 | 0 | 16878.5532 | 13043.2 | 11347.5841 | 0 |  | 0 | 16878.5532 | 13043.2 | 11347.5841
48 | ? | 1.1 | In support of new legistlation at municipal. |  | 0 | 2500 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3174.5 | 2500 | 2140.9425 | 3174.5 | 2500 | 2140.9425
49 | Study visit to UK | 1.2 | Education finance |  | 30500 | 16576.85 |  | 16576.85 | 21626.988 | 16576.85 | 14630.325 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 21626.988 | 16576.85 | 14630.325 | 0 | 0 | 0 | 21626.988 | 16576.85 | 14630.325 | 0 |  | 0 | 21626.988 | 16576.85 | 14630.325
50 | Training | 1.2 | Training for Municipalities in the implementation of the financing Formula |  | 0 | 14700.56 |  | 14700.56 | 3873.506 | 2969 | 2620.3673 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 8439.7954 | 6870.28 | 5719.9951 | 0 |  | 0 | 5822.2933 | 4499.28 | 3914.3736 | 468.4461 | 362 | 314.94 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 18604.0408 | 14700.56 | 12569.676 | 0 | 0 | 0 | 18604.0408 | 14700.56 | 12569.676 | 0 | 0 | 0 | 18604.0408 | 14700.56 | 12569.676
51 | ? | 1.2 | Workshop Education budget planning in municipalities |  | 0 | 5000 |  | 310 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 393.638 | 310 | 265.4769 | 393.638 | 310 | 265.4769 | 6349 | 5000 | 4281.885 | 6742.638 | 5310 | 4547.3619
51 | Training | 1.2 | Additional Training Aids for Finance |  |  | 1000 |  | 310 | [17 empty] | 0 | [22 empty] | 220
52 | Training | 1.2 | Conference on Reforming the education Financing mechanisms |  |  | 10000 | [19 empty] | 0
53 | Training | 1.2 | Training - implementation of financing formula, Albania |  | 0 | 6348.81 |  | 6348.81 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8215.6776 | 6348.81 | 5523.4647 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 8215.6776 | 6348.81 | 5523.4647 | 0 | 0 | 0 | 8215.6776 | 6348.81 | 5523.4647 | 0 | 0 | 0 | 8215.6776 | 6348.81 | 5523.4647
54 | Workshop | 1.3 | Workshop for SGAB |  | 0 | 352 |  | 352 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 455.5056 | 352 | 306.24 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 455.5056 | 352 | 306.24 | 0 | 0 | 0 | 455.5056 | 352 | 306.24 | 0 |  | 0 | 455.5056 | 352 | 306.24
55 | Workshop | 1.3 | Workshop for SDG, Grant agreement signing ceremony |  | 0 | 445 |  | 445 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 575.8522 | 445 | 387.15 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 575.8522 | 445 | 387.15 | 0 | 0 | 0 | 575.8522 | 445 | 387.15 | 0 | 0 | 0 | 575.8522 | 445 | 387.15
56 | Subtotal Training |  |  |  | 30500 | 69966.42 | 0 | 52086.42 | 25500.4939 | 19545.85 | 17250.6922 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 16730.3844 | 12928.7 | 11247.9691 | 8439.7954 | 6870.28 | 5719.9951 | 0 | 0 | 0 | 5970.462 | 4613.78 | 4013.9886 | 468.4461 | 362 | 314.94 | 8215.6776 | 6348.81 | 5523.4647 | 455.5056 | 352 | 306.24 | 575.8522 | 4345 | 3780.15 | 0 | 0 | 0 | 0 | 220 | 191.4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 66356.6173 | 51466.42 | 44764.4397 | 393.638 | 310 | 265.4769 | 66750.2553 | 51776.42 | 45029.9166 | 9523.5 | 7500 | 6422.8275 | 76273.7553 | 59276.42 | 51452.7441
57 | [10 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
58 | GRANTS | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
59 | School Development Grants | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
60 | Municipal Development Grants | [9 empty] | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0
61 | 1. Kacanik | 1.2 | Municipal development grants |  | 35000 | 24256 |  | 24256 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 10599.5637 | 8191 | 7126.17 | 6907.5743 | 5623 | 4681.5461 | 0 |  | 0 | 2934.9054 | 2268 | 1973.16 | 148.8157 | 115 | 100.05 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 20590.8591 | 16197 | 13880.9261 | 10233.3182 | 8059 | 6901.5422 | 30824.1773 | 24256 | 20782.4684 | 0 |  | 0 | 30824.1773 | 24256 | 20782.4684
62 | 2. Gjilan | 1.2 | Municipal development grants |  | 35000 | 21200 |  | 21200 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 21028.3127 | 16250 | 14137.5001 | 0 |  | 0 | 0 |  | 0 | 1427.9842 | 1103.5 | 960.045 | 0 |  | 0 | 2679.9776 | 2071 | 1801.77 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 25136.2745 | 19424.5 | 16899.3151 | 2254.5299 | 1775.5 | 1520.4974 | 27390.8044 | 21200 | 18419.8124 | 0 |  | 0 | 27390.8044 | 21200 | 18419.8124
63 | 3. Istog | 1.2 | Municipal development grants |  | 35000 | 10890 |  | 10890 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 8708.7236 | 6729.82 | 5854.9434 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 8708.7236 | 6729.82 | 5854.9434 | 5282.5966 | 4160.18 | 3562.6825 | 13991.3201 | 10890 | 9417.6259 | 0 |  | 0 | 13991.3201 | 10890 | 9417.6259
64 | 4. Klina | 1.2 | Municipal development grants |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
65 | 5. Shtime | 1.2 | Municipal development grants |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
66 | 6. Mitrovica | 1.2 | Municipal development grants |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
67 | 7. Peja | 1.2 | Municipal development grants |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
68 | 8. Gjakova | 1.2 | Municipal development grants |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
69 | 9. Prizreni | 1.2 | Municipal development grants |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
70 | 10. Suhareka | 1.2 | Municipal development grants |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
71 | 11. Ferizaj | 1.2 | Municipal development grants |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
72 | 12. Podujeva | 1.2 | Municipal development grants |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
73 | 13. Prishtina | 1.2 | Municipal development grants |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
74 | 14. Other | 1.2 | Municipal development grants |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
75 | 15. Other | 1.2 | Municipal development grants |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
76 | Subtotal Municipal Development Grants |  |  |  | 105000 | 56346 | 0 | 56346 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 31627.8764 | 24441 | 21263.6701 | 6907.5743 | 5623 | 4681.5461 | 0 | 0 | 0 | 4362.8896 | 3371.5 | 2933.205 | 148.8157 | 115 | 100.05 | 11388.7011 | 8800.82 | 7656.7134 | 455.5056 | 352 | 306.24 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54435.8572 | 42351.32 | 36635.1846 | 17770.4447 | 13994.68 | 11984.7221 | 72206.3018 | 56346 | 48619.9067 | 0 | 0 | 0 | 72206.3018 | 56346 | 48619.9067
77 | Other services | 1.2 | Implementation of the school development grants (including monitoring and training) |  | 0 | 3191.76 |  | 3191.76 | 0 |  | 0 | 0 |  | 0 | 2411.791 | 1638 | 1520.5407 | 2227.5478 | 1553.76 | 1426.8045 | 0 | 0 | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 |  |  | 0 | 4639.3389 | 3191.76 | 2947.3452 | 0 | 0 | 0 | 4639.3389 | 3191.76 | 2947.3452 | 0 |  | 0 | 4639.3389 | 3191.76 | 2947.3452
78 | Primary Schools | [9 empty] | 0 |  |  | 0 |  |  | 0 | [8 empty] | 0 | [42 empty] | 0 | 0 | 0
79 | C1.3/SDG/01 | 1.3 | Gjon Serreçi |  | 11349.13 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77 | 0 | 0 | 0 | 12698 | 10000 | 8563.77
80 | C1.3/SDG/02 | 1.3 | Ahemet Hoxha |  | 11349.06 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77 | 0 | 0 | 0 | 12698 | 10000 | 8563.77
81 | C1.3/SDG/03 | 1.3 | Naim Frasheri |  | 11349.06 | 9605 |  | 9605 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12196.429 | 9605 | 8225.5011 | 12196.429 | 9605 | 8225.5011 | 0 | 0 | 0 | 12196.429 | 9605 | 8225.5011
82 | C1.3/SDG/04 | 1.3 | Dituria - Ferizaj |  | 11349.06 | 6180 |  | 6180 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7847.364 | 6180 | 5292.4099 | 7847.364 | 6180 | 5292.4099 | 0 | 0 | 0 | 7847.364 | 6180 | 5292.4099
83 | C1.3/SDG/05 | 1.3 | Ali Hadri |  | 11349.06 | 6140 |  | 6140 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7796.572 | 6140 | 5258.1548 | 7796.572 | 6140 | 5258.1548 | 0 | 0 | 0 | 7796.572 | 6140 | 5258.1548
84 | C1.3/SDG/06 | 1.3 | Ismail Luma |  | 11349.06 | 8725 |  | 8725 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 11079.005 | 8725 | 7471.8893 | 11079.005 | 8725 | 7471.8893 | 0 | 0 | 0 | 11079.005 | 8725 | 7471.8893
85 | C1.3/SDG/07 | 1.3 | Zenel Hajdini |  | 11349.06 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77 | 0 | 0 | 0 | 12698 | 10000 | 8563.77
86 | C1.3/SDG/08 | 1.3 | Haradin Bajrami (Jeronim de Rada) |  | 11349.06 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77 | 0 | 0 | 0 | 12698 | 10000 | 8563.77
87 | C1.3/SDG/09 | 1.3 | Bajram Curri |  | 11349.06 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1339.3417 | 1035 | 900.45 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1339.3417 | 1035 | 900.45 | 11383.757 | 8965 | 7677.4198 | 12723.0987 | 10000 | 8577.8698 | 0 | 0 | 0 | 12723.0987 | 10000 | 8577.8698
88 | C1.3/SDG/11 | 1.3 | Dituria - Kaqanik |  | 11349.06 | 5825 |  | 5825 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7396.585 | 5825 | 4988.396 | 7396.585 | 5825 | 4988.396 | 0 | 0 | 0 | 7396.585 | 5825 | 4988.396
89 | C1.3/SDG/14 | 1.3 | Sh. F. Kabashi |  | 11349.06 | 5100 |  | 5100 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6475.98 | 5100 | 4367.5227 | 6475.98 | 5100 | 4367.5227 | 0 | 0 | 0 | 6475.98 | 5100 | 4367.5227
90 | C1.3/SDG/15 | 1.3 | Ardhmeria |  | 11349.06 | 5335 |  | 5335 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6774.383 | 5335 | 4568.7713 | 6774.383 | 5335 | 4568.7713 | 0 | 0 | 0 | 6774.383 | 5335 | 4568.7713
91 | C1.3/SDG/16 | 1.3 | Zenun Cocaj |  | 11349.06 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77 | 0 | 0 | 0 | 12698 | 10000 | 8563.77
92 | C1.3/SDG/17 | 1.3 | Izvor |  | 11349.06 | 5435 |  | 5435 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6901.363 | 5435 | 4654.409 | 6901.363 | 5435 | 4654.409 | 0 | 0 | 0 | 6901.363 | 5435 | 4654.409
93 | C1.3/SDG/18 | 1.3 | Zef Lush Marku |  | 11349.06 | 8130 |  | 8130 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 10323.474 | 8130 | 6962.345 | 10323.474 | 8130 | 6962.345 | 0 | 0 | 0 | 10323.474 | 8130 | 6962.345
94 | C1.3/SDG/19 | 1.3 | Nazmi Buduri |  | 11349.06 | 8040 |  | 8040 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 10209.192 | 8040 | 6885.2711 | 10209.192 | 8040 | 6885.2711 | 0 | 0 | 0 | 10209.192 | 8040 | 6885.2711
95 | C1.3/SDG/22 | 1.3 | Drita |  | 11349.06 | 5210 |  | 5210 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 8724.7439 | 6742.2 | 5865.714 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 8724.7439 | 6742.2 | 5865.714 | -1945.5876 | -1532.2 | -1312.1408 | 6779.1563 | 5210 | 4553.5732 | 0 | 0 | 0 | 6779.1563 | 5210 | 4553.5732
96 | C1.3/SDG/23 | 1.3 | K. I Manastirit |  | 11349.06 | 8940 |  | 8940 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 11352.012 | 8940 | 7656.0104 | 11352.012 | 8940 | 7656.0104 | 0 | 0 | 0 | 11352.012 | 8940 | 7656.0104
97 | C1.3/SDG/24 | 1.3 | Ilmi Bahtijari |  | 11349.06 | 9395 |  | 9395 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 11929.771 | 9395 | 8045.6619 | 11929.771 | 9395 | 8045.6619 | 0 | 0 | 0 | 11929.771 | 9395 | 8045.6619
98 | C1.3/SDG/25 | 1.3 | Fetah Sylejmani |  | 11349.06 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77 | 0 | 0 | 0 | 12698 | 10000 | 8563.77
99 | C1.3/SDG/26 | 1.3 | Haxhi Ymer Lutfiu |  | 11349.06 | 4437 |  | 4437 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 5634.1026 | 4437 | 3799.7447 | 5634.1026 | 4437 | 3799.7447 | 0 | 0 | 0 | 5634.1026 | 4437 | 3799.7447
100 | C1.3/SDG/27 | 1.3 | Vellazerimi |  | 11349.06 | 7815 |  | 7815 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9923.487 | 7815 | 6692.5863 | 9923.487 | 7815 | 6692.5863 | 0 | 0 | 0 | 9923.487 | 7815 | 6692.5863
101 | C1.3/SDG/28 | 1.3 | Zef Lush Marku - Bregoc |  | 11349.06 | 9615 |  | 9615 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12209.127 | 9615 | 8234.0649 | 12209.127 | 9615 | 8234.0649 | 0 | 0 | 0 | 12209.127 | 9615 | 8234.0649
102 | C1.3/SDG/29 | 1.3 | Nimon Ferizi |  | 11349.06 | 5385 |  | 5385 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6837.873 | 5385 | 4611.5901 | 6837.873 | 5385 | 4611.5901 | 0 | 0 | 0 | 6837.873 | 5385 | 4611.5901
103 | C1.3/SDG/30 | 1.3 | Fehmi Agani |  | 11349.06 | 8075 |  | 8075 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 10253.635 | 8075 | 6915.2443 | 10253.635 | 8075 | 6915.2443 | 0 | 0 | 0 | 10253.635 | 8075 | 6915.2443
104 | C1.3/SDG/31 | 1.3 | Ganimer Terbeshi |  | 11349.06 | 6085 |  | 6085 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7726.733 | 6085 | 5211.054 | 7726.733 | 6085 | 5211.054 | 0 | 0 | 0 | 7726.733 | 6085 | 5211.054
105 | C1.3/SDG/32 | 1.3 | 7 Shtatori |  | 11349.06 | 5255 |  | 5255 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6672.799 | 5255 | 4500.2611 | 6672.799 | 5255 | 4500.2611 | 0 | 0 | 0 | 6672.799 | 5255 | 4500.2611
106 | C1.3/SDG/33 | 1.3 | Fan Noli |  | 11349.06 | 5510 |  | 5510 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6996.598 | 5510 | 4718.6373 | 6996.598 | 5510 | 4718.6373 | 0 | 0 | 0 | 6996.598 | 5510 | 4718.6373
107 | C1.3/SDG/34 | 1.3 | Rilindja |  | 11349.06 | 4435 |  | 4435 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 5631.563 | 4435 | 3798.032 | 5631.563 | 4435 | 3798.032 | 0 | 0 | 0 | 5631.563 | 4435 | 3798.032
108 | C1.3/SDG/35 | 1.3 | Mustafe Ibishi |  | 11349.06 | 8185 |  | 8185 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 10393.313 | 8185 | 7009.4457 | 10393.313 | 8185 | 7009.4457 | 0 | 0 | 0 | 10393.313 | 8185 | 7009.4457
109 | C1.3/SDG/36 | 1.3 | Jusf Gervalla |  | 11349.06 | 6695 |  | 6695 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 8501.311 | 6695 | 5733.444 | 8501.311 | 6695 | 5733.444 | 0 | 0 | 0 | 8501.311 | 6695 | 5733.444
110 | C1.3SDG/38 | 1.3 | 7 Shtatori - Rahovec |  | 11349.06 | 5755 |  | 5755 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7307.699 | 5755 | 4928.4496 | 7307.699 | 5755 | 4928.4496 | 0 | 0 | 0 | 7307.699 | 5755 | 4928.4496
111 | C1.3SDG/40 | 1.3 | Rifat Berisha |  | 11349.06 | 6290 |  | 6290 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7987.042 | 6290 | 5386.6113 | 7987.042 | 6290 | 5386.6113 | 0 | 0 | 0 | 7987.042 | 6290 | 5386.6113
112 | C1.3SDG/41 | 1.3 | Vesel Pagarusha |  | 11349.06 | 6285 |  | 6285 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 6398.8314 | 4944.81 | 4301.9847 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 6398.8314 | 4944.81 | 4301.9847 | 1701.7733 | 1340.19 | 1147.7079 | 8100.6046 | 6285 | 5449.6926 | 0 | 0 | 0 | 8100.6046 | 6285 | 5449.6926
113 | C1.3SDG/42 | 1.3 | Ismet Jashari Kumanova |  | 11349.06 | 5265 |  | 5265 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6685.497 | 5265 | 4508.8249 | 6685.497 | 5265 | 4508.8249 | 0 | 0 | 0 | 6685.497 | 5265 | 4508.8249
114 | C1.3SDG/43 | 1.3 | Tafil Kelmendi |  | 11349.06 | 5685 |  | 5685 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7218.813 | 5685 | 4868.5032 | 7218.813 | 5685 | 4868.5032 | 0 | 0 | 0 | 7218.813 | 5685 | 4868.5032
115 | C1.3SDG/44 | 1.3 | Bajram Curri - Drenoc |  | 11349.06 | 6450 |  | 6450 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 8190.21 | 6450 | 5523.6317 | 8190.21 | 6450 | 5523.6317 | 0 | 0 | 0 | 8190.21 | 6450 | 5523.6317
116 | C1.3/SDG/46 | 1.3 | Xhemajl Kada |  | 11349.06 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77 | 0 | 0 | 0 | 12698 | 10000 | 8563.77
117 | C1.3/SDG/47 | 1.3 | 7 Shtatori - Vitomirice |  | 11349.06 | 9340 |  | 9340 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 11859.932 | 9340 | 7998.5612 | 11859.932 | 9340 | 7998.5612 | 0 | 0 | 0 | 11859.932 | 9340 | 7998.5612
118 | C1.3/SDG/48 | 1.3 | Deshmoret e Kombit |  | 11349.06 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77 | 0 | 0 | 0 | 12698 | 10000 | 8563.77
119 | C1.3/SDG/49 | 1.3 | Skenderbeu |  | 11349.06 | 6900 |  | 6900 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 8761.62 | 6900 | 5909.0013 | 8761.62 | 6900 | 5909.0013 | 0 | 0 | 0 | 8761.62 | 6900 | 5909.0013
120 | C1.3/SDG/50 | 1.3 | Ndre Mjeda |  | 11349.06 | 8560 |  | 8560 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 10869.488 | 8560 | 7330.5871 | 10869.488 | 8560 | 7330.5871 | 0 | 0 | 0 | 10869.488 | 8560 | 7330.5871
121 | C1.3/SDG/51 | 1.3 | Avni Rrustemi |  | 11349.06 | 7450 |  | 7450 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9460.01 | 7450 | 6380.0087 | 9460.01 | 7450 | 6380.0087 | 0 | 0 | 0 | 9460.01 | 7450 | 6380.0087
122 | C1.3/SDG/52 | 1.3 | Fan Noli - Lluk I Bregut |  | 11349.06 | 6975 |  | 6975 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 8856.855 | 6975 | 5973.2296 | 8856.855 | 6975 | 5973.2296 | 0 | 0 | 0 | 8856.855 | 6975 | 5973.2296
123 | C1.3/SDG/53 | 1.3 | Emin Duraku |  | 11349.06 | 9000 |  | 9000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 11428.2 | 9000 | 7707.393 | 11428.2 | 9000 | 7707.393 | 0 | 0 | 0 | 11428.2 | 9000 | 7707.393
124 | C1.3/SDG/54 | 1.3 | Ali Krasniqi |  | 11349.06 | 8425 |  | 8425 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 10698.065 | 8425 | 7214.9762 | 10698.065 | 8425 | 7214.9762 | 0 | 0 | 0 | 10698.065 | 8425 | 7214.9762
125 | C1.3/SDG/55 | 1.3 | Azem Bejta |  | 11349.06 | 6730 |  | 6730 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 8545.754 | 6730 | 5763.4172 | 8545.754 | 6730 | 5763.4172 | 0 | 0 | 0 | 8545.754 | 6730 | 5763.4172
126 | C1.3/SDG/56 | 1.3 | Tre Deshmoret |  | 11349.06 | 8945 |  | 8945 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 11358.361 | 8945 | 7660.2923 | 11358.361 | 8945 | 7660.2923 | 0 | 0 | 0 | 11358.361 | 8945 | 7660.2923
127 | C1.3/SDG/57 | 1.3 | Ate Gjergj Fishta |  | 11349.06 | 4675 |  | 4675 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 5936.315 | 4675 | 4003.5625 | 5936.315 | 4675 | 4003.5625 | 0 | 0 | 0 | 5936.315 | 4675 | 4003.5625
128 | C1.3/SDG/58 | 1.3 | Drita - Gramqel |  | 11349.06 | 7365 |  | 7365 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9352.077 | 7365 | 6307.2166 | 9352.077 | 7365 | 6307.2166 | 0 | 0 | 0 | 9352.077 | 7365 | 6307.2166
129 | C1.3/SDG/59 | 1.3 | Heronjt e Dukagjinit |  | 11349.06 | 5265 |  | 5265 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6685.497 | 5265 | 4508.8249 | 6685.497 | 5265 | 4508.8249 | 0 | 0 | 0 | 6685.497 | 5265 | 4508.8249
130 | C1.3/SDG/60 | 1.3 | Faik Konica |  | 11349.06 | 4715 |  | 4715 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 5987.107 | 4715 | 4037.8176 | 5987.107 | 4715 | 4037.8176 | 0 | 0 | 0 | 5987.107 | 4715 | 4037.8176
131 | C1.3/SDG/61 | 1.3 | Esat Mekuli |  | 11349.06 | 4510 |  | 4510 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 5726.798 | 4510 | 3862.2603 | 5726.798 | 4510 | 3862.2603 | 0 | 0 | 0 | 5726.798 | 4510 | 3862.2603
132 | C1.3/SDG/62 | 1.3 | Rexhep Kadrijaj |  | 11349.06 | 5500 |  | 5500 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6983.9 | 5500 | 4710.0735 | 6983.9 | 5500 | 4710.0735 | 0 | 0 | 0 | 6983.9 | 5500 | 4710.0735
133 | C1.3/SDG/64 | 1.3 | Avni Rrustemi - Mramuer |  | 11349.06 | 7155 |  | 7155 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9085.419 | 7155 | 6127.3774 | 9085.419 | 7155 | 6127.3774 | 0 | 0 | 0 | 9085.419 | 7155 | 6127.3774
134 | C1.3/SDG/65 | 1.3 | Nexhmi Mustafa |  | 11349.06 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77 | 0 | 0 | 0 | 12698 | 10000 | 8563.77
135 | C1.3/SDG/66 | 1.3 | Tefik Canga |  | 11349.06 | 6565 |  | 6565 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 8336.237 | 6565 | 5622.115 | 8336.237 | 6565 | 5622.115 | 0 | 0 | 0 | 8336.237 | 6565 | 5622.115
136 | C1.3/SDG/67 | 1.3 | Pjeter Bogdani |  | 11349.06 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77 | 0 | 0 | 0 | 12698 | 10000 | 8563.77
137 | C1.3/SDG/68 | 1.3 | Sami Frasheri |  | 11349.06 | 7710 |  | 7710 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9790.158 | 7710 | 6602.6667 | 9790.158 | 7710 | 6602.6667 | 0 | 0 | 0 | 9790.158 | 7710 | 6602.6667
138 | C1.3/SDG/70 | 1.3 | Jahe Hasani |  | 11349.06 | 5370 |  | 5370 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6818.826 | 5370 | 4598.7445 | 6818.826 | 5370 | 4598.7445 | 0 | 0 | 0 | 6818.826 | 5370 | 4598.7445
139 | C1.3/SDG/71 | 1.3 | Luigj Gurakuqi |  | 11349.06 | 9680 |  | 9680 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12291.664 | 9680 | 8289.7294 | 12291.664 | 9680 | 8289.7294 | 0 | 0 | 0 | 12291.664 | 9680 | 8289.7294
140 | C1.3/SDG/72 | 1.3 | Drita - Majac |  | 11349.06 | 9790 |  | 9790 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12431.342 | 9790 | 8383.9308 | 12431.342 | 9790 | 8383.9308 | 0 | 0 | 0 | 12431.342 | 9790 | 8383.9308
141 | C1.3/SDG/73 | 1.3 | Laura Scotti |  | 11349.06 | 4805 |  | 4805 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6101.389 | 4805 | 4114.8915 | 6101.389 | 4805 | 4114.8915 | 0 | 0 | 0 | 6101.389 | 4805 | 4114.8915
142 | C1.3/SDG/74 | 1.3 | Lismir |  | 11349.06 | 4755 |  | 4755 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6037.899 | 4755 | 4072.0726 | 6037.899 | 4755 | 4072.0726 | 0 | 0 | 0 | 6037.899 | 4755 | 4072.0726
143 | C1.3/SDG/75 | 1.3 | Naim Frasheri - Bresnice |  | 11349.06 | 7180 |  | 7180 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9117.164 | 7180 | 6148.7869 | 9117.164 | 7180 | 6148.7869 | 0 | 0 | 0 | 9117.164 | 7180 | 6148.7869
144 | C1.3/SDG/76 | 1.3 | Migjeni |  | 11349.06 | 7450 |  | 7450 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9460.01 | 7450 | 6380.0087 | 9460.01 | 7450 | 6380.0087 | 0 | 0 | 0 | 9460.01 | 7450 | 6380.0087
145 | C1.3/SDG/77 | 1.3 | Knez Llazar |  | 11349.06 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77 | 0 | 0 | 0 | 12698 | 10000 | 8563.77
146 | C1.3/SDG/78 | 1.3 | Aferdita |  | 11349.06 | 7030 |  | 7030 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 8926.694 | 7030 | 6020.3303 | 8926.694 | 7030 | 6020.3303 | 0 | 0 | 0 | 8926.694 | 7030 | 6020.3303
147 | C1.3/SDG/79 | 1.3 | Bajram Curri - Shurdhan |  | 11349.06 | 4630 |  | 4630 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 5879.174 | 4630 | 3965.0255 | 5879.174 | 4630 | 3965.0255 | 0 | 0 | 0 | 5879.174 | 4630 | 3965.0255
148 | C1.3/SDG/80 | 1.3 | Fetah Qerimi |  | 11349.06 | 5690 |  | 5690 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7225.162 | 5690 | 4872.7851 | 7225.162 | 5690 | 4872.7851 | 0 | 0 | 0 | 7225.162 | 5690 | 4872.7851
149 | C1.3/SDG/81 | 1.3 | Liria |  | 11349.06 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77 | 0 | 0 | 0 | 12698 | 10000 | 8563.77
150 | C1.3/SDG/82 | 1.3 | Kadri Zeka |  | 11349.06 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77 | 0 | 0 | 0 | 12698 | 10000 | 8563.77
151 | C1.3/SDG/83 | 1.3 | Sadri Misini |  | 11349.06 | 6885 |  | 6885 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 8742.573 | 6885 | 5896.1556 | 8742.573 | 6885 | 5896.1556 | 0 | 0 | 0 | 8742.573 | 6885 | 5896.1556
152 | C1.3/SDG/84 | 1.3 | Asdreni |  | 11349.06 | 6095 |  | 6095 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7739.431 | 6095 | 5219.6178 | 7739.431 | 6095 | 5219.6178 | 0 | 0 | 0 | 7739.431 | 6095 | 5219.6178
153 | C1.3/SDG/86 | 1.3 | Hysen Terpeza |  | 11349.06 | 6010 |  | 6010 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7631.498 | 6010 | 5146.8258 | 7631.498 | 6010 | 5146.8258 | 0 | 0 | 0 | 7631.498 | 6010 | 5146.8258
154 | C1.3/SDG/87 | 1.3 | Vellezerit Gervalla |  | 11349.06 | 8470 |  | 8470 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 10755.206 | 8470 | 7253.5132 | 10755.206 | 8470 | 7253.5132 | 0 | 0 | 0 | 10755.206 | 8470 | 7253.5132
155 | C1.3/SDG/88 | 1.3 | Deshmoret e 5 Prillit |  | 11349.06 | 7095 |  | 7095 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9009.231 | 7095 | 6075.9948 | 9009.231 | 7095 | 6075.9948 | 0 | 0 | 0 | 9009.231 | 7095 | 6075.9948
156 | C1.3/SDG/90 | 1.3 | Gjon Serreci - Mogille |  | 11349.06 | 5980 |  | 5980 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7593.404 | 5980 | 5121.1345 | 7593.404 | 5980 | 5121.1345 | 0 | 0 | 0 | 7593.404 | 5980 | 5121.1345
157 | C1.3/SDG/91 | 1.3 | Deshmoret e Qendreses |  | 11349.06 | 5485 |  | 5485 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6964.853 | 5485 | 4697.2278 | 6964.853 | 5485 | 4697.2278 | 0 | 0 | 0 | 6964.853 | 5485 | 4697.2278
158 | C1.3/SDG/92 | 1.3 | Desjmoret e Drenices |  | 11349.06 | 5140 |  | 5140 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6526.772 | 5140 | 4401.7778 | 6526.772 | 5140 | 4401.7778 | 0 | 0 | 0 | 6526.772 | 5140 | 4401.7778
159 | C1.3/SDG/93 | 1.3 | Xheve Lladrovci |  | 11349.06 | 5435 |  | 5435 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6901.363 | 5435 | 4654.409 | 6901.363 | 5435 | 4654.409 | 0 | 0 | 0 | 6901.363 | 5435 | 4654.409
160 | C1.3/SDG/94 | 1.3 | Shote Galica |  | 11349.06 | 6480 |  | 6480 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 8228.304 | 6480 | 5549.323 | 8228.304 | 6480 | 5549.323 | 0 | 0 | 0 | 8228.304 | 6480 | 5549.323
161 | C1.3/SDG/96 | 1.3 | Abedin Rexha |  | 11349.06 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77 | 0 | 0 | 0 | 12698 | 10000 | 8563.77
162 | C1.3/SDG/98 | 1.3 | Habib Jusufi |  | 11349.06 | 5345 |  | 5345 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6787.081 | 5345 | 4577.3351 | 6787.081 | 5345 | 4577.3351 | 0 | 0 | 0 | 6787.081 | 5345 | 4577.3351
163 | C1.3/SDG/99 | 1.3 | Jusuf Rexha |  | 11349.06 | 6115 |  | 6115 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4833.2767 | 3735 | 3249.45 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4833.2767 | 3735 | 3249.45 | 3022.124 | 2380 | 2038.1773 | 7855.4008 | 6115 | 5287.6273 | 0 | 0 | 0 | 7855.4008 | 6115 | 5287.6273
164 | C1.3/SDG/100 | 1.3 | Sefedin Smakolli |  | 11349.06 | 5625 |  | 5625 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 6406.7768 | 4950.95 | 4307.3265 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 6406.7768 | 4950.95 | 4307.3265 | 855.9087 | 674.05 | 577.2409 | 7262.6855 | 5625 | 4884.5674 | 0 | 0 | 0 | 7262.6855 | 5625 | 4884.5674
165 | C1.3/SDG/101 | 1.3 | Trepca |  | 11349.06 | 7620 |  | 7620 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9675.876 | 7620 | 6525.5927 | 9675.876 | 7620 | 6525.5927 | 0 | 0 | 0 | 9675.876 | 7620 | 6525.5927
166 | C1.3/SDG/102 | 1.3 | Bedri Gjinaj |  | 11349.06 | 7165 |  | 7165 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9098.117 | 7165 | 6135.9412 | 9098.117 | 7165 | 6135.9412 | 0 | 0 | 0 | 9098.117 | 7165 | 6135.9412
167 | C1.3/SDG/104 | 1.3 | Azem Bejta - Dubovc |  | 11349.06 | 6090 |  | 6090 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7733.082 | 6090 | 5215.3359 | 7733.082 | 6090 | 5215.3359 | 0 | 0 | 0 | 7733.082 | 6090 | 5215.3359
168 | C1.3/SDG/105 | 1.3 | Bajram Curri - Dumnice |  | 11349.06 | 6255 |  | 6255 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7942.599 | 6255 | 5356.6381 | 7942.599 | 6255 | 5356.6381 | 0 | 0 | 0 | 7942.599 | 6255 | 5356.6381
169 | C1.3/SDG/106 | 1.3 | Gj.K. Skenderbeu |  | 11349.06 | 7350 |  | 7350 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9333.03 | 7350 | 6294.371 | 9333.03 | 7350 | 6294.371 | 0 | 0 | 0 | 9333.03 | 7350 | 6294.371
170 | C1.3/SDG/107 | 1.3 | Adem Voca |  | 11349.06 | 5075 |  | 5075 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6444.235 | 5075 | 4346.1133 | 6444.235 | 5075 | 4346.1133 | 0 | 0 | 0 | 6444.235 | 5075 | 4346.1133
171 | C1.3/SDG/108 | 1.3 | Emin Duraku - Novolane |  | 11349.06 | 6555 |  | 6555 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 8323.539 | 6555 | 5613.5512 | 8323.539 | 6555 | 5613.5512 | 0 | 0 | 0 | 8323.539 | 6555 | 5613.5512
| SECOND ROUND FOR PRIMARY SCHOOLS | [24 empty] | 0
172 | C1.3/SDG/111 | 1.3 | Dardania |  | 11349.06 | 5005 |  | 5005 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6355.349 | 5005 | 4286.1669 | 6355.349 | 5005 | 4286.1669 | 0 | 0 | 0 | 6355.349 | 5005 | 4286.1669
173 | C1.3/SDG/112 | 1.3 | K. Kristoforidhi |  | 11349.06 | 6585 |  | 6585 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 8361.633 | 6585 | 5639.2425 | 8361.633 | 6585 | 5639.2425 | 0 | 0 | 0 | 8361.633 | 6585 | 5639.2425
174 | C1.3/SDG/113 | 1.3 | Fehmi Agani |  | 11349.06 | 6180 |  | 6180 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7847.364 | 6180 | 5292.4099 | 7847.364 | 6180 | 5292.4099 | 0 | 0 | 0 | 7847.364 | 6180 | 5292.4099
175 | C1.3/SDG/114 | 1.3 | Shtjefen Gjeqovi |  | 11349.06 | 8125 |  | 8125 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 10317.125 | 8125 | 6958.0631 | 10317.125 | 8125 | 6958.0631 | 0 | 0 | 0 | 10317.125 | 8125 | 6958.0631
176 | C1.3/SDG/115 | 1.3 | Abdullah Shabani |  | 11349.06 | 8565 |  | 8565 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 647517.6319 | 500380.69 | 435331.2003 | 313323.7585 | 242126.47 | 210650.0289 | 79580.4258 | 61497.18 | 53502.5466 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1040421.8162 | 804004.34 | 699483.7758 | -1010048.8739 | -795439.34 | -681195.9557 | 30372.9422 | 8565 | 18287.8201 | 0 | 0 | 0 | 30372.9422 | 8565 | 18287.8201
177 | C1.3/SDG/116 | 1.3 | G. Luma |  | 11349.06 | 5110 |  | 5110 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6488.678 | 5110 | 4376.0865 | 6488.678 | 5110 | 4376.0865 | 0 | 0 | 0 | 6488.678 | 5110 | 4376.0865
178 | C1.3/SDG/117 | 1.3 | Sharski Odredi |  | 11349.06 | 8510 |  | 8510 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 10805.998 | 8510 | 7287.7683 | 10805.998 | 8510 | 7287.7683 | 0 | 0 | 0 | 10805.998 | 8510 | 7287.7683
179 | C1.3/SDG/118 | 1.3 | Sezai Surroi |  | 11349.06 | 7495 |  | 7495 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9517.151 | 7495 | 6418.5456 | 9517.151 | 7495 | 6418.5456 | 0 | 0 | 0 | 9517.151 | 7495 | 6418.5456
180 | C1.3/SDG/119 | 1.3 | Mic Sokoli |  | 11349.06 | 6165 |  | 6165 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7828.317 | 6165 | 5279.5642 | 7828.317 | 6165 | 5279.5642 | 0 | 0 | 0 | 7828.317 | 6165 | 5279.5642
181 | C1.3/SDG/120 | 1.3 | Haziz Tola |  | 11349.06 | 7275 |  | 7275 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9237.795 | 7275 | 6230.1427 | 9237.795 | 7275 | 6230.1427 | 0 | 0 | 0 | 9237.795 | 7275 | 6230.1427
182 | C1.3/SDG/121 | 1.3 | Luigj Gurakuqi |  | 11349.06 | 8030 |  | 8030 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 10196.494 | 8030 | 6876.7073 | 10196.494 | 8030 | 6876.7073 | 0 | 0 | 0 | 10196.494 | 8030 | 6876.7073
183 | C1.3/SDG/123 | 1.3 | Sadri Duhla |  | 11349.06 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77 | 0 | 0 | 0 | 12698 | 10000 | 8563.77
184 | C1.3/SDG/124 | 1.3 | Deshmoret e Tivarit |  | 11349.06 | 8000 |  | 8000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 10158.4 | 8000 | 6851.016 | 10158.4 | 8000 | 6851.016 | 0 | 0 | 0 | 10158.4 | 8000 | 6851.016
185 | C1.3/SDG/125 | 1.3 | Shaban Shabani |  | 11349.06 | 9445 |  | 9445 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 11993.261 | 9445 | 8088.4808 | 11993.261 | 9445 | 8088.4808 | 0 | 0 | 0 | 11993.261 | 9445 | 8088.4808
186 | C1.3/SDG/126 | 1.3 | Ferhat Binishi |  | 11349.06 | 6260 |  | 6260 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7948.948 | 6260 | 5360.92 | 7948.948 | 6260 | 5360.92 | 0 | 0 | 0 | 7948.948 | 6260 | 5360.92
187 | C1.3/SDG/127 | 1.3 | Ukshin Miftari |  | 11349.06 | 6050 |  | 6050 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7682.29 | 6050 | 5181.0809 | 7682.29 | 6050 | 5181.0809 | 0 | 0 | 0 | 7682.29 | 6050 | 5181.0809
188 | C1.3/SDG/128 | 1.3 | Qemajl Bakia |  | 11349.06 | 5850 |  | 5850 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7428.33 | 5850 | 5009.8055 | 7428.33 | 5850 | 5009.8055 | 0 | 0 | 0 | 7428.33 | 5850 | 5009.8055
189 | C1.3/SDG/130 | 1.3 | Pataq I ulet |  | 11349.06 | 5510 |  | 5510 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 6996.598 | 5510 | 4718.6373 | 6996.598 | 5510 | 4718.6373 | 0 | 0 | 0 | 6996.598 | 5510 | 4718.6373
190 | C1.3/SDG/131 | 1.3 | 4 Deshmoret |  | 11349.06 | 7836 |  | 7836 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9950.1528 | 7836 | 6710.5702 | 9950.1528 | 7836 | 6710.5702 | 0 | 0 | 0 | 9950.1528 | 7836 | 6710.5702
191 | C1.3/SDG/132 | 1.3 | Arfim Buqaj |  | 11349.06 | 5710 |  | 5710 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7250.558 | 5710 | 4889.9127 | 7250.558 | 5710 | 4889.9127 | 0 | 0 | 0 | 7250.558 | 5710 | 4889.9127
192 | C1.3/SDG/133 | 1.3 | Deshmoret e fshatit bubavec |  | 11349.06 | 6000 |  | 6000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7618.8 | 6000 | 5138.262 | 7618.8 | 6000 | 5138.262 | 0 | 0 | 0 | 7618.8 | 6000 | 5138.262
193 | C1.3/SDG/134 | 1.3 | Gjergj Kastrioti |  | 11349.06 | 7850 |  | 7850 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9967.93 | 7850 | 6722.5595 | 9967.93 | 7850 | 6722.5595 | 0 | 0 | 0 | 9967.93 | 7850 | 6722.5595
194 | C1.3/SDG/136 | 1.3 | Ramiz Sadiku |  | 11349.06 | 7505 |  | 7505 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9529.849 | 7505 | 6427.1094 | 9529.849 | 7505 | 6427.1094 | 0 | 0 | 0 | 9529.849 | 7505 | 6427.1094
195 | C1.3/SDG/137 | 1.3 | Jusuf Gervalla |  | 11349.06 | 7095 |  | 7095 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9009.231 | 7095 | 6075.9948 | 9009.231 | 7095 | 6075.9948 | 0 | 0 | 0 | 9009.231 | 7095 | 6075.9948
196 | C1.3/SDG/138 | 1.3 | Nene Tereza |  | 11349.06 | 8025 |  | 8025 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 10190.145 | 8025 | 6872.4254 | 10190.145 | 8025 | 6872.4254 | 0 | 0 | 0 | 10190.145 | 8025 | 6872.4254
197 | C1.3/SDG/139 | 1.3 | Shkendija |  | 11349.06 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77 | 0 | 0 | 0 | 12698 | 10000 | 8563.77
198 | C1.3/SDG/140 | 1.3 | Ganimete Terbeshi |  | 11349.06 | 6515 |  | 6515 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 8272.747 | 6515 | 5579.2962 | 8272.747 | 6515 | 5579.2962 | 0 | 0 | 0 | 8272.747 | 6515 | 5579.2962
199 | C1.3/SDG/142 | 1.3 | Mitrush Kuteli |  | 11349.06 | 7875 |  | 7875 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9999.675 | 7875 | 6743.9689 | 9999.675 | 7875 | 6743.9689 | 0 | 0 | 0 | 9999.675 | 7875 | 6743.9689
200 | C1.3/SDG/143 | 1.3 | Xhavit Ahmeti |  | 11349.06 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77 | 0 | 0 | 0 | 12698 | 10000 | 8563.77
201 | C1.3/SDG/144 | 1.3 | Zahir Pajaziti |  | 11349.06 | 8560 |  | 8560 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 10869.488 | 8560 | 7330.5871 | 10869.488 | 8560 | 7330.5871 | 0 | 0 | 0 | 10869.488 | 8560 | 7330.5871
202 | C1.3/SDG/145 | 1.3 | Kadri Kadriu |  | 11349.06 | 7750 |  | 7750 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9840.95 | 7750 | 6636.9218 | 9840.95 | 7750 | 6636.9218 | 0 | 0 | 0 | 9840.95 | 7750 | 6636.9218
203 | C1.3/SDG/147 | 1.3 | Daut Bogujevci |  |  | 6850 |  | 6850 | [17 empty] | 0
204 | C1.3/SDG/148 | 1.3 | Bajram Curri |  |  | 9705 |  | 9705 | [17 empty] | 0
205 | C1.3/SDG/149 | 1.3 | Fazli Grajcevci |  |  | 7685 |  | 7685 | [17 empty] | 0
206 | C1.3/SDG/150 | 1.3 | Gradjevinsko Saobracajna Skola |  |  | 7767 |  | 7767 | [17 empty] | 0
207 | C1.3/SDG/152 | 1.3 | Vehbi Ibrahimi |  |  | 5055 |  | 5055 | [17 empty] | 0
208 | C1.3/SDG/153 | 1.3 | Esat Berisha |  |  | 5600 |  | 5600 | [17 empty] | 0
209 | C1.3/SDG/154 | 1.3 | Fan Noli |  |  | 10000 |  | 10000 | [17 empty] | 0
210 | C1.3/SDG/155 | 1.3 | Kenan Halimi |  |  | 6590 |  | 6590 | [17 empty] | 0
211 | C1.3/SDG/156 | 1.3 | Halil Alidema |  |  | 9520 |  | 9520 | [17 empty] | 0
212 | C1.3/SDG/157 | 1.3 | Ali Gashi |  |  | 6090 |  | 6090 | [17 empty] | 0
213 | C1.3/SDG/158 | 1.3 | 28 Nentori |  |  | 5615 |  | 5615 | [17 empty] | 0
214 | C1.3/SDG/159 | 1.3 | Shaban Jashari |  |  | 10000 |  | 10000 | [17 empty] | 0
215 | C1.3/SDG/160 | 1.3 | Shote Galica |  |  | 9035 |  | 9035 | [17 empty] | 0
213 | C1.3/SDG/161 | 1.3 | Fazli Grajcevci |  |  | 10000 |  | 10000 | [17 empty] | 0
214 | C1.3/SDG/163 | 1.3 | Lumni Surdulli |  | 11349.06 | 5790 |  | 5790 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7352.142 | 5790 | 4958.4228 | 7352.142 | 5790 | 4958.4228 | 0 | 0 | 0 | 7352.142 | 5790 | 4958.4228
215 | C1.3/SDG/164 | 1.3 | SHMU 2 |  | 11349.06 | 10000 |  | 10000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77 | 0 | 0 | 0 | 12698 | 10000 | 8563.77
216 | C1.3/SDG/165 | 1.3 | Mihaliq |  |  | 5290 |  | 5290 | [17 empty] | 0
217 | Subtotal Primary Schools |  |  |  | 1429981.63 | 1027190 | 0 | 1027190 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27702.9706 | 21407.96 | 18624.9252 | 647517.6319 | 500380.69 | 435331.2003 | 313323.7585 | 242566.47 | 210650.0289 | 79580.4258 | 61497.18 | 53502.5466 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1068124.7868 | 828604.06 | 718108.701 | 110441.7439 | 86975.7 | 74483.989 | 1178566.5307 | 912388 | 792592.69 | 0 | 0 | 0 | 1178566.5307 | 912388 | 792592.69 | 0
218 | Secondary Schools | [24 empty] | 0
219 | C1.3/SDG/10 | 1.3 | F. Guri V.Caka |  | 17023.61 | 13661 |  | 13661 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 17346.7378 | 13661 | 11698.9662 | 17346.7378 | 13661 | 11698.9662 | 0 | 0 | 0 | 17346.7378 | 13661 | 11698.9662
220 | C1.3/SDG/12 | 1.3 | Dardania |  | 17023.59 | 8610 |  | 8610 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 10932.978 | 8610 | 7373.406 | 10932.978 | 8610 | 7373.406 | 0 | 0 | 0 | 10932.978 | 8610 | 7373.406
221 | C1.3/SDG/13 | 1.3 | K. I Manastirit - Firaje |  | 17023.59 | 6912 |  | 6912 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 8776.8576 | 6912 | 5919.2778 | 8776.8576 | 6912 | 5919.2778 | 0 | 0 | 0 | 8776.8576 | 6912 | 5919.2778
222 | C1.3/SDG/20 | 1.3 | Gjimnazi II Gjuhersor |  | 17023.59 | 14100 |  | 14100 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 17904.18 | 14100 | 12074.9157 | 17904.18 | 14100 | 12074.9157 | 0 | 0 | 0 | 17904.18 | 14100 | 12074.9157
223 | C1.3/SDG/21 | 1.3 | Jeta e Re |  | 17023.59 | 14999.9993 |  | 15000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 19047 | 15000 | 12845.655 | 19047 | 15000 | 12845.655 | 0 | 0 | 0 | 19047 | 15000 | 12845.655
224 | C1.3/SDG/37 | 1.3 | 12 Maji |  | 17023.59 | 10806 |  | 10806 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 13721.4588 | 10806 | 9254.0099 | 13721.4588 | 10806 | 9254.0099 | 0 | 0 | 0 | 13721.4588 | 10806 | 9254.0099
225 | C1.3/SDG/39 | 1.3 | Lasgush Poradeci |  | 17023.59 | 11995 |  | 11995 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 15231.251 | 11995 | 10272.2421 | 15231.251 | 11995 | 10272.2421 | 0 | 0 | 0 | 15231.251 | 11995 | 10272.2421
226 | C1.3/SDG/45 | 1.3 | Shaban Spahija |  | 17023.59 | 14999.9993 |  | 15000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 19047 | 15000 | 12845.655 | 19047 | 15000 | 12845.655 | 0 | 0 | 0 | 19047 | 15000 | 12845.655
227 | C1.3/SDG/63 | 1.3 | Gj. Sami Frasheri |  | 17023.59 | 14999.9993 |  | 15000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 19047 | 15000 | 12845.655 | 19047 | 15000 | 12845.655 | 0 | 0 | 0 | 19047 | 15000 | 12845.655
228 | C1.3/SDG/69 | 1.3 | Aleksander Xhuvani |  | 17023.59 | 14999.9993 |  | 15000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 19047 | 15000 | 12845.655 | 19047 | 15000 | 12845.655 | 0 | 0 | 0 | 19047 | 15000 | 12845.655
229 | C1.3/SDG/85 | 1.3 | Veliko Rapotovo |  | 17023.59 | 8740 |  | 8740 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 11098.052 | 8740 | 7484.735 | 11098.052 | 8740 | 7484.735 | 0 | 0 | 0 | 11098.052 | 8740 | 7484.735
230 | C1.3/SDG/89 | 1.3 | Shkolla e Mesme e Mjekesise |  | 17023.59 | 7641 |  | 7641 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9702.5418 | 7641 | 6543.5767 | 9702.5418 | 7641 | 6543.5767 | 0 | 0 | 0 | 9702.5418 | 7641 | 6543.5767
231 | C1.3/SDG/95 | 1.3 | Gj,K. Skenderbeu |  | 17023.59 | 14999.9993 |  | 15000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 19047 | 15000 | 12845.655 | 19047 | 15000 | 12845.655 | 0 | 0 | 0 | 19047 | 15000 | 12845.655
232 | C1.3/SDG/97 | 1.3 | Anton Cetta |  | 17023.59 | 14999.9993 |  | 15000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 19047 | 15000 | 12845.655 | 19047 | 15000 | 12845.655 | 0 | 0 | 0 | 19047 | 15000 | 12845.655
233 | C1.3/SDG/103 | 1.3 | Arkitekt Sinani |  | 17023.59 | 13549 |  | 13549 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 17204.5202 | 13549 | 11603.052 | 17204.5202 | 13549 | 11603.052 | 0 | 0 | 0 | 17204.5202 | 13549 | 11603.052
234 | C1.3/SDG/109 | 1.3 | Eqrem Qabej |  | 17023.59 | 14999.9993 |  | 15000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 19047 | 15000 | 12845.655 | 19047 | 15000 | 12845.655 | 0 | 0 | 0 | 19047 | 15000 | 12845.655
| SECOND ROUND FOR SECONDARY SCHOOLS | [24 empty] | 0
235 | C1.3/SDG/110 | 1.3 | Pjeter Bogdani |  | 17023.59 | 13885 |  | 13885 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 17631.173 | 13885 | 11890.7946 | 17631.173 | 13885 | 11890.7946 | 0 | 0 | 0 | 17631.173 | 13885 | 11890.7946
236 | C1.3/SDG/122 | 1.3 | Gani Cavderbashi |  | 17023.59 | 15000 |  | 15000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 19047 | 15000 | 12845.655 | 19047 | 15000 | 12845.655 | 0 | 0 | 0 | 19047 | 15000 | 12845.655
237 | C1.3/SDG/129 | 1.3 | Hysni Zajmi |  | 17023.59 | 15000 |  | 15000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 19047 | 15000 | 12845.655 | 19047 | 15000 | 12845.655 | 0 | 0 | 0 | 19047 | 15000 | 12845.655
238 | C1.3/SDG/135 | 1.3 | Odhise Paskali |  | 17023.59 | 9650 |  | 9650 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 12253.57 | 9650 | 8264.0381 | 12253.57 | 9650 | 8264.0381 | 0 | 0 | 0 | 12253.57 | 9650 | 8264.0381
239 | C1.3/SDG/141 | 1.3 | Eqrem Qabej |  | 17023.59 | 11634 |  | 11634 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 14772.8532 | 11634 | 9963.09 | 14772.8532 | 11634 | 9963.09 | 0 | 0 | 0 | 14772.8532 | 11634 | 9963.09
240 | C1.3/SDG/146 | 1.3 | Isa Boletini |  | 17023.59 | 15000 |  | 15000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 19047 | 15000 | 12845.655 | 19047 | 15000 | 12845.655 | 0 | 0 | 0 | 19047 | 15000 | 12845.655
241 | C1.3/SDG/151 | 1.3 | Arberia |  | 17023.59 | 12912.01 |  | 12912 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 16395.6576 | 12912 | 11057.5398 | 16395.6576 | 12912 | 11057.5398 | 0 | 0 | 0 | 16395.6576 | 12912 | 11057.5398
242 | C1.3/SDG/162 | 1.3 | Frang Bardhi |  | 17023.59 | 15000 |  | 15000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 19047 | 15000 | 12845.655 | 19047 | 15000 | 12845.655 | 0 | 0 | 0 | 19047 | 15000 | 12845.655
| SDG Round 3 | [52 empty] | 383113.8549 | 296058 | 257570.46
243 |  |  |  |  | 17023.59 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
244 | Subtotal Secondary Schools |  |  |  | 425589.77 | 309095.0048 | 0 | 309095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 383113.8549 | 296058 | 257570.46 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 392488.831 | 309095 | 264701.8488 | 392488.831 | 309095 | 264701.8488 | 0 | 0 | 0 | 392488.831 | 309095 | 264701.8488
245
246 | Subtotal Component 1 |  |  | 2550000 | #REF! | 2354678.9848 | 64099 | 2331698.98 | 52220.3399 | 40026.32 | 35326.2574 | 0 | 0 | 0 | 28417.3328 | 19300.01 | 17916.0256 | 58637.5701 | 40900.9 | 37558.9459 | 103318.6484 | 79841.31 | 69461.94 | 80412.0763 | 65458.16 | 54498.5585 | 53091.3686 | 40040.25 | 34591.4952 | 45404.7982 | 35087.36 | 30526.0032 | 69814.334 | 53950.26 | 46936.7262 | 49058.5225 | 37910.84 | 32982.4308 | 18350.4054 | 13828.6 | 12337.122 | 147641.1926 | 117992.34 | 102653.3358 | 661283.6452 | 511018.62 | 444586.1994 | 355530.985 | 275402.85 | 239217.6795 | 205564.2293 | 158853.39 | 138202.4493 | 467012.8879 | 424548.86 | 313976.4402 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2012188.9756 | 1567843.33 | 1349310.5091 | 875527.4048 | 689500.24 | 590472.147 | 2887716.3804 | 2149625.41 | 1939782.6561 | 97320.7108 | 52500 | 44959.7925 | 2971364.1363 | 2295422.17 | 1975339.6385 | 574660.3615
247
248 | COMPONENT 2. BUILDING INSTITUTIONS & MANAGEMENT CAPACITY IN PRIMARY & SECONDARY EDUCATION
249
250 | CONSULTANTS
251 | Blerim Saqipi | 2.1 | Consultant on licensing and delivery of in-service teacher training (national) |  | 19900 | 71533 |  | 71533 | 3120.7229 | 2392 | 2111.1211 | 8432.6976 | 5980 | 5447.3023 | 0 |  | 0 | 5143.9357 | 3588 | 3294.8297 | 5383.2481 | 4160 | 3619.2 | 6068.543 | 4940 | 4112.9002 | 0 |  | 0 | 0 |  | 0 | 7570.1925 | 5850 | 5089.5 | 7486.0792 | 5785 | 5032.95 | 10641.6202 | 8223.5 | 7154.445 | 6206.2638 | 4796 | 4172.52 | 5656.9525 | 4371.51 | 3803.2137 | 3785.0962 | 2925 | 2544.75 | 3280.4167 | 2535 | 2205.45 | 5551.4745 | 4290 | 3732.3 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 78327.243 | 59836.01 | 52320.482 | 14852.8379 | 11696.99 | 10017.0332 | 93180.0809 | 71533 | 62337.5152 | 0 |  | 0 | 93180.0809 | 71533 | 62337.5152 |  | Contracted
252 | Pilar Romaguera | 2.1 | Consultant to assist in teachers' professional development (international) |  | 62700 | 36805 | 52300 | 36805 | 23301.441 | 17860.3 | 15763.0668 | 0 |  | 0 | 27057.8071 | 18376.67 | 17058.8974 | 814.4135 | 568.07 | 521.6538 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 51173.6616 | 36805.04 | 33343.618 | 1126.3384 | -0.04 | -0.034255 | 52300 | 36805 | 33343.5837 | 0 | 0 | 0 | 52300 | 36805 | 33343.5837 |  | Completed
253 | Pasi Ikonen | 2.1 | Consultant to design teacher training career advancement system |  | 0 | 15416 | 24975.84 | 15416 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 10966.9197 | 7649.65 | 7024.608 | 0 |  | 0 | 9541.4817 | 7767.09 | 6466.653 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 20508.4014 | 15416.74 | 13491.2611 | 4467.4386 | -0.74 | -0.63372 | 24975.84 | 15416 | 13490.6274 | 0 |  | 0 | 24975.84 | 15416 | 13490.6274 |  | Completed
254 | Jorge Manzi | 2.1 | Consultant to assist in teachers' performance evaluation (international) |  | 60600 | 0 | 32733.76 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 32733.76 | 0 | 0 | 32733.76 | 0 | 0 | 0 | 0 | 0 | 32733.76 | 0 | 0 |  | Contracted
255 | Nicole Saginor | 2.1 | Consultant - teachers' performance evaluation |  | 0 | 92350 | 0 | 92350 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 6848.022 | 5291.93 | 4603.9791 | 24467.988 | 18908.07 | 16450.0209 | 0 |  | 0 | 43842.414 | 33880 | 29475.6 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 75158.424 | 58080 | 50529.6 | -75158.424 | 34270 | 29348.0398 | 0 | 92350 | 79877.6398 | 0 | 0 | 0 | 0 | 92350 | 79877.6398 |  | Contracted
256 | David Lynn | 2.1 | Consultant on Teacher Development Policies Study |  | 0 | 47830 | 0 | 47830 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 18311.7133 | 14150.7 | 12311.109 | 0 |  | 0 | 32924.1001 | 25442.68 | 22135.1316 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 51235.8134 | 39593.38 | 34446.2406 | -51235.8134 | 8236.62 | 7053.6519 | 0 | 47830 | 41499.8925 | 0 | 0 | 0 | 0 | 47830 | 41499.8925 |  | 0
257 | Edmond Krasniqi | 2.1 | Consultant for database population and logistical support on performance evaluation |  | 0 | 6000 | 0 | 6000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2882.4964 | 2227.5 | 1937.925 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2882.4964 | 2227.5 | 1937.925 | -2882.4964 | 3772.5 | 3230.6822 | 0 | 6000 | 5168.6072 | 0 | 0 | 0 | 0 | 6000 | 5168.6072 |  | 0
258 | Kreshnik Shatri | 2.1 | Consultant for database population and logistical support on performance evaluation |  |  | 6000 | 0 | 6000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2162.3575 | 1671 | 1453.77 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2162.3575 | 1671 | 1453.77 | -2162.3575 | 4329 | 3707.256 | 0 | 6000 | 5161.026 | 0 | 0 | 0 | 0 | 6000 | 5161.026 |  | 0
259 | Mentor Vokshi | 2.1 | Consultant for database population and logistical support on performance evaluation |  | 0 | 6000 | 0 | 6000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2135.1825 | 1650 | 1435.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2135.1825 | 1650 | 1435.5 | -2135.1825 | 4350 | 3725.24 | 0 | 6000 | 5160.74 | 0 | 0 | 0 | 0 | 6000 | 5160.74 |  | 0
260 | Armend Bajrami | 2.1 | Consultant for database population and logistical support on performance evaluation |  | 0 | 6000 | 0 | 6000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2863.0856 | 2212.5 | 1924.875 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2863.0856 | 2212.5 | 1924.875 | -2863.0856 | 3787.5 | 3243.5279 | 0 | 6000 | 5168.4029 | 0 |  | 0 | 0 | 6000 | 5168.4029 |  | 0
261 | Donika Rexhepi | 2.1 | Consultant for database population and logistical support on performance evaluation |  | 0 | 6000 | 0 | 6000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3396.8812 | 2625 | 2283.75 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3396.8812 | 2625 | 2283.75 | -3396.8812 | 3375 | 2890.2724 | 0 | 6000 | 5174.0224 | 0 |  | 0 | 0 | 6000 | 5174.0224 |  | 0
262 | Zahir ibishi | 2.1 | Consultant for database population and logistical support on performance evaluation |  | #REF! | 6000 | 0 | 6000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2911.6125 | 2250 | 1957.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2911.6125 | 2250 | 1957.5 | -2911.6125 | 3750 | 3211.4138 | 0 | 6000 | 5168.9137 | 0 |  | 0 | 0 | 6000 | 5168.9137 |  | 0
263 | Agim Ramadani | 2.1 | Consultant for database population and logistical support on performance evaluation |  | #REF! | 6000 | 0 | 6000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2935.8759 | 2268.75 | 1973.8125 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2935.8759 | 2268.75 | 1973.8125 | -2935.8759 | 3731.25 | 3195.3567 | 0 | 6000 | 5169.1692 | 0 |  | 0 | 0 | 6000 | 5169.1692 |  | 0
264 | Mirlind Bruqi | 2.1 | Consultant for the Managing the database process |  | 0 | 8000 | 0 | 8000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 9058.35 | 7000 | 6090 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 9058.35 | 7000 | 6090 | -9058.35 | 1000 | 856.377 | 0 | 8000 | 6946.377 | 0 | 0 | 0 | 0 | 8000 | 6946.377 |  | 0
265 | Camerron Harisson | 2.2 | Consultant to develop institutional capacities of curriculum unit and CACTI (international) |  | 0 | 44738.3 | 56000 | 44738.3 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 53109.9989 | 41041.69 | 35706.2703 | 0 |  | 0 | 0 |  | 0 | 4783.5982 | 3696.61 | 3216.0507 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 57893.5971 | 44738.3 | 38922.321 | 0 | 0 | 0 | 57893.5971 | 44738.3 | 38922.321 | 0 |  | 0 | 57893.5971 | 44738.3 | 38922.321 |  | Contracted
266 | Camerron Harisson | 2.2 | Consultant to develop institutional capacities of curriculum unit and CACTI (international) |  | 0 | 27059 |  | 27059 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 20320.4154 | 15702.96 | 13661.5752 | 14695.2059 | 11355.98 | 9879.7026 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 35015.6213 | 27058.94 | 23541.2778 | 0.076188 | 0.06 | 0.051383 | 35015.6975 | 27059 | 23541.3292 | 0 | 0 | 0 | 35015.6975 | 27059 | 23541.3292 |  | Contracted
267 | Kelvin Gregory | 2.3 | Consultant to build capacity in Assessment Unit and MEST experts (international) |  | 186100 | 41196 | 75600 | 41196 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 32769.2152 | 25322.99 | 22031.0013 | 0 |  | 0 | 20540.4556 | 15873 | 13809.51 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 53309.6709 | 41195.99 | 35840.5113 | 0.012698 | 0.01 | 0.0085638 | 53309.6836 | 41196 | 35840.5199 | 0 | 0 | 0 | 53309.6836 | 41196 | 35840.5199 |  | Contracted
268 | Kelvin Gregory | 2.3 | IC on Capacity Building for External Assessment in Kosovo |  | 0 | 43650 | 0 | 43650 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 55426.77 | 43650 | 37380.8561 | 55426.77 | 43650 | 37380.8561 | 63490 | 50000 | 42818.85 | 118916.77 | 93650 | 80199.7061
269 | Steven Bakker | 2.3 | Consultant to carry out the study on test administration (international) |  | 0 | 51800 |  | 51800 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 13406.358 | 10360 | 9013.2 | 40219.074 | 31080 | 27039.6 | 13406.358 | 10360 | 9013.2 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 67031.79 | 51800 | 45066 | 0 | 0 | 0 | 67031.79 | 51800 | 45066 | 0 | 0 | 0 | 67031.79 | 51800 | 45066 |  | Contracted
270 | Steven Bakker | 2.3 | Consultant - Matura reform |  | 0 | 53150 |  | 53150 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 8553.3858 | 6609.78 | 5750.5086 | 24993.9417 | 19314.51 | 16803.6237 | 15717.9972 | 12146.36 | 10567.3332 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 49265.3246 | 38070.65 | 33121.4655 | 19147.7586 | 15079.35 | 12913.6085 | 68413.0833 | 53150 | 46035.074 | 0 | 0 | 0 | 68413.0833 | 53150 | 46035.074 |  | Contracted
271 | Ivane Mindadze | 2.3 | Consultant Mother Tongue and Modern Foreign Language Exams |  | 0 | 10150 |  | 10150 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3943.8115 | 3047.65 | 2651.4555 | 3380.0586 | 2612 | 2272.44 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 7323.8701 | 5659.65 | 4923.8955 | 5701.8464 | 4490.35 | 3845.4325 | 13025.7165 | 10150 | 8769.328 | 0 | 0 | 0 | 13025.7165 | 10150 | 8769.328 |  | not planned
272 | David Tchankotadze | 2.3 | Consultant for Supporting the Item Bank Development in Kosovo External Assessment |  | 0 | 12520 |  | 12520 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4309.1865 | 3330 | 2897.1 | 3231.2428 | 2497 | 2172.39 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 7540.4293 | 5827 | 5069.49 | 8498.7714 | 6693 | 5731.7313 | 16039.2007 | 12520 | 10801.2213 | 0 | 0 | 0 | 16039.2007 | 12520 | 10801.2213 |  | not planned
273 | Steven Bakker | 2.3 | Supporting the Assessment Reform in Kosovo |  | 0 | 29000 |  | 28800 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 36570.24 | 28800 | 24663.6576 | 36570.24 | 28800 | 24663.6576 | 0 | 0 | 0 | 36570.24 | 28800 | 24663.6576 |  | not planned
274 | Mircea Enache | 2.4 | Consultant to work on the EMIS TOR and training needs assessment (international) |  | 31000 | 23560 |  | 23560 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 18292.6908 | 14136 | 12298.32 | 12195.1272 | 9424 | 8198.88 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 30487.818 | 23560 | 20497.2 | 0 | 0 | 0 | 30487.818 | 23560 | 20497.2 | 0 |  | 0 | 30487.818 | 23560 | 20497.2 |  | Contracted
275 | Mircea Enache | 2.4 | Consultant to work on the EMIS TOR and training needs assessment (international) |  | 0 | 31980 |  | 31980 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 8276.7438 | 6396 | 5564.52 | 8276.7438 | 6396 | 5564.52 | 8276.7438 | 6396 | 5564.52 | 8276.7438 | 6396 | 5564.52 | 8276.7438 | 6396 | 5564.52 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 41383.719 | 31980 | 27822.6 | 0 | 0 | 0 | 41383.719 | 31980 | 27822.6 | 0 |  | 0 | 41383.719 | 31980 | 27822.6 |  | Contracted
276 | Mircea Enache | 2.4 | Consultant to work on the EMIS TOR and training needs assessment (international) |  | 0 | 10000 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77
277 | Bersant Krasniqi | 2.4 | IT officer to support EMIS department (national) |  | 0 | 21413 |  | 21413 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1535.5625 | 1250 | 1040.7136 | 0 |  | 0 | 1941.075 | 1500 | 1305 | 2523.0093 | 1949.7 | 1696.239 | 2006.1657 | 1550.3 | 1348.761 | 2614.8868 | 2020.7 | 1758.009 | 2614.8868 | 2020.7 | 1758.009 | 2016.9063 | 1558.6 | 1355.982 | 3623.34 | 2800 | 2436 | 2614.8868 | 2020.7 | 1758.009 | 2717.505 | 2100 | 1827 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 24208.2243 | 18770.7 | 16283.7226 | 3355.1925 | 2642.3 | 2262.8049 | 27563.4169 | 21413 | 18546.5276 | 0 |  | 0 | 27563.4169 | 21413 | 18546.5276 |  | Contracted
278 | Kosova Education Center | 2.5 | Firm to draft project action plan (national) |  | 20300 | 12780 |  | 12780 | 16673.4275 | 12780 | 11279.3174 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 16673.4275 | 12780 | 11279.3174 | 0 | 0 | 0 | 16673.4275 | 12780 | 11279.3174 | 0 |  | 0 | 16673.4275 | 12780 | 11279.3174 |  | Completed
279 | Xhafer Ahmeti | 2.5 | Project coordinator (national) |  | 71300 | 13000 |  | 13000 | 10176.2703 | 7800 | 6884.0905 | 5499.5854 | 3900 | 3552.5885 | 1914.1199 | 1300 | 1206.7783 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 17589.9755 | 13000 | 11643.4572 | 0 | 0 | 0 | 17589.9755 | 13000 | 11643.4572 | 0 |  | 0 | 17589.9755 | 13000 | 11643.4572 |  | Completed
280 | Edita Alo | 2.5 | Project coordinator (national) |  | 0 | 82793 |  | 82793 | 0 |  | 0 | 0 |  | 0 | 5053.2765 | 3432 | 3185.8947 | 9462.0892 | 6600 | 6060.7234 | 8540.7301 | 6600 | 5742 | 5405.18 | 4400 | 3663.3119 | 0 |  | 0 | 8540.73 | 6600 | 5742 | 8540.73 | 6600 | 5742 | 11387.64 | 8800 | 7656 | 2846.91 | 2200 | 1914 | 0 |  | 0 | 6733.201 | 5203.2 | 4526.784 | 8924.804 | 6896.8 | 6000.216 | 8156.656 | 6303.2 | 5483.784 | 8540.73 | 6600 | 5742 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 92132.6766 | 70235.2 | 61458.7141 | 15945.8944 | 12557.8 | 10754.2111 | 108078.5711 | 82793 | 72212.9252 | 0 |  | 0 | 108078.5711 | 82793 | 72212.9252 |  | Contracted
281 | Edita Alo | 2.5 | Project coordinator (national) |  | #REF! | 13200 |  | 13200 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 16761.36 | 13200 | 11304.1764 | 16761.36 | 13200 | 11304.1764 | 0 |  | 0 | 16761.36 | 13200 | 11304.1764
281 | Gazmend Bajra | 2.5 | Financial manager (national) |  | 61100 | 56781 |  | 56781 | 3750.8689 | 2875 | 2537.4051 | 4865.0178 | 3450 | 3142.6744 | 5079.7797 | 3450 | 3202.6039 | 4946.0921 | 3450 | 3168.1054 | 5022.8551 | 3881.5 | 3376.905 | 3249.2748 | 2645.02 | 2202.1667 | 0 |  | 0 | 5134.1822 | 3967.53 | 3451.7511 | 5134.1822 | 3967.53 | 3451.7511 | 6845.5245 | 5290 | 4602.3 | 4914.7501 | 3797.96 | 3304.2252 | 4914.6725 | 3797.9 | 3304.173 | 5353.5366 | 4137.04 | 3599.2248 | 5353.6143 | 4137.1 | 3599.277 | 4914.7372 | 3797.95 | 3304.2165 | 3642.2202 | 2814.59 | 2448.6933 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 73121.3081 | 55459.12 | 48695.4726 | 1678.5232 | 1321.88 | 1132.0276 | 74799.8314 | 56781 | 49827.5002 | 0 |  | 0 | 74799.8314 | 56781 | 49827.5002 |  | Contracted
282 | Gazmend Bajra | 2.5 | Financial manager (national) |  | #REF! | 793 |  | 793 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1026.8287 | 793.5 | 690.345 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1026.8287 | 793.5 | 690.345 | -0.6349 | -0.5 | -0.42819 | 1026.1938 | 793 | 689.9168 | 0 |  | 0 | 1026.1938 | 793 | 689.9168
282 | Mirjeta Hysa | 2.5 | Financial manager (national) |  | #REF! | 9000 |  | 7200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 9142.56 | 7200 | 6165.9144 | 9142.56 | 7200 | 6165.9144 | 0 |  | 0 | 9142.56 | 7200 | 6165.9144
282 | Vlora Kuqi | 2.5 | Procurement Officer (national) |  | 49000 | 13800 |  | 13800 | 3750.8689 | 2875 | 2537.4051 | 4865.0178 | 3450 | 3142.6744 | 5079.7797 | 3450 | 3202.6039 | 4946.0921 | 3450 | 3168.1054 | 1488.1575 | 1150 | 1000.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 20129.9159 | 14375 | 13051.2889 | -730.135 | -575 | -492.4168 | 19399.7809 | 13800 | 12558.8722 | 0 |  | 0 | 19399.7809 | 13800 | 12558.8722 |  | Completed
283 | Luan Asllani | 2.5 | Procurement Officer (national) |  | 0 | 16200 |  | 16200 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1004.8721 | 818 | 681.043 | 0 |  | 0 | 3493.5468 | 2699.7 | 2348.739 | 3493.935 | 2700 | 2349 | 4658.58 | 3600 | 3132 | 3353.7894 | 2591.7 | 2254.779 | 3353.7894 | 2591.7 | 2254.779 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 19358.5127 | 15001.1 | 13020.34 | 1522.3632 | 1198.9 | 1026.7104 | 20880.8759 | 16200 | 14047.0504 | 0 | 0 | 0 | 20880.8759 | 16200 | 14047.0504 |  | Contracted
284 | Luan Asllani | 2.5 | Procurement Officer (national) |  | 0 | 11550 |  | 11550 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 3994.15 | 3086.55 | 2685.2985 | 4244.5487 | 3280.05 | 2853.6435 | 3907.9663 | 3019.95 | 2627.3565 | 4076.2575 | 3150 | 2740.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 16222.9225 | 12536.55 | 10906.7985 | -1252.7212 | -986.55 | -844.8587 | 14970.2013 | 11550 | 10061.9398 | 0 | 0 | 0 | 14970.2013 | 11550 | 10061.9398 |  | Contracted
285 | Luan Asllani | 2.5 | Procurement Officer (national) |  | 0 | 6300 |  | 6300 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 7999.74 | 6300 | 5395.1751 | 7999.74 | 6300 | 5395.1751 | 0 | 0 | 0 | 7999.74 | 6300 | 5395.1751
285 | Altin Ademi | 2.5 | Administrative assistant (national) |  | 40800 | 23450 |  | 23450 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1792.0623 | 1250 | 1147.8643 | 1941.075 | 1500 | 1305 | 1228.45 | 1000 | 832.5709 | 0 |  | 0 | 2717.505 | 2100 | 1827 | 2717.505 | 2100 | 1827 | 3623.34 | 2800 | 2436 | 2737.0452 | 2115.1 | 1840.137 | 2622.1335 | 2026.3 | 1762.881 | 2820.1232 | 2179.3 | 1895.991 | 2820.1232 | 2179.3 | 1895.991 | 2614.8868 | 2020.7 | 1758.009 | 2717.505 | 2100 | 1827 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 30351.7542 | 23370.7 | 20355.4442 | 100.6951 | 79.3 | 67.9107 | 30452.4493 | 23450 | 20423.3549 | 0 |  | 0 | 30452.4493 | 23450 | 20423.3549 |  | Contracted
286 | Altin Ademi | 2.5 | Administrative assistant (national) |  | #REF! | 4200 |  | 4200 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 5333.16 | 4200 | 3596.7834 | 5333.16 | 4200 | 3596.7834 | 0 |  | 0 | 5333.16 | 4200 | 3596.7834
286 | Vas Demetriou | 2.5 | Implementation adviser (international) |  | 55700 | 39465.78 | 54193 | 39465.78 | 4618.709 | 3540.19 | 3124.4857 | 26521.3275 | 18807.45 | 17132.0846 | 767.3707 | 521.17 | 483.7974 | 13487.0325 | 9407.48 | 8638.8083 | 9304.789 | 7190.44 | 6255.6828 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 54699.2287 | 39466.73 | 35634.8588 | -506.2287 | -0.95 | -0.81356 | 54193 | 39465.78 | 35634.0453 | 0 |  | 0 | 54193 | 39465.78 | 35634.0453 |  | Contracted
287 | Alexandar Najdovski | 2.5 | Procurement consultant (international) |  |  | 30900 |  | 30900 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 17993.7653 | 13905 | 12097.35 | 15994.458 | 12360 | 10753.2 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 33988.2232 | 26265 | 22850.55 | 5885.523 | 4635 | 3969.3074 | 39873.7462 | 30900 | 26819.8574 | 0 |  | 0 | 39873.7462 | 30900 | 26819.8574 |  | Contracted
288 | Ernest & Young , KPMG | 2.5 | Firm to audit project accounts (external) |  | 64600 | 2700 |  | 2700 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1294.05 | 1000 | 870 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2199.885 | 1700 | 1479 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3493.935 | 2700 | 2349 | 0 | 0 | 0 | 3493.935 | 2700 | 2349 | 0 | 0 | 0 | 3493.935 | 2700 | 2349
289 | KPMG | 2.5 | Firm to audit project accounts (external) |  | 0 | 3400 |  | 3400 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2199.885 | 1700 | 1479 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2199.885 | 1700 | 1479 | 2158.66 | 1700 | 1455.8409 | 4358.545 | 3400 | 2934.8409 | 0 | 0 | 0 | 4358.545 | 3400 | 2934.8409
290 | Ficadex Albania LTD | 2.5 | Firm to audit project accounts (external) |  | 0 | 25600 |  | 1688 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 2143.4224 | 1688 | 1445.5644 | 2143.4224 | 1688 | 1445.5644 | 32506.88 | 25600 | 21923.2512 | 34650.3024 | 27288 | 23368.8156
291 | GOODS | [7 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  | 0
292 | Hardsoft Integration | 2.1 | Developing a sofware for teacher licencing |  | 0 | 37000 |  | 37000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 49060.1492 | 37000 | 31964.9683 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 49060.1492 | 37000 | 31964.9683 | 0 | 0 | 0 | 49060.1492 | 37000 | 31964.9683 | 0 |  | 0 | 49060.1492 | 37000 | 31964.9683 |  | Contracted
293 | ? | 2.1 | Teacher license production support hardware and software |  | 0 | 29000 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
294 | SI Consulting | 2.1 | Computers for 7 regional +1 main offices for licensing |  | 0 | 6680 |  | 6680 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 8644.254 | 6680 | 5811.6 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 8644.254 | 6680 | 5811.6 | 0 | 0 | 0 | 8644.254 | 6680 | 5811.6 | 0 | 0 | 0 | 8644.254 | 6680 | 5811.6
294 | Comtrade Computers | 2.3 | Software (assessment analysis) Software upgrades (for assessment) and specialized equipment (optical readers) |  | 0 | 70240 |  | 70240 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 93134.09 | 70239.52 | 60681.19 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 93134.09 | 70239.52 | 60681.19 | 0.6095 | 0.48 | 0.41106 | 93134.6995 | 70240 | 60681.6011 | 0 |  | 0 | 93134.6995 | 70240 | 60681.6011 |  | Contracted
295 | ? | 2.3 | Printing of brochures for the parents and publication of test models |  | 41800 | 20000 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25396 | 20000 | 17127.54 | 25396 | 20000 | 17127.54
296 | Illir Kosova | 2.3 | IT Equipment for MEDs |  | 6400 | 32967 |  | 32967 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 42660.9463 | 32967 | 28681.29 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 42660.9463 | 32967 | 28681.29 | 0 | 0 | 0 | 42660.9463 | 32967 | 28681.29 | 0 |  | 0 | 42660.9463 | 32967 | 28681.29 |  | Contracted
279 | Abellardo | 2.3 | Development of the Item Bank Software |  | 0 | 30000 |  | 37128 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 47145.1344 | 37128 | 31795.5653 | 47145.1344 | 37128 | 31795.5653 | 0 |  | 0 | 47145.1344 | 37128 | 31795.5653
280 | SI Consulting | 2.3 | Hardware Support for Item Bank Database Application |  | 0 | 20000 |  | 21066 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 26749.6068 | 21066 | 18040.4379 | 26749.6068 | 21066 | 18040.4379 | 0 |  | 0 | 26749.6068 | 21066 | 18040.4379
280 | Illir Kosova | 2.4 | IT Equipment for EMIS |  | 0 | 27940 |  | 27940 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 36155.757 | 27940 | 24307.8 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 36155.757 | 27940 | 24307.8 | 0 | 0 | 0 | 36155.757 | 27940 | 24307.8 | 0 |  | 0 | 36155.757 | 27940 | 24307.8 |  | Contracted
281 | Neocom & Edusoft | 2.4 | EMIS Upgrade |  |  | 135000 |  | 135000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 42960.7793 | 32400 | 27990.9452 | 0 |  | 0 | 0 |  | 0 | 13975.74 | 10800 | 9396 | 0 |  | 0 | 65685.978 | 50760 | 44161.2 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 53107.812 | 41040 | 35704.8 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 175730.3093 | 135000 | 117252.9452 | 0 | 0 | 0 | 175730.3093 | 135000 | 117252.9452 | 0 |  | 0 | 175730.3093 | 135000 | 117252.9452
282 | Hardsoft Systems | 2.4 | USB for EMIS |  |  | 8950 |  | 8950 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 11581.7475 | 8950 | 7786.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 11581.7475 | 8950 | 7786.5 | 0 | 0 | 0 | 11581.7475 | 8950 | 7786.5 | 0 | 0 | 0 | 11581.7475 | 8950 | 7786.5
283 | SI Consulting | 2.4 | Backup software for three servers of EMIS |  |  | 8850 |  | 8850 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 11452.3425 | 8850 | 7699.5 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 11452.3425 | 8850 | 7699.5 | 0 | 0 | 0 | 11452.3425 | 8850 | 7699.5 | 0 | 0 | 0 | 11452.3425 | 8850 | 7699.5
283 | SM Commerce | 2.5 | Furniture for PST |  |  | 6088 |  | 6088 | 0 |  | 0 | 0 |  | 0 | 8963.9706 | 6088 | 5651.4356 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 8963.9706 | 6088 | 5651.4356 | 0 | 0 | 0 | 8963.9706 | 6088 | 5651.4356 | 0 |  | 0 | 8963.9706 | 6088 | 5651.4356 |  | Completed
284 | Comtrade Computers | 2.5 | IT Equipment for PCT |  |  | 16610.38 |  | 16610.38 | 0 |  | 0 | 0 |  | 0 | 24457.1219 | 16610.38 | 15419.2663 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 24457.1219 | 16610.38 | 15419.2663 | 0 | 0 | 0 | 24457.1219 | 16610.38 | 15419.2663 | 0 |  | 0 | 24457.1219 | 16610.38 | 15419.2663 |  | Contracted
285 | Comtrade Computers | 2.5 | IT Equipment for PCT |  |  | 3521.42 |  | 3521.42 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4556.8936 | 3521.42 | 3063.6354 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4556.8936 | 3521.42 | 3063.6354 | 0 | 0 | 0 | 4556.8936 | 3521.42 | 3063.6354 | 0 |  | 0 | 4556.8936 | 3521.42 | 3063.6354 |  | Contracted+C3.2
286 | Codex | 2.5 | Office Renovation |  |  | 996.8 |  | 996.8 | 0 |  | 0 | 1405.6376 | 996.8 | 908.0052 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1405.6376 | 996.8 | 908.0052 | 0 | 0 | 0 |  | 996.8 | [5 empty] | 996.8
287 | TRAINING |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  | 0
288 | Study visit - U.S. | 2.1 | Performance evaluation of teachers |  | 25396 | 26998 |  | 26998 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 34936.7619 | 26998 | 23488.26 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 34936.7619 | 26998 | 23488.26 | 0 | 0 | 0 | 34936.7619 | 26998 | 23488.26 | 0 | 0 | 0 | 34936.7619 | 26998 | 23488.26
289 | Workshops | 2.1 | Performance evaluation of teachers and licencing |  | 0 | 8464.7 |  | 8464.7 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2199.7556 | 1699.9 | 1478.913 | 7322.7904 | 5961 | 4962.9551 | 0 |  | 0 | 1040.1574 | 803.8 | 699.306 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2285.4735 | 1766.14 | 1536.5418 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 12848.1769 | 10230.84 | 8677.7159 | -2242.6446 | -1766.14 | -1512.4817 | 10605.5323 | 8464.7 | 7165.2342 | 0 | 0 | 0 | 10605.5323 | 8464.7 | 7165.2342
290 | ? | 2.1 | Workshops - Teacher Performance/lincencing |  | 0 | 3000 |  | 682 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 866.0036 | 682 | 584.0491 | 866.0036 | 682 | 584.0491 | 2943.3964 | 2318 | 1985.0819 | 3809.4 | 3000 | 2569.131
291 | Workshops | 2.1 | Teacher licensing |  |  | 1727.8 |  | 1727.8 | 0 |  | 0 | 0 |  | 0 | 2544.0125 | 1727.8 | 1603.9012 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2544.0125 | 1727.8 | 1603.9012 |  | 0 |  | 2544.0125 | 1727.8 | 1603.9012 | 0 | 0 | 0 |  | 1727.8
292 | ? | 2.1 | Workshop - Teacher Licencing |  |  | 10000 |  | 1680 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 |  | 1680 |  |  | 1680 | 0 | 10564.736 | 8320 | 7125.0566 |  | 10000
293 | ? | 2.3 | Training on assessment S. Bakker |  | 0 | 3000 |  | 880 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 939.9332 | 726.35 | 631.9245 | 663.4594 | 512.7 | 446.049 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1603.3927 | 1239.05 | 1077.9735 | -455.9217 | -359.05 | -307.4822 | 1147.471 | 880 | 770.4913 | 3961.776 | 3120 | 2671.8962 | 5109.247 | 4000 | 3442.3876
294 | ? | 2.3 | Continuation on Training on assessment S. Bakker |  | 0 | 2000 |  | 880 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 476.081 | 367.9 | 320.073 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 476.081 | 367.9 | 320.073 | 650.2646 | 512.1 | 438.5507 | 1126.3456 | 880 | 758.6237 | 2844.352 | 2240 | 1918.2845 | 3970.6976 | 3120 | 2676.9081
294 | Study visit 1 | 2.3 | Assessment & examinations |  | 52300 | 9426.7 |  | 9426.7 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3738.1611 | 2888.73 | 2513.1951 | 8460.4989 | 6538 | 5688.06 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 314.5836 | 243.1 | 211.497 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 12513.2435 | 9669.83 | 8412.7521 | -308.7265 | -243.13 | -208.2109 | 12204.517 | 9426.7 | 8204.5412 | 0 |  | 0 | 12204.517 | 9426.7 | 8204.5412
295 | ? | 2.3 | Study visit on assessment |  | 0 | 10000 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12698 | 10000 | 8563.77 | 12698 | 10000 | 8563.77
295 | ? | 2.3 | Conference Vision for the Matura 2015 in Kosovo |  |  | 50800 |  | 50800 | [17 empty] | 0 | [21 empty] | 8960.5198 | 6924.4 | 6024.228 | [27 empty] | 31871.98 | 25100 | 21495.0627
296 | Conference - Germany | 2.3 | Participat​ion in the ECA education Conference |  | 0 | 5631 |  | 5631 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4701.6719 | 3633.3 | 3160.971 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4701.6719 | 3633.3 | 3160.971 | 2536.6795 | 1997.7 | 1710.7843 | 7238.3513 | 5631 | 4871.7553 | 0 | 0 | 0 | 7238.3513 | 5631 | 4871.7553
297 | Workshop | 2.3 | Workshop on the Test and Design, S.Bakker |  |  | 880 | [19 empty] | 0
298 | Study visit | 2.4 | EMIS |  | 29700 | 7980 |  | 7980 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 10133.004 | 7980 | 6833.8885 | 10133.004 | 7980 | 6833.8885 | 0 |  | 0 | 10133.004 | 7980 | 6833.8885
299 | Conferences | 2.5 | Conferences |  | 0 | 5426.5 |  | 5426.5 | 0 |  | 0 | 0 |  | 0 | 2053.9979 | 1395 | 1294.9659 | 0 |  | 0 | 3532.7565 | 2730 | 2375.1 | 1054.0101 | 858 | 714.3458 | 0 |  | 0 | 0 |  | 0 | 573.9112 | 443.5 | 385.845 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 7214.6757 | 5426.5 | 4770.2568 | 0 | 0 | 0 | 7214.6757 | 5426.5 | 4770.2568 | 0 |  | 0 | 7214.6757 | 5426.5 | 4770.2568
[54 empty] | 404.0024 | 312.2 | 271.614
300 | [5 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 567.3115 | 438.4 | 381.408 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 567.3115 | 438.4 | 381.408 | -556.6803 | -438.4 | -375.4357 | 10.6312 | 0 | 5.9723 | 0 |  | 0 | 10.6312 | 0 | 5.9723
301 | Training | 2.5 | Procurement training |  | 0 | 3221 |  | 3221 | 0 |  | 0 | 0 |  | 0 | 940.8635 | 639 | 593.1779 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1658.8298 | 1281.89 | 1115.2443 | 1682.265 | 1300 | 1131 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 4281.9583 | 3220.89 | 2839.4222 | 0.13968 | 0.11 | 0.094201 | 4282.098 | 3221 | 2839.5165 | 0 | 0 | 0 | 4282.098 | 3221 | 2839.5165
302 | ? | 2.5 | Staff Professional Development |  | 11216.86 | 9000 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11428.2 | 9000 | 7707.393 | 11428.2 | 9000 | 7707.393
303 | Training - Financial Management | 2.5 | Financial management training |  |  | 1164 |  | 1164 | [17 empty] | 0 | [12 empty] | 1237.1377 | 956.02 | 831.7374 | [9 empty] | 945.9635 | 731.01 | 635.9787 | [15 empty] | 2183.1012 | 1687.03 | 1467.7161 | -664.1435 | -523.03 | -447.9109 | 1518.9577 | 1164 | 1019.8052 | 0 | 0 | 0 | 1518.9577 | 1164 | 1019.8052
304 | OPEARATIONS |  |  |  |  | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  | 0
305 | For all local consultants | 2.5 | Pension contributions |  | 0 | 6163.7 |  | 6163.1 | 469.674 | 360 | 317.7273 | 760.0709 | 539 | 490.9859 | 856.6423 | 581.8 | 540.0797 | 1057.3168 | 737.5 | 677.2399 | 812.4822 | 627.86 | 546.2382 | 621.178 | 505.66 | 420.9978 | 0 |  | 0 | 1091.3888 | 843.39 | 733.7493 | 1091.3888 | 843.39 | 733.7493 | 1455.1592 | 1124.5 | 978.315 | 1009.1131 | 779.81 | 678.4347 | 785.566 | 607.06 | 528.1422 | 1315.9453 | 1016.92 | 884.7204 | 1545.7686 | 1194.52 | 1039.2324 | 772.8843 | 597.26 | 519.6162 | 1780.4705 | 1375.89 | 1197.0243 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 15425.0489 | 11734.56 | 10286.2526 | -7074.6399 | -5571.46 | -4771.2702 | 8350.409 | 6163.1 | 5514.9824 | 0 | 0 | 0 | 8350.409 | 6163.1 | 5514.9824
306 | For all local consultants | 2.5 | Pension contributions |  | 0 | 8191 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10400.9318 | 8191 | 7014.584 | 10400.9318 | 8191 | 7014.584
307 |  | 2.5 | Translation services |  | 0 | 35357.77 |  | 35357.77 | 3256.4065 | 2496 | 2202.9089 | 0 |  | 0 | 0 |  | 0 | 5567.78 | 3883.64 | 3566.3133 | 4371.301 | 3378 | 2938.86 | 0 |  | 0 | 0 |  | 0 | 14461.6946 | 11175.53 | 9722.7111 | 2008.7409 | 1552.29 | 1350.4923 | 16657.4128 | 12872.31 | 11198.9097 | 784.4531 | 606.2 | 527.394 | 988.0331 | 763.52 | 664.2624 | 621.144 | 480 | 417.6 | 7770.6926 | 6004.94 | 5224.2978 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 56487.6584 | 43212.43 | 37813.7496 | -9973.8473 | -7854.66 | -6726.5502 | 46513.8112 | 35357.77 | 31087.1994 | 0 | 0 | 0 | 46513.8112 | 35357.77 | 31087.1994
308 |  | 2.5 | Translation services |  | 0 | 41000 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 52061.8 | 41000 | 35111.457 | 52061.8 | 41000 | 35111.457
309 |  | 2.5 | Phone cards |  | 0 | 4919.52 |  | 4919.52 | 489.3742 | 375.1 | 331.0541 | 476.5743 | 337.96 | 307.8546 | 634.6044 | 431 | 400.0934 | 840.3482 | 586.16 | 538.2657 | 825.4486 | 637.88 | 554.9556 | 698.8898 | 568.92 | 473.6662 | 0 |  | 0 | 803.1392 | 620.64 | 539.9568 | 892.3769 | 689.6 | 599.952 | 870.0675 | 672.36 | 584.9532 | 870.0675 | 672.36 | 584.9532 | 870.0675 | 672.36 | 584.9532 | 870.0675 | 672.36 | 584.9532 | 895.9485 | 692.36 | 602.3532 | 870.0675 | 672.36 | 584.9532 | 853.3354 | 659.43 | 573.7041 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 11760.3767 | 8960.85 | 7846.6218 | -5131.6808 | -4041.33 | -3460.9021 | 6628.6959 | 4919.52 | 4385.7197 | 0 | 0 | 0 | 6628.6959 | 4919.52 | 4385.7197
310 |  | 2.5 | Phone cards |  | 0 | 5750 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7301.35 | 5750 | 4924.1678 | 7301.35 | 5750 | 4924.1678
311 |  | 2.5 | Fuel |  | 0 | 1108.98 |  | 1108.98 | 99.1534 | 76 | 67.0758 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 908.4231 | 702 | 610.74 | 228.504 | 186.01 | 154.8665 | 0 |  | 0 | 187.5984 | 144.97 | 126.1239 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1423.6789 | 1108.98 | 958.8062 | 0 | 0 | 0 | 1423.6789 | 1108.98 | 958.8062 | 0 | 0 | 0 | 1423.6789 | 1108.98 | 958.8062
312 |  | 2.5 | Fuel |  | 0 | 4500 |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 486.1358 | 375.67 | 326.8329 | 12.9405 | 10 | 8.7 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 499.0763 | 385.67 | 335.5329 | -489.7238 | -385.67 | -330.2789 | 9.3525 | 0 | 5.254 | 5714.1 | 4500 | 3853.6965 | 5723.4525 | 4500 | 3858.9505
313 |  | 2.5 | Vehicle Maintenance |  | 0 | 1628.53 |  | 1628.53 | [12 empty] | 2107.3993 | 1628.53 | 1416.8211 | 0 |  | 0 | [24 empty] | 0 |  | 0 | [15 empty] | 2107.3993 | 1628.53 | 1416.8211 | 0 | 0 | 0 | 2107.3993 | 1628.53 | 1416.8211 | 0 |  | 0 | 2107.3993 | 1628.53 | 1416.8211
314 |  | 2.5 | Advertisments |  | 0 | 4271.97 |  | 4271.97 | [6 empty] | 1785.653 | 1212.75 | 1125.7849 |  | 78 |  | 1285.9234 | 993.72 | 864.5364 | 1498.279 | 1219.65 | 1015.4451 | [7 empty] | 767.85 | [16 empty] | 0 |  | 0 |  | 351.99 | [13 empty] | 4569.8554 | 4623.96 | 3005.7664 | -446.9569 | -351.99 | -301.4361 | 4122.8985 | 4271.97 | 2704.3303 | 0 | 0 | 0 | 4122.8985 | 4271.97 | 2704.3303
315 |  | 2.5 | Advertisments |  | 0 | 680 | [8 empty] | 0 | 0 | 0 |  | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0 | [16 empty] | 529.8617 | 409.46 | 356.2302 | [15 empty] | 529.8617 | 409.46 | 356.2302 | -519.9323 | -409.46 | -350.6521 | 9.9294 | 0 | 5.5781 | 863.464 | 680 | 582.3364 | 873.3934 | 680 | 587.9144
316 |  | 2.5 | Hospitality |  | 0 | 977.25 |  | 977.25 | 485.4211 | 372.07 | 328.3799 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 435.4867 | 336.53 | 292.7811 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 347.6465 | 268.65 | 233.7255 | 1754.6153 | 1355.91 | 1179.6417 | 0 |  | 0 | 0 |  | 0 | 511.0203 | 394.9 | 343.563 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3534.19 | 2728.06 | 2378.0912 | -2223.1785 | -1750.81 | -1499.3534 | 1311.0115 | 977.25 | 878.7378 | 0 | 0 | 0 | 1311.0115 | 977.25 | 878.7378
317 |  | 2.5 | Other |  | 0 | 2710 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 671.3402 | 518.79 | 451.3473 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 671.3402 | 518.79 | 451.3473 | -658.7595 | -518.79 | -444.2798 | 12.5807 | 0 | 7.0675 | 3441.158 | 2710 | 2320.7817 | 3453.7387 | 2710 | 2327.8491
318 |  | 2.5 | Office supplies & consumables |  | 0 | 3546.55 |  | 3546.55 | 121.3325 | 93 | 82.0795 | [9 empty] | 2766.006 | 2137.48 | 1859.6076 |  |  | 0 |  |  |  |  | 468.3 |  |  |  |  | 1097.0568 | 847.77 | 737.5599 | 0 |  | 0 | 714.3156 | 552 | 480.24 | 1236.4777 | 955.51 | 831.2937 | 3459.5003 | 2673.39 | 2325.8493 | 389.2502 | 300.8 | 261.696 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 9783.9391 | 8028.25 | 6578.326 | -5690.8627 | -4481.7 | -3838.0248 | 4093.0765 | 3546.55 | 2740.3012 | 0 | 0 | 0 | 4093.0765 | 3546.55 | 2740.3012
319 |  | 2.5 | Office supplies & consumables |  | 0 | 3756 |  |  | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 |  |  | 0 |  |  |  |  | 0 |  |  |  |  | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4769.3688 | 3756 | 3216.552 | 4769.3688 | 3756 | 3216.552
320 | Subtotal Component 2 |  |  | 1470000 | #REF! | 1817187.65 | 295802.6 | 1640124.05 | 70313.6701 | 53894.66 | 47566.1173 | 52825.929 | 37461.21 | 34124.17 | 87188.9993 | 59215.57 | 54969.2807 | 59024.0821 | 41248.5 | 37806.5173 | 52219.8873 | 40353.84 | 35107.841 | 39457.0153 | 32119.35 | 26741.6358 | 185155.0185 | 139639.52 | 120637.1035 | 224768.6948 | 174162.28 | 151113.7626 | 148043.0598 | 115170.74 | 99530.5143 | 90055.9288 | 69592.31 | 60545.3097 | 86685.6014 | 66987.83 | 58279.4121 | 111727.6559 | 86339.52 | 75115.3824 | 68564.424 | 52984.37 | 46096.4019 | 173466.4061 | 134049.23 | 116622.8301 | 64106.577 | 49539.49 | 43099.3563 | 213425.6478 | 165280.43 | 143487.7428 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1717664.075 | 1310802.25 | 1144547.5358 | 144966.8891 | 278521.8 | 237080.9502 | 1861225.3264 | 1589324.05 | 1380720.4807 | 294955.493 | 232285 | 198923.5314 | 2111200.0909 | 1796509.05 | 1549419.9917 | -79419.9917
321 | [77 empty] | 0 |  | 0
322 | COMPONENT 3. CREATING CONDITIONS TO INTRODUCE EFFICIENT DESIGNS IN KOSOVO'S SCHOOLS | [76 empty] | 0 |  | 0
323
324 | WORKS | [68 empty] | 0
325 | Standard | 3.3 | Basic Education Model Primary School (Grades 0-9) |  | 0 | 1500000 |  | 2480942.47 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 3150300.7484 | 2480942.47 | 2124622.0696 | 3150300.7484 | 2480942.47 | 2124622.0696 | 1904700 | 1500000 | 1284565.5 | 5055000.7484 | 3980942.47 | 3409187.5696
326 | [8 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0
327 | GOODS | [7 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0
328 | ? | 3.3 | Equipment for the model Basic Education School (0-9) |  | 0 | 122840 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 155982.232 | 122840 | 105197.3507 | 155982.232 | 122840 | 105197.3507
329 | ? | 3.3 | Furniture for the model Basic Education School (0-9) |  | 0 | 200000 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 76822.9 | 60500 | 51810.8085 | 76822.9 | 60500 | 51810.8085
330 | Comtrade Computers | 3.1 | Autocad 2 Licence |  | 6081 | 3991 |  | 3991 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 5164.5535 | 3991 | 3472.17 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 5164.5535 | 3991 | 3472.17 | 0 | 0 | 0 | 5164.5535 | 3991 | 3472.17 | 0 |  | 0 | 5164.5535 | 3991 | 3472.17
331 | Comtrade Computers | 3.2 | Computers & Peripherals and Software |  | 0 | 7483.21 |  | 7483.21 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 9683.6479 | 7483.21 | 6510.3927 | -9683.6479 | -7483.21 | -6510.3927 | 9683.6479 | 7483.21 | 6510.3927 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 9683.6479 | 7483.21 | 6510.3927 | 0 | 0 | 0 | 9683.6479 | 7483.21 | 6510.3927 | 0 |  | 0 | 9683.6479 | 7483.21 | 6510.3927
332 | Trembelat | 3.1 | Design and Layout of the Guideline on School Facilities Design- Norms and Standards |  | 0 | 1000 |  | 2260 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 2869.748 | 2260 | 1935.412 | 2869.748 | 2260 | 1935.412 | 2869.748 | 2260 | 1935.412 | 5739.496 | 4520 | 3870.824
333 | Grafika Rezniqi | 3.1 | Printing of the Guideline on School Facilities Design- Norms and Standards |  | 0 | 2000 |  | 1829 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 2322.4642 | 1829 | 1566.3135 | 2322.4642 | 1829 | 1566.3135 | 2539.6 | 2000 | 1712.754 | 4862.0642 | 3829 | 3279.0675
333 | CONSULTANTS | [7 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0
334 | TELOS | 3.1 | Firm to assist in the development of school database, school mapping and investment planning (international) |  | 166700 | 129580 |  | 129580 | 0 |  | 0 | 0 |  | 0 | 20083.5346 | 13640 | 12661.8892 | 58664.9528 | 40920 | 37576.4853 | 97079.6321 | 75020 | 65267.4003 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 175828.1195 | 129580 | 115505.7749 | 0 | 0 | 0 | 175828.1195 | 129580 | 115505.7749 | 0 |  | 0 | 175828.1195 | 129580 | 115505.7749 |  | Completed
335 | CMC | 3.1 | Firm to carry out inventory taking for Area A & B (1100 school locations) (national) |  | 287400 | 202280 |  | 202280 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 24849.0865 | 20228 | 16841.244 | 53642.6323 | 40456 | 34950.6691 | 104704.1736 | 80912 | 70393.44 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 78528.1302 | 60684 | 52795.08 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 261724.0226 | 202280 | 174980.4331 | 0 | 0 | 0 | 261724.0226 | 202280 | 174980.4331 | 0 |  | 0 | 261724.0226 | 202280 | 174980.4331 |  | Contracted
336 | Merita Behluli | 3 | Task Manager for Priority 3 Activities (national) |  | 41200 | 16716 |  | 16716 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 5217.0519 | 3639 | 3341.6625 | 5240.9026 | 4050 | 3523.5 | 3316.815 | 2700 | 2247.9414 | 0 |  | 0 | 5357.367 | 4140 | 3601.8 | 2830.1003 | 2187.01 | 1902.6987 | 0 |  | 0 | 7686.657 | 5940 | 5167.8 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 6832.584 | 5280 | 4593.6 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 36481.4777 | 27936.01 | 24379.0026 | -14247.1687 | -11220.01 | -9608.5585 | 22234.309 | 16716 | 14770.4441 | 0 |  | 0 | 22234.309 | 16716 | 14770.4441 |  | Contracted
337 | Local staff | 3 | Pension contributions |  | 0 | 0 |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 260.8526 | 181.95 | 167.0831 | 262.0451 | 202.5 | 176.175 | 165.8407 | 135 | 112.3971 | 0 |  | 0 | 267.8683 | 207 | 180.09 | 141.5044 | 109.35 | 95.1345 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1098.1112 | 835.8 | 730.8797 | -1061.2988 | -835.8 | -715.7599 | 36.8123 | 0 | 15.1198 | 0 |  | 0 | 36.8123 | 0 | 15.1198
338 | Vas Demetriou | 3 | Implementation of Comp 3 (international) |  | 0 | 27194 |  | 27194 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 7747.2936 | 6306.56 | 5250.6583 | 0 |  | 0 | 0 |  | 0 | 16050.2057 | 12403.08 | 10790.6796 | 0 |  | 0 | 10979.4837 | 8484.59 | 7381.5933 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 34776.983 | 27194.23 | 23422.9312 | -0.29205 | -0.23 | -0.19697 | 34776.6909 | 27194 | 23422.7342 | 0 |  | 0 | 34776.6909 | 27194 | 23422.7342 |  | Contracted
339 | Vas Demetriou | 3 | Implementation adviser for component 3 |  | 0 | 37840 |  | 37840 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 48049.232 | 37840 | 32405.3057 | 48049.232 | 37840 | 32405.3057 | 0 |  | 0 | 48049.232 | 37840 | 32405.3057 |  | Contracted
340 | Urban Plus | 3.2 | Firm to design and supervise the model primary school (international) |  | 0 | 178921 |  | 178921 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 41295.3861 | 31144 | 26905.8641 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 9909.8349 | 7658 | 6662.46 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 46659.5608 | 36057 | 31369.59 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 97864.7819 | 74859 | 64937.9141 | 132137.9276 | 104062 | 89116.3034 | 230002.7095 | 178921 | 154054.2175 | 0 |  | 0 | 230002.7095 | 178921 | 154054.2175
341 | EME | 3.2 | Firm to assist in the development of school facility standards and a manual for the design of schools (international) |  | 167500 | 60332 |  | 60332 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 32524.6531 | 25134 | 21866.5801 | 43227.067 | 35188.3 | 29296.7543 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 75751.72 | 60322.3 | 51163.3344 | 12.3171 | 9.7 | 8.3069 | 75764.0371 | 60332 | 51171.6412 | 0 |  | 0 | 75764.0371 | 60332 | 51171.6412 |  | Completed
342 | Daniel Dupety | 3.2 | Consultant to assist in the development of school facility standards and a manual for the design of schools (international) |  |  | 35992 |  | 35992 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 28266.6016 | 21318 | 18417.0052 |  |  |  | 13981.4985 | 10804.45 | 9399.8715 |  | 0 |  |  | 3870 | [28 empty] | 42248.1002 | 35992.45 | 27816.8767 | -0.57141 | -0.45 | -0.38537 | 42247.5287 | 35992 | 27816.4914 | 0 |  | 0 | 42247.5287 | 35992 | 27816.4914
343 | Merita Behluli | 3.3 | Consultant for Priority 3 Activities |  | 0 | 16500 |  | 16500 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 2419.8735 | 1870 | 1626.9 | 6120.8565 | 4730 | 4115.1 | 0 |  | 0 | 3131.601 | 2420 | 2105.4 | 1992.837 | 1540 | 1339.8 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 13665.168 | 10560 | 9187.2 | 7542.612 | 5940 | 5086.8794 | 21207.78 | 16500 | 14274.0794 | 0 | 0 | 0 | 21207.78 | 16500 | 14274.0794
344 | Merita Behluli | 3.3 | Consultant for Priority 3 Activities |  | 0 | 21120 |  | 21120 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 9679.494 | 7480 | 6507.6 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 9679.494 | 7480 | 6507.6 | 17320.072 | 13640 | 11680.9823 | 26999.566 | 21120 | 18188.5823 | 0 | 0 | 0 | 26999.566 | 21120 | 18188.5823
345 | TRAINING | [7 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0
346 | Study visit | 3.2 | School mapping |  | 0 | 22564 |  | 22564 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 17457.5545 | 12177 | 11182.0347 | 8952.238 | 6918 | 6018.66 | 4261.493 | 3469 | 2888.1884 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 30671.2855 | 22564 | 20088.8832 | 0 | 0 | 0 | 30671.2855 | 22564 | 20088.8832 | 0 |  | 0 | 30671.2855 | 22564 | 20088.8832
347 | Workshop | 3.1 | Safeguards training |  | 0 | 3034.9 |  | 3034.9 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2316.2201 | 1789.9 | 1557.213 | 1529.4202 | 1245 | 1036.5508 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3845.6404 | 3034.9 | 2593.7638 | 0 | 0 | 0 | 3845.6404 | 3034.9 | 2593.7638 | 0 |  | 0 | 3845.6404 | 3034.9 | 2593.7638
348 | Workshops | 3.1 | School mapping, investement planning and inventory taking |  | 0 | 1590.4 |  | 1590.4 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1636.9733 | 1265 | 1100.55 | 0 |  | 0 | 0 | 0 | 0 | 421.0839 | 325.4 | 283.098 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2058.0571 | 1590.4 | 1383.648 | 0 | 0 | 0 | 2058.0571 | 1590.4 | 1383.648 | 0 |  | 0 | 2058.0571 | 1590.4 | 1383.648
349 | Study visit | 3.2 | Standards and Norms on School Design |  | 0 | 2475 |  | 2475 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 3202.7737 | 2475 | 2153.25 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3202.7737 | 2475 | 2153.25 | 0 | 0 | 0 | 3202.7737 | 2475 | 2153.25 | 0 | 0 | 0 | 3202.7737 | 2475 | 2153.25 |  | Under EME?
350 | Study visit | 3.2 | Overseas study visit on school design |  | 19107.0187 | 12214 |  | 12214 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 15805.5267 | 12214 | 10626.18 | 12874.827 | 9949.25 | 8655.8475 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 28680.3537 | 22163.25 | 19282.0275 | -12633.5577 | -9949.25 | -8520.3089 | 16046.796 | 12214 | 10761.7186 | 0 |  | 0 | 16046.796 | 12214 | 10761.7186 |  | Under EME?
351 | ? | 3.2 | Public presentation of manual in municipaities |  | #REF! | 500 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
352 | ? | 3.2 | Conference on School Buildings and Standards |  | #REF! | 10000 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
353 | Study visits | 3.1 | Closing advances |  | 0 | 0 | [14 empty] | -15757.647 | -12177 | -10593.99 |  |  | 0 |  |  |  |  | -7239 | [7 empty] | -15805.5267 | -12214 | -10626.18 | [27 empty] | -31563.1737 | -31630 | -21220.17
354 | Subtotal Component 3 |  |  | 1400000 | #REF! | 2616167.51 | 0 | 3264858.98 | 0 | 0 | 0 | 0 | 0 | 0 | 20083.5346 | 13640 | 12661.8892 | 81600.4117 | 56917.95 | 52267.2657 | 132255.0173 | 102202.4 | 88916.0884 | 85097.0161 | 69271.86 | 57673.7341 | 123204.6201 | 92918 | 80273.5385 | 113953.2666 | 80820.4 | 76611.678 | 35423.1824 | 27373.89 | 23815.2843 | 36774.5847 | 28418.21 | 24723.8427 | 6051.7931 | 8546.63 | 4068.6681 | 101253.214 | 78245.21 | 68073.3327 | 1992.837 | 1540 | 1339.8 | 9679.494 | 7480 | 6507.6 | 0 | 0 | 0 | 53492.1448 | 41337 | 35963.19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 800861.1162 | 608711.55 | 532895.9118 | 3332612.2326 | 2624517.43 | 2247576.3632 | 4165036.5226 | 3264858.98 | 2801692.445 | 2142914.48 | 1687600 | 1445221.8252 | 6307951.0026 | 4952458.98 | 4246914.2702 | -2846914.2702
355
356 | COMPONENT 4. FINANCING MECHANISMS FOR HIGHER EDUCATION
357
358 | GOODS
359 | Rrota | 4.2 | Publication of feasibility study |  | 18300 | 2000 |  | 2000 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2588.1 | 2000 | 1740 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2588.1 | 2000 | 1740 | 0 | 0 | 0 | 2588.1 | 2000 | 1740 | 0 | 0 | 0 | 2588.1 | 2000 | 1740
360 | CONSULTANTS | [7 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  |  |  |  | 0 | [5 empty] | 0
361 | Steve Bristow | 4.1 | Consultant to review and draft higher education legislation (international) |  | 69800 | 54327 |  | 54327 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 11827.6114 | 8250 | 7575.9043 | 7343.4491 | 5674.78 | 4937.0586 | 0 |  | 0 | 53572.5691 | 40403.16 | 34905.0197 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 72743.6297 | 54327.94 | 47417.9826 | -1.1936 | -0.94 | -0.80499 | 72742.4361 | 54327 | 47417.1776 | 0 | 0 | 0 | 72742.4361 | 54327 | 47417.1776 |  | Contracted
362 | Stephen L.Bristow | 4.1 | Consultant for the implementation of higher education legislation (international) |  | 0 | 22940 |  | 22940 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 29129.212 | 22940 | 19645.2884 | 29129.212 | 22940 | 19645.2884 | 38094 | 30000 | 25691.31 | 67223.212 | 52940 | 45336.5984
363 | Jehona Lushaku | 4.1 | Consultant to support the efforts of the international consultants on legislation and financial sustainability of higher education (national) |  | 6768 | 2400 |  | 2400 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3105.72 | 2400 | 2088 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 3105.72 | 2400 | 2088 | 0 | 0 | 0 | 3105.72 | 2400 | 2088 | 0 |  | 0 | 3105.72 | 2400 | 2088 |  | Completed
364 | Blerim Saqipi | 4.1 | Consultant to support the efforts of the international consultants on legislation and financial sustainability of higher education (national) |  | 14100 | 2600 |  | 2600 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 12509.5166 | 9666.95 | 8410.2465 | 3364.53 | 2600 | 2262 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 15874.0466 | 12266.95 | 10672.2465 | -12275.0931 | -9666.95 | -8278.5536 | 3598.9535 | 2600 | 2393.6929 | 0 |  | 0 | 3598.9535 | 2600 | 2393.6929 |  | Completed
365 | Sigurd Hoellinger | 4.2 | Consultant to study financial sustainability of higher education (international) |  | 69800 | 61565 |  | 61565 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 7883.3527 | 6092 | 5300.04 | 48893.1943 | 39800.72 | 33136.9209 | 0 |  | 0 | 0 |  | 0 | 7772.2584 | 6006.15 | 5225.3505 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 64548.8054 | 51898.87 | 43662.3114 | 12274.0519 | 9666.13 | 8277.8514 | 76822.8572 | 61565 | 51940.1628 | 0 |  | 0 | 76822.8572 | 61565 | 51940.1628 |  | Contracted
366 | Thomas Gougen | 4.1 | Consultant |  |  | 12164 |  | 12164 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 14942.878 | 12164.01 | 10127.4006 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 14942.878 | 12164.01 | 10127.4006 | -0.012698 | -0.01 | -0.0085638 |  | 12164 | [5 empty] | 12164 |  |  | Completed
367 | TRAINING | [7 empty] | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 |  | 0 |  |  | 0
368 | Workshop | 4.1 | Higher education legislation |  | 122096 | 1684.7 |  | 1684.7 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2180.0861 | 1684.7 | 1465.689 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 251.0457 | 194 | 168.78 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 2431.1318 | 1878.7 | 1634.469 | -246.3412 | -194 | -166.1371 | 2184.7906 | 1684.7 | 1468.3319 | 0 |  | 0 | 2184.7906 | 1684.7 | 1468.3319
369 | ? | 4.1 | Workshop on Higher Education Legislation |  | 0 | 5000 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6349 | 5000 | 4281.885 | 6349 | 5000 | 4281.885
370 | Workshop | 4.2 | Financng of higher education |  | 37181.6224 | 1369.9 |  | 1369.9 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1772.7191 | 1369.9 | 1191.813 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 1772.7191 | 1369.9 | 1191.813 | 0 | 0 | 0 | 1772.7191 | 1369.9 | 1191.813 | 0 | 0 | 0 | 1772.7191 | 1369.9 | 1191.813
371 | ? | 4.2 | Workshop on Financing of Higher Education |  | 0 | 2000 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2539.6 | 2000 | 1712.754 | 2539.6 | 2000 | 1712.754
372 | Subtotal Component 4 |  |  | 340000 | 338045.6224 | 168050.6 | 0 | 161050.6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 11827.6114 | 8250 | 7575.9043 | 19179.607 | 14821.38 | 12894.6007 | 63836.0723 | 51964.73 | 43264.3215 | 53572.5691 | 40403.16 | 34905.0197 | 12509.5166 | 9666.95 | 8410.2465 | 11136.7884 | 8606.15 | 7487.3505 | 0 | 0 | 0 | 251.0457 | 194 | 168.78 | 2588.1 | 2000 | 1740 | 3105.72 | 2400 | 2088 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 178007.0306 | 138306.37 | 118534.2232 | 28880.6233 | 22744.23 | 19477.6355 | 191944.7886 | 161050.6 | 127884.4665 | 46982.6 | 37000 | 31685.949 | 238927.3886 | 198050.6 | 159570.4155 | 180429.5845
373
374 | UNALLOCATED |  |  | 640000 |  |  |  |  | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | 0 |  | 0 | [15 empty] | 640000
375
376 | GRAND TOTALS |  |  | 6400000 | #REF! | 6956084.7448 | 359901.6 | 7397732.61 | 122534.01 | 93920.98 | 82892.3747 | 52825.929 | 37461.21 | 34124.17 | 135689.8668 | 92155.58 | 85547.1955 | 211089.6753 | 147317.35 | 135208.6333 | 306973.1599 | 237218.93 | 206380.47 | 268802.18 | 218814.1 | 182178.25 | 415023.5762 | 313000.93 | 270407.1569 | 396636.2762 | 299736.99 | 266661.6903 | 264417.3645 | 205101.04 | 177769.8753 | 175889.0359 | 135921.36 | 118251.5832 | 111338.8456 | 89557.06 | 74853.9822 | 363210.1624 | 284577.07 | 247582.0509 | 734946.6262 | 567942.99 | 494110.4013 | 538676.8851 | 416932.08 | 362348.1096 | 269670.8064 | 208392.88 | 181301.8056 | 733930.6805 | 631166.29 | 493427.373 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 4708721.1974 | 3625663.5 | 3145288.1798 | 4381987.1497 | 3615283.7 | 3094607.0958 | 9105923.0179 | 7164859.04 | 6250080.0483 | 2582173.2838 | 2009385 | 1720791.0981 | 11629442.6183 | 9242440.8 | 7931244.3158 | -1531244.3158
[75 empty] | Exchange Rates used: | 1 XDR = | 1.5891 | USD
[75 empty] | Appraisal | 1 EUR = | 1.4681 | USD |  | USD | XDR | ç This is the figure obtained in XDR if the rate of 0.6292711 is used. However, the XDR Grant was 6,400,000
[76 empty] | 1 USD = | 0.62927 | XDR |  | 10000000 | 6292711
[76 empty] | 1 EUR = | 0.92727 | XDR |  | According to Dec 14 2007 Archives
[75 empty] | Current as of: | 1 XDR = | 1.4693 | USD
[75 empty] | 2010-05-18 | 1 EUR = | 1.3315 | USD |  | USD | XDR
[76 empty] | 1 USD = | 0.66225 | XDR |  | 10000000 | 6622516
[76 empty] | 1 EUR = | 0.8443 | XDR

## Allocations XDR EUR USD
Cat | Description | XDR |  |  | EUR |  |  | USD
|  | Amounts Allocated | Revised Require- ments | Diff. Plus or Minus | Amounts Allocated | Revised Require- ments | Diff. Plus or Minus | Amounts Allocated | Revised Require- ments | Diff. Plus or Minus
1 | COMPONENT 1. STRENGTHENING ORGANIZATION & FINANCING OF EDUCATION SYSTEM | 2310000 | 1975339.6385 | 334660.3615 | 2500370.1262 | 2295422.17 | 204947.9562 | 3670913.4 | 2971364.1363 | 699549.2637
2 | COMPONENT 2. BUILDING INSTITUTIONS & MANAGEMENT CAPACITY IN PRIMARY & SECONDARY EDUCATION | 1382000 | 1549419.9917 | -167419.9917 | 1495892.4305 | 1796509.05 | -300616.6195 | 2196191.48 | 2111200.0909 | 84991.3891
3 | COMPONENT 3. CREATING CONDITION TO INTRODUCE EFFICIENT DESIGNS IN KOSOVO'S SCHOOLS | 2258000 | 4246914.2702 | -1988914.2702 | 2444084.7381 | 4952458.98 | -2508374.2419 | 3588278.12 | 6307951.0026 | -2719672.8826
4 | COMPONENT 4. FINANCING MECHANISMS FOR HIGHER EDUCATION | 156000 | 159570.4155 | -3570.4155 | 168856.1644 | 198050.6 | -29194.4356 | 247905.84 | 238927.3886 | 8978.4514
5 | UNALLOCATED | 294000 | 0 | 294000 | 318228.9251 | 0 | 318228.9251 | 467207.16 | 0 | 467207.16
| TOTALS | 6400000 | 7931244.3158 | -1531244.3158 | 6927432.3842 | 9242440.8 | -2315008.4158 | 10170496 | 11629442.6183 | -1458946.6183
| Exchange Rates used: | 1 XDR = | 1.5891 | USD
| Appraisal | 1 EUR = | 1.4681 | USD | USD | XDR | ç This is the figure obtained in XDR if the rated of 0.6292711 is used. However, the XDR Grant was 6,400,000
|  | 1 USD = | 0.62927 | XDR | 10000000 | 6292711
|  | 1 EUR = | 0.92727 | XDR | According to Dec 14 2007 Archives
| Current as of: | 1 XDR = | 1.4693 | USD
| 2010-05-18 | 1 EUR = | 1.3315 | USD | USD | XDR
|  | 1 USD = | 0.66225 | XDR | 10000000 | 6622516
|  | 1 EUR = | 0.8443 | XDR

## Allocations XDR (+ or -)
Sl # | Category | Current Allocations XDR | Amounts Disbursed XDR April 30 2010 | % Disb. /Curr. Alloc. | Revised Requirements XDR | Surplus/ Deficit XDR | Remarks
A | B | C | D | E | F | G | H
1 | Component 1 | 2550000 | 156719.67 | 6.146% | 1975339.6385 | 574660.3615
2 | Component 2 | 1470000 | 211838.53 | 14.41% | 1549419.9917 | -79419.9917
3 | Component 3 | 1400000 | 152697.73 | 10.91% | 4246914.2702 | -2846914.2702
4 | Component 4 | 340000 | 20304.09 | 5.972% | 159570.4155 | 180429.5845
5 | Unallocated | 640000 |  |  |  | 640000
| Total Expenditures | 6400000 | 541560.02 | 8.462% | 7931244.3158 | -1531244.3158
Notes:
Red text are formulae, please do not override

## Procurement Steps
Selection Methods for Consulting Services
Step | Description | Selection Methods |  |  | Estimated Timing
|  | QCBS | CQS | IC
1 | Preparation of TOR | l | l | l | Depending on complexity 1-2 weeks
2 | WB "No Objection" | l | l | l | Within 2 weeks
3 | EOI/Advertizing | l | l | l | 1-2 weeks
4 | Submission of EOI | l | l | l | Normally within a week
5 | Evaluation of EOI | l | l | l | 1-2 weeks
6 | WB "No Objection" | l |  |  | Within 2 weeks
7 | Preparation of RFP | l |  |  | Depending on complexity 1-2 weeks
8 | WB "No Objection" | l |  |  | Within 2 weeks
9 | Issue of RFP/Invitation | l | l |  | Depending on WB comments 1-2 weeks
10 | Submission of Proposals | l | l |  | Depending on complexity 1-4 weeks
11 | Technical Evaluation | l |  |  | Depending on complexity 1-2 weeks
12 | WB "No Objection" | l |  |  | Within 2 weeks
13 | Open. and Eval. Fin. Proposals | l |  |  | 1-2 weeks
14 | Invitation to Negotiate Contract | l | l | l | 1-2 weeks
15 | Negotiations/Draft Contract | l | l | l | 1-2 weeks
16 | WB "No Objection" | l | l | l | Within 2 weeks
17 | Contract Signing | l | l | l | 1 week
18 | Start of Assignment | l | l | l | Within a week of signing
19 | Completion of Assignment | l | l | l | As per TOR of the assignment
Note:
Procurement Plan has used the same steps
Procurement Methods for Goods and Works
Step | Description | Selection Methods |  |  | Estimated Timing
|  | ICB | NCB | Shop-ping
1 | Preparation of Documents | l | l | l | Depending on complexity 3-5 months
2 | WB "No Objection" | l | l | l | Within 2 weeks
3 | Advertizing | l | l |  | 2 weeks but could be more
4 | Issue of Documents | l | l | l | Within a week
5 | Submission of Bids | l | l | l | Depending on complexity 1-4 or 6 weeks
6 | Evaluation of Bids | l | l | l | Within 2 weeks (but could be less)
7 | WB "No Objection" | l | l | l | Within 2 weeks
8 | Contract Award | l | l | l | Within 2 weeks (but could be less)
9 | Contract Signing | l | l | l | 1 week
10 | Start | l | l | l | Depending on complexity 1-2 weeks
11 | Completion | l | l | l | Depending on complexity 90 days for goods 9-15 months for works
Note:
Procurement Plan has used the same steps

## Sheet1
Works | 3.1
1 | Design and Layout of the Guideline on School Facilities Design- Norms and Standards |  |  |  | 1000
2 | Printing of the Guideline on School Facilities Design- Norms and Standards |  |  |  | 2000
CONSULTNATS
1 | Roslaind Levacic | 5,440.00 Eu
2 | Pakize Isufaj | 10,350.00 eu
3 | Vjollca Selimi | 8,469.00 Eu
4 | Besim Kokollari | 10,800.00 Eu
5 | Nicol Saginor | 43,950.00 Eu
TRAINING
2.3 | Test Item development | 900.00 Eu
2.3 | Workshop for Assessment unit | 1,144.00 Eu
2.3 | Training for Matura test Administrators |  | 25,700.00 Eu | pako e re
GRANTS
Te gjitha shkollat e rundit te III (38 fillore dhe 4 te mesme)