## Threshold
Project: |  | ULAANBAATAR CLEAN AIR PROJECT
Credit No.: |  | IDA 5039-MN
Project ID: |  | P122320
Project Implementation Agency: |  | MUNICIPALITY OF ULAANBAATAR, MONGOLIA
Guidelines Version: |  | JANUARY 2011
GPN Date: |  | 2011-11-28
Date of Bank no objection last time for procurement plan: |  | 2012-04-16
Date of this updating of procurement plan: |  | 2013-04-09
Period covered by this procurement plan: |  | 2013
THRESHOLDS
Category | Procurement method | Thresholds for Procurement method | Thresholds for Prior Review
Civil Works | NCB: | <USD 3,000,000 | ● First 2 NCB works contracts by each PIU irrespective of value; ● All contracts >= USD 500,000
| Shopping: | <USD 200,000 | In case unable to obtain at least 3 quotations
Goods | NCB: | <USD 300,000 | ● First 2 NCB goods contracts by each PIU irrespective of value; ● All contracts >= USD 200,000
| Shopping: | <USD 100,000 | In case unable to obtain at least 3 quotations
Consultancy | QCBS: | >=USD 200,000 | For firm only: ● First contract for each selection method; ● All contracts >=USD 100,000
| CQS: | <USD200,000
| LCS: | Contracts meeting the requirements of paragraph 3.6 of the Consultants Guidelines and all assignments for auditing PIU accounts, regardless of contract value
| IC: | Assignments meeting the requirements of Articles 5.1-5.6 of the Consultants Guidelines. | Only in Exceptional Cases
| SSS: | Assignments meeting the requirements of paragraphs 3.8-3.11 of the Consultant Guidelines | All SSS
| SSS (IC): | Assignments meeting the requirements of paragraph 5.6 of Consultant Guidelines | >=USD 20,000
| Shortlist Comprising only National Consultants | <USD100,000
Requirement of Advertising in National Neswpaper
Category | Requirement
Works | All ICB; All NCB
Goods | All ICB; All NCB
Consultant | All firm consultant selection
Requirement of Advertising in UNDB online through Client Connection
Category | Requirement
Works | All ICB
Goods | All ICB
Consultant | >=USD100,000

## PP Apr 9 2013 En
Approved by Project Steering Committee meeting dated January 24, 2013 | [16 empty] | 78744
MONGOLIA
ULAANBAATAR CLEAN AIR PROJECT
IDA 5039-MN
PROCUREMENT PLAN
2013-06-06
|  |  |  | Prepared: | 2011-09-29 |  |  | Last Revised: | 2013-06-06 |  |  | Last Approved by WB: | 2012-04-16
No | Category Num | Contract ID | Contract Name | Proc't method | WB review | Estimated total cost (000' USD) | Actual cost (000' USD) | Plan vs. Actual | BD preparation | Submission to WB | WB approval of BD | Bid Invitation | Bid Opening | Evaluation Complete | WB approval | Contract Signing | Contract Completion |  |  | Contract Amt | Consultant Name | Contract implementation status
A. | Goods |  |  |  |  | 180
1 | A2(b2) | GLEQ-01 | TS to Stove Producers: Laboratory Equipment (Supply of additional equipment needed for sustainable operation of the Lab and equipment for testing of small water heating boiler) | Shopping | Post | 90 |  | Plan | 2013-06-10 |  |  | 2013-06-21 | 2013-07-08 | 2013-07-17 |  | 2013-07-26 | 2013-09-09
Actual
2 | A2(b2) | GLEQ-02 | TS to Stove Producers: Laboratory Equipment (Supply of additional equipment needed for sustainable operation of the Lab and equipment for testing of small water heating boiler) | Shopping | Post | 90 |  | Plan | 2013-09-02 |  |  | 2013-09-05 | 2013-09-27 | 2013-10-11 |  | 2013-10-18 | 2013-12-02
Actual
C. | Works |  |  |  |  | 500
5 | B1(b) | WPLT-01 | Pilot project for City Greening (Implementation of pilot project for a good example of establishment or upgrading of green space in UB) | NCB | Prior | 500 |  | Plan | 2013-11-15 | 2013-12-06 | 2013-12-20 | 2013-12-23 | 2014-01-24 | 2014-02-21 | 2014-04-04 | 2014-04-14 | 2014-09-01
Actual
B. | Consulting Service |  |  |  |  | 3311.5 | 1005.3971
Contract ID | Category Num |  | Contract Name | Proc't method | WB review | Estimated total cost (000' USD) | Contract Price (000' USD) | Plan vs. Actual | TOR/BD preparation/review | WB approval of TOR | Advertisement of EOI | EOI submission | Subm of Shortlist/Ranking to WB | RFP submission to Bidders | Proposals submission | WB approval of Tech Proposal | WB approval of Negotiated Contract | Contract Signing | Contract Completion | Contract Amt (USD) | Consultant Name | Contract implementation status
6 | A1(a3) | CSVC-01 | Verification and quality control (Selection of NGO for verification and quality control of stoves to be delivered ger area households) | CQS | Prior | 197 |  | Plan | 2013-04-10 | 2013-06-14 | 2013-06-18 | 2013-07-19 | 2013-08-09 | 2013-08-19 | 2013-09-10 |  | 2013-09-30 | 2013-08-04 | 2014-08-04
[8 empty] | Actual | 2013-04-10
7 | A2(b1) | CLTA-01 | TA for Laboratory Testing and Stove Development Center (Increase technical capacity and sustainability of SEET, Support SDC for design and production of cleaner, affordable stoves & boilers) | QCBS | Prior | 600 | 287.54 | Plan | 2011-10-15 | 2011-10-21 | 2011-10-26 | 2011-11-16 | 1/10/20121 | 2012-03-28 | 2012-05-09 | 2012-06-11 | 2013-01-15 | 2013-01-17 | 2015-01-16 | 287540 | Mon-Energy Consult LLC, Mongolia | Under implementation
[8 empty] | Actual |  |  | 2011-10-27 | 2011-12-13 | 2012-03-12 | 2012-04-30 | 2012-06-11 | 2012-09-07 | 2013-01-11 | 2013-01-18
8 | A2(b4) | CWHB-01 | Low Pressure Boiler Market Study (Assist MUB in design a program supporting rapid penetration of clean, affordable small water heating boilers and development of sustainable boiler market) | CQS | Prior | 180 |  | Plan | 2011-09-15 | 2011-11-02 | 2012-01-03 | 2012-01-17 | 2012-03-03 | 2012-04-06 | 2012-05-04 |  | 2012-05-18 | 2012-05-28 | 2012-10-29 |  |  | Reason of rebidding: The selected firm proposed too high financial proposal
[8 empty] | Actual |  |  | 2012-01-04 | 2012-01-18 | 2012-03-12 | 2012-05-21 | 2012-06-21 |  | 2012-10-11
[8 empty] | Plan | 2013-02-01 | 2013-04-15 | 2013-06-12 | 2013-07-09 | 2013-08-09 | 2013-08-21 | 2013-09-19 |  | 2013-10-15 | 2013-10-21 | 2014-06-21
[8 empty] | Actual | 2013-02-21 | 2013-04-15
9 | B1(a) | CPLG-01 | Study for City Greening & Preparation of Pilot Project (Preparation of technical and economic feasibility of a city greening investment and development of pilot project) | QCBS | Prior | 280 | 406.392 | Plan | 2011-10-05 | 2012-03-30 | 2012-04-02 | 2012-04-20 | 2012-05-15 | 2012-05-30 | 2012-06-11 | 2013-04-05 | 2013-04-30 | 2013-05-01 | 2015-05-13 | 406392 | ASCONIT CONSULTANTS (France); Sub-Consultants: ALMEC CORPORATION (Japan), VPI INC. (Japan), DESO ARCHITECTS (France), and INSTITUTE OF GEO-ECOLOGY (Mongolia) | Under implementation
[8 empty] | Actual | 2011-10-05 | 2012-04-15 | 2012-04-02 | 2012-04-20 | 2012-05-22 | 2012-08-14 | 2012-09-24 | 2013-04-02 | 2013-05-08 | 2013-05-13
10 | B2(a) | CPAP-01 | FS for Improved Emission Control and Ash Ponds (Review and assess all possible measures to reduce emissions including improved emission controls & improved ash pond management) | QCBS | Prior | 395 |  | Plan | 2011-10-29 | 2012-04-20 | 2013-01-30 | 2013-02-25 | 2013-04-17 | 2013-04-30 | 2013-06-12 | 2013-07-15 | 2013-08-16 | 2013-08-26 | 2014-02-26 |  |  | Under preparation of proposals
[8 empty] | Actual | 2011-10-17 | 2012-04-20 | 2011-10-27: 2013-01-30; 2011-12-13: 2013-02-25; 2012-03-12: 2013-04-17; 2012-04-30: 2013-04-30
11 | B3(a) | CDHS-01 | FS for Rehabilitation & Expansion of DH system (Recommend investment and institutional capacity building program for UB district heating supply system - technically, environmentally, economically and financially feasible) | QCBS | Prior | 600 |  | Plan | 2012-11-06 | 2012-12-05 | 2013-01-11 | 2013-02-04 | 2013-03-18 | 2013-04-15 | 2013-05-13 | 2013-06-28 | 2013-07-26 | 2013-08-05 | 2014-08-05 |  |  | Under evaluation of tech.proposals
[8 empty] | Actual | 2012-11-06 | 2012-12-05 | 2013-01-11 | 2013-02-04 | 2013-03-18 | 2013-04-12 | 2013-05-13
12 | B4(a) | CAHS-01 | Affordable Housing Study (Development of Affordable Housing Strategy) | QCBS | Prior | 415 |  | Plan | 2011-11-01 | 2012-06-08 | 2012-06-11 | 2012-07-02 | 2012-07-16 | 2012-07-26 | 2012-09-06 | 2012-09-28 | 2012-10-19 | 2012-11-02 | 2013-04-19 |  |  | Rejected all EOIs due to lack of experience
[8 empty] | Actual | 2011-10-26 | 2012-04-15 | 2011-10-27: 2012-05-25; 2011-12-13: 2012-06-15; 2012-03-12: 2012-09-04; 2013-01-11: 2012-09-07
[8 empty] | Plan | Rebidding |  | 2012-09-17 | 2012-10-19 | 2013-01-21 | 2013-04-01 | 2013-04-30 | 2013-06-24 | 2013-07-24 | 2013-08-01 | 2015-04-01 |  |  | Under evaluation of tech.proposals
[8 empty] | Actual |  |  | 2012-09-17: 2012-09-17; 2012-10-19: 2012-10-19; 2013-01-21: 2013-02-06; 2013-04-01: 2013-04-01; 2013-04-30: 2013-04-30
13 | C2(a) | CPC-01A | Support Operational Work of Coordination (Assistance to Vice Mayor in charge of Ecology and Green Development of UB to continuously coordinate air pollution reduction activities in UB, research coordinator) | IC | Prior | 125 | 19.2248 | Plan | 2012-03-01 | 2012-03-28 | 2012-09-17: 2013-01-17; 2012-10-19: 2013-02-07; 2013-07-24: 2013-03-18; 2013-08-01: 2013-03-27; 2015-04-01: 2014-03-27 | 19224.771 | Ts.Ariuntuya | Under implementation
[8 empty] | Actual | 2012-03-01 | 2012-04-15 | 2012-09-17: 2013-01-17; 2012-10-19: 2013-02-07; 2013-07-24: 2013-03-18; 2013-08-01: 2013-03-27
14 | C2(a) | CPC-01B | Support Operational Work of Coordination (Assistance to Vice Mayor in charge of Ecology and Green Development of UB to continuously coordinate air pollution reduction activities in UB, communication coordinator) | IC | Prior | 125 | 19.2248 | Plan | 2012-03-01 | 2012-03-28 | 2012-09-17: 2013-01-17; 2012-10-19: 2013-02-07; 2013-07-24: 2013-03-18; 2013-08-01: 2013-03-20; 2015-04-01: 2014-03-27 | 19224.771 | D.Munkhzul | Under implementation
[8 empty] | Actual | 2012-03-01 | 2012-04-15 | 2013-07-24: 2013-03-18; 2013-08-01: 2013-03-27
15 | C2(c) | CPAS-01 | Support for PR campaign (Develop and implement a package of consistent public awareness campaigns and assist MUB in supporting effective air pollution reduction program in UB city) | CQS | Prior | 195 | 199 | Plan | 2012-04-01 | 2012-04-13 | 2012-05-22 | 2012-06-11 | 2012-09-04 | 2013-03-29 | 2013-04-19 |  | 2013-06-06 | 2013-06-10 | 2014-06-10 | 199000 | JV of BREAKTHROUGH PR CO., LTD (Mongolia) and OGILVY PUBLIC RELATIONS WORLDWIDE COMPANY (Canada) | Under contract signing
[8 empty] | Actual | 2012-04-01 | 2012-04-13 | 2012-05-22 | 2012-06-11 | 2012-09-04 | 2013-03-29 | 2013-04-19 |  | 2013-06-06
16 | C3(c) | CPMT-01 | M&E (Evaluation of Current status of clean air activities in UB ) | CQS | Prior | 110 |  | Plan | 2013-06-05 | 2013-06-17 | 2013-06-19 | 2013-07-17 | 2013-08-15 | 2013-08-26 | 2013-09-18 |  | 2013-10-10 | 2013-10-14 | 2014-08-14
[8 empty] | Actual | 2013-06-05
17 | A2(b1) | CLTA-02 | Supervision of Lab equipment installation (Verify lab equipment reassembling and ensure new operators to be able to operate and maintain SEET lab independently) | SS | Prior | 75 | 74.0155 | Plan | 2013-03-27 | 2013-04-05 | 2013-07-24: 2013-05-21; 2013-08-01: 2013-05-22; 2015-04-01: 2014-01-22 | 74015.53 | Mr. Crispin Pemberton-Pigott | Under implementation
[8 empty] | Actual | 2013-03-27 | 2013-04-02 | 2013-07-24: 2013-05-21; 2013-08-01: 2013-05-22
18 | A2(b5)1 | CHWS-01 | Heating Wall Consultant (Study of heating walls in use, determination of requirements for safe connection of new clean low-emission) | IC | Post | 14.5 |  | Plan | 2013-05-13 | 2013-05-14 | 2012-09-17: 2013-05-24; 2012-10-19: 2013-06-03; 2013-08-01: 2013-06-14; 2015-04-01: 2013-09-01 |  |  | Under evaluation
[8 empty] | Actual | 2013-05-13 | 2013-05-14 | 2012-09-17: 2013-05-24; 2012-10-19: 2013-06-03
|  |  | TOTAL |  |  | 3991.5 | 1005.3971
Description:
[6 empty] | CQS - Consultant Qualification Selection |  |  |  |  | 2012-09-17: 1 - New contract, added due to causing requirement.
QCBS - Quality and Cost Based Selection
QBS - Quality Based Selection
[6 empty] | IC - Individual Consultant |  |  |  |  | 2012-10-19: Revised
SSS - Single Source Selection
NCB - National Competitive Bidding
[10 empty] | Prepared by: | 2013-04-01: M.Enkhbayar, Sr. Procurement Specialist, PMU
Note on L23: enkhee: 2nd announcement on Dec 1, 2011
Note on T30: Enkhee: Duration 6 months
Note on T32: Enkhee: Duration 12 months
Note on T36: Enkhee: Duration 20 months
Note on T38: Enkhee: Contract extension is based on consultant's performance
Note on T40: Enkhee: Contract extension is based on consultant's performance
Note on T42: Enkhee: Duration is 1 year with intermediate lapse
Note on T48: user: Duration 2.5 months