|  |
| --- |
| **Restructuring** **Status:** **Archived** |
| **Restructuring Type:** **Level two** |
| Last modified on date : 01/04/2013 |

|  |
| --- |
| **1. Basic Information** |
| Project ID & Name | P088876: DJ-URBAN POVERTY REDUCTION PROJECT |
| Country | Djibouti |
| Task Team Leader | Francois Boulanger |
| Sector Manager/Director | Franck Bousquet |
| Country Director | Hartwig Schafer |
| Original Board Approval Date | 04/29/2008 |
| Original Closing Date: | 05/31/2012 |
| Current Closing Date | 05/31/2013 |
| Proposed Closing Date [if applicable] | 03/31/2014 |
| EA Category | B-Partial Assessment |
| Revised EA Category | B-Partial Assessment-Partial Assessment |
| EA Completion Date | 04/23/2010 |
| Revised EA Completion Date |  |

|  |
| --- |
| **2. Revised Financing Plan (US$m)** |
| **Source** | **Original** | **Revised** |
|  AFD | 8.00 | 8.00 |
|  AFDB | 12.00 | 12.00 |
|  BORR | 7.00 | 7.00 |
|  IDAT | 3.00 | 2.97 |
|  ISDB | 8.50 | 8.50 |
|  **Total** | 38.50 | 38.47 |

|  |
| --- |
| **3. Borrower** |
| **Organization** | **Department** | **Location** |
|  Ministry of Econ and Finance | Department of External Financing | Djibouti |

|  |
| --- |
| **4. Implementing Agency** |
| **Organization** | **Department** | **Location** |
|  Djiboutian Agency for Social Development |  | Djibouti |

|  |
| --- |
| **5. Disbursement Estimates (US$m)** |
| **Actual amount disbursed as of 01/14/2013** **3.11** |
| **Fiscal Year** | **Annual** | **Cumulative** |
|  2012 | 0.00 | 3.11 |
|  2013 | 0.00 | 3.11 |
|   | **Total** | **3.11** |

|  |
| --- |
| **6. Policy Exceptions and Safeguard Policies** |
| **Does the restructured project require any exceptions to Bank policies?** | N |
|  |  |
|  |  |
| **Does the restructured projects trigger any new safeguard policies? If yes, please select from the checklist below and update ISDS accordingly before submitting the package.** | N |

|  |
| --- |
| **7a. Project Development Objectives/Outcomes****Original/Current Project Development Objectives/Outcomes** |
| The project development objective is to increase access to basic economic and social infrastructure and to community development opportunities within Quartier 7.  |

|  |
| --- |
| **7b. Revised Project Development Objectives/Outcomes** [if applicable] |
|   |