## General
Procurement Plan
I. General
1. | Project Information
| Project Name: | Public Finance Modernization Project
| Country: | Republic of Yemen
| Project ID: | P117363
| Loan/Credit/Grant Numbers: | H635-RY
2. | Bank's approval date of Procurement Plan | Original: | 2010-11-15
|  | Revision 1: | 2011-02-23
|  | Revision 2: | 2012-04-17
3. | Date of General Procurement Notice |  | 2011-02-08
II. Goods, Work and Non-Consulting Services Thresholds
1. | Prior Review Threshold. Procurement Decisions subject to Prior Review by the Bank will be as follows
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Goods | ≥500,000 | All Contracts+ first two contracts less than the threshold
| Works | NA | NA
| Non-Consultant Services | ≥ 20,000 | Plus first two contracts
| Direct contract |  | All contracts
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
1 | ICB and LIB (Goods) | >= 500,000 | All Contracts
2 - a | NCB (Goods) | < 500,000 | First two Contracts
2 - b | Shopping (Goods) | <50,000 | First two Contracts
2 - c | Direct Contracting
| ICB (Works) | NA | NA
| NCB (Works) | NA | NA
| NCB (Non-Consultant Services) |  | First two Contracts
Include all methods authorized by the loan agreement
2. | Prequalification. Bidders for bid ( Goods- C2.1-A) shall be prequalified in accordance with the provisions of paragraphs 2.9 and 2.10 of the Guidelines.
3. | Proposed Procedures for CDD Components NA
4. | Reference to (if any) Project Operational/Procurement Manual: under approval process
5. | Any Other Special Procurement Arrangements: [including advance procurement and retroactive financing, if applicable
6. | Procurement Packages with Methods and Time Schedule: See attached "Goods and Works" sheet
III. Selection of Consultants
1. | Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix 1 to the Guidelines Selection and Employment of Consultants:
1a. | Procurement Category | Prior Review Threshold (USD) | Comments
| Consulting Firms (Competitive) | > = 200,000 | All contracts
| Consulting Firms (QBS) |  | First two Contracts
| Individual Consultants (Competitive) | > 50,000 | First two contracts
| Individual Consultants (Sole Source) |  | All SS contracts
| Consulting Firms (Sole Source) |  | All SS contracts
1b. | Procurement Method | Procurement Method Threshold (USD) | Comments
1 | Quality and Cost based Selection (QCBS) | > = 200,000
2 - a | Quality Based Selection (QBS ) | <200,000
2 - b | Selection Under a Fixed Budget (SFB)
2 - c | Least Cost Selection ( LCS ) | <200,000
2 - d | Consultant Qualification Selection ( CQS ) | < 200,000
2 - e | Single Source Selection | <100,000
2 - f | Procedure Paragraph 5.2 section V Selection of Individual Consultant (IC )
Procedure Paragraph 5.3 section V Selection of Individual Consultant ( IC )
2 - g | Sole Source Procedures For Selection of Individual Consultant ( IC )
Include all methods authorized by the Grant agreement
2. | Note: procurement following DC and SS will be under taken only if these are agreed to by IDA based on justification from the project, other wise competitive method will be followed.
| Note: OPCPR list of ceilings can be found here: | http://go.worldbank.org/MKXO98RY40
3. | Any Other Special Selection Arrangements: [including advance procurement and retroactive financing, if applicable]
4. | Consultancy Assignments with Selection Methods and Time Schedule: See attached "Consulting Services" sheet
IV. Implementing Agency Capacity Building Activities with Time Schedule: See attached "Capacity Building" sheet

## Goods
Procurement Plan for Goods/Works/Non-Consulting Services
|  |  |  | ** Applicable in case of Bank's prior review | [7 empty] | Prequalification
COMPONENT | SL No. | Reference No. | Package/ Reference No. |  | Package/ Reference No. | Description of Goods/ Works | Goods/ Works/ NCS | Review by Bank (Prior/ Post) | Method of Selection | Domestic Preference (yes/no) | Prequalification (yes/no) | No Objection from Bank for Draft Prequalification documents (Date)** | No Objection from Bank for Evaluation of Prequalification Application (Date)** | Preparation of Bid Document (Date) | Bank’s No Objection to Bidding Document (Date)** | Bid Invitation (Date) | Bid Closing (Date) | Bid Opening (Date) | Contract Award Decision (Date) | Bank’s No Objection to Bid Evaluation Report and Contract Award (Date)** | Contract Signed (Date) | Contract Value | Contract Currency | Contract No. | Name, City, and Country of Contractor (incl. Zip Code if US) | Completion of Contract (Date) | Expenditure incurred to Date | Comments
1 | 1 | 1/C1/G/NS/PFMP/10 | Goods- C1-A | Planned | ICB-1.1-1 | Establishing Cash Management Unit and supporting the department in charge of commitment controls | Goods | Post | NS | No | No | NA | NA | 2011-01-05 | NA | 2011-01-19 | 2011-01-26 | 2011-01-26 | 2011-02-09 | NA | 2011-02-12 |  |  |  |  | 2011-02-26
Revised
Actual
|  | 1/C1-A/G/NS/PFMP/10 | Lot A |  |  | furniture for cash management unit | [15 empty] | 30660 | $
|  | 1/C1-B/G/NS/PFMP/10 | Lot B |  |  | office equipments for cash management unit | [5 empty] | NA | NA | 2010-12-12 | NA | 2010-12-12 | 2010-12-28 | 2010-12-28 | 2011-04-20 | 2011-04-19 | 2011-04-24 | 23260 | $ |  | smart technology
|  | 1/C1-C/G/NS/PFMP/10 | Lot C |  |  | copy machine for cash management unit | [5 empty] | NA | NA | 2010-12-12 | NA | 2010-12-12 | 2010-12-28 | 2010-12-28 | 2011-03-16 | 2011-03-13 | 2011-03-19 | 6800 | $ |  | Shaher co. | 2011-04-05
|  | 1/C1-D/G/NS/PFMP/11 | Lot D |  |  | Air-condition for cash management unit | [5 empty] | NA | NA | 2010-12-12 | NA | 2010-12-12 | 2011-02-14 | 2011-02-14 | 2011-03-20 | 2011-03-17 | 2011-03-22 | 600 | $ |  | Atech computers | 2011-04-02
1 | 2.1 | 2/C1.1/G/NS/PFMP/12 | Goods C 1.1 | Planned |  | Providing equipment to the Budget Sector and Planning Sector | Goods | Post | NS | No | No | NA | NA | 2012-04-01 | NA | 2012-04-06 | 2012-04-20 | 2012-04-20 | 2012-05-10 | NA | 2012-05-17 |  |  |  | Horizon for Telecommunication and Technology | 2012-06-16
Revised
|  |  |  | Actual | [7 empty] | NA | NA | 2011-06-20 | NA | 2012-07-03 | 2012-08-04 | 2012-08-04 | 25Sep.2012 | NA | 2012-10-06 | 43390 | $
1 | 3 | 3/C1.2-D/G/NS/PFMP/12 | Goods 1.2 D | Planned |  | Providing computers (PCs)+printers +scanners to 9 ministries to implement the pilot CMS and CCS. | Goods | Post | NS | No | No |  |  | 2012-08-10 | NA | 2012-08-15 | 2012-09-02 | 2012-09-02 | 2012-09-17 | NA | 2012-09-21 |  |  |  |  | 2012-11-15
Revised
|  |  |  | Actual | [9 empty] | 2012-05-15 | NA | 2012-05-15 | 2012-06-02 | 2012-06-02 | 2012-07-08 | NA | 2012-07-11 | 29617 | $ |  | AL-FALAK
2.1 | 4 | 4/C2.1-A/G/ICB/PFMP/13 | Goods- C2.1-A | Planned |  | Establishment of the computing platform and datacenter backup | Goods | Prior | ICB | No | Yes | 2011-04-05 | 2011-05-23 | 2011-01-15 | 2011-01-25 | 2011-01-29 | 2011-03-10 | 2011-02-24 | 2011-03-17 | 2011-03-24 | 2011-04-07 |  |  |  |  | 2012-04-06
|  |  |  | Revised1 |  |  |  | Prior | ICB | No | Yes | N/A | N/A | 2012-06-30 | 2012-04-25 | 2012-05-02 | 2012-06-08 | 2012-05-25 | 2012-07-04 | 2012-07-15 | 2012-07-22 |  |  |  |  | 2013-08-10
|  |  |  | Revised2 |  |  |  | Prior | ICB | No | Yes | 2013-05-15 | 2013-07-02 | 2013-07-16 | 2013-07-26 | 2013-08-25 | 2013-10-09 | 2013-10-09 | 2013-11-08 | 2013-11-22 | 2013-11-30 |  |  |  |  | 2014-11-30 |  | cost estimate in PP is US$ 2,708,000, while the price of the bidder is 3,881,852 the gap of almost more than 1,1 million need to adjusted
|  |  |  | Actual | [10 empty] | 2013-08-14 | 2013-09-01 | 2013-11-06 | 2013-11-06 | 2014-02-03 | 2014-01-30 | 2014-04-03 |  |  |  |  | 2014-10-30
2.1 | 5 | 5/C2.1-E/G/NCB/PFMP/13 | Goods- C2.1-E | Planned |  | Generator | Goods | Prior | ICB | No | Yes | 2011-04-05 | 2011-05-23 | 2011-01-15 | 2011-01-25 | 2011-01-29 | 2011-03-10 | 2011-02-24 | 2011-03-17 | 2011-03-24 | 2011-04-07 |  |  |  |  | 2012-04-06 |  | This activity has been merged with Data Center Bid.
|  |  |  | Revised1 |  |  |  | Prior | ICB | No | Yes | N/A | N/A | 2012-06-30 | 2011-05-05 | 2011-02-10 | 2011-03-16 | 2011-03-01 | 2011-04-10 | 2011-04-19 | 2011-04-17 |  |  |  |  | 2012-04-25
|  |  |  | Revised2 |  |  |  | Post | NCB |  |  | N/A | N/A | 2013-04-15 | 2013-04-25 | 2013-05-02 | 2013-06-01 | 2013-06-01 | 2013-06-11 | 2013-06-18 | 2013-07-02 |  |  |  |  | 2013-10-10
|  |  |  | Actual | [11 empty] | CANCELLED
2.1 | 6 | 6/C2.1-B/G/NCB/PFMP/11 | Goods- C2.1-B | Planned |  | Roll-out of AFMIS to 6 ministries and 2 central offices Turn-key vendor with assistance from PMU | Goods | Prior | ICB | No | Yes | 2011-04-05 | 2011-05-23 | 2013-07-01 | 2013-07-11 | 2013-07-18 | 2013-08-19 | 2013-08-07 | 2013-08-28 | 2013-08-28 | 2013-09-11 |  |  |  |  | 2014-09-04
|  |  |  | Revised |  |  |  | Prior | NCB | No | No
|  |  |  | Actual | [5 empty] | NO | No |  |  |  | 2011-07-26 | 2011-07-30 | 2011-08-24 | 2011-08-24 | 2011-10-26 | 2012-03-09 | 2011-11-02 | 299937.5 | $ |  | Compute me
2.1 | 7 | 7/C2.1-A/G/NCB/PFMP/12 | Goods- C2.1-A | Planned |  | Roll-out of AFMIS to 10 ministries and 3 central offices Turn-key vendor with assistance from PMU to: Procure hardware build infrastructure | Goods | post | ICB | No | Yes | 2011-10-01 | 2011-11-18 | 2011-12-23 | 2012-01-02 | 2012-01-09 | 2012-02-20 | 2012-02-20 | 2012-03-12 | 2012-03-19 | 2012-04-02 |  | $ |  | Leaders Technology | 2013-04-02
|  |  |  | Revised |  |  |  |  | NCB | NO | No | NA | NA | 2012-04-01 | 2012-04-11 | 2012-04-18 | 2012-05-30 | 2012-05-30 | 2012-06-20 | 2012-06-27 | 2012-07-11 |  |  |  |  | 2012-12-28
|  |  |  | Actual | [9 empty] | 2012-05-10 | NA | 2012-05-19 | 2012-06-16 | 2012-06-30 | 2012-09-18 | NA | 2012-10-01 | 399828 |  |  |  | 2013-05-27
2.1 | 8 | 8/C2.1-F/G/NCB/PFMP/13 | Goods-C2.1 F | Planned |  | Roll-out of AFMIS to Ministries, departments and Governorates Turn-key vendor with assistance from PMU to: Procure hardware build infrastructure | Goods | post | ICB |  |  | 2013-01-05 | 1900-02-16 | 1900-02-03 | 1900-01-09 | 1900-01-06 | 1900-02-10 | 0 | 1900-01-20 | 1900-01-06 | 1900-01-13 |  | $ |  |  | 1900-11-15
|  | 8/C2.1-FpartA/G/NCB/PFMP/13 | Part A | Revised |  |  |  | post | NCB |  |  | NA | NA | 2013-04-30 | 2013-05-10 | 2013-05-17 | 2013-06-16 | 2013-06-16 | 2013-07-07 | 2013-07-14 | 2013-07-28 |  |  |  |  | 2014-06-13
|  |  |  | Actual |  |  |  |  | NCB | [6 empty] | 2013-04-23 | 2013-05-25 | 2013-05-25 | 2013-10-05 |  | 2013-11-26 | 303430 |  |  | Smart Soft | 2014-04-26
|  | 8/C2.1-FpartB/G/NS/PFMP/14 | Goods C2.1-F | Planned |  | Procurement of UPS 1000VA (163 Nos.) |  | post | NS |  |  | NA | NA | 2014-01-15 | NA | 2014-01-20 | 2014-01-29 | 2014-01-29 | 2014-02-12 |  | 2014-02-23 |  |  |  |  | 2014-03-23
|  |  | Part B | Revised
|  |  |  | Actual | [11 empty] | 2014-01-22 | 2014-02-03 | 2014-02-03
2.1 | 9 | 9/C2.1-C/G/DC/PFMP/12 | Goods C2.1-C | Planned |  | Update Antivirus software | Goods | Prior | DC | NO | No |  |  | NA | NA | NA | NA | NA | NA | 2012-05-02 | 2012-05-15 |  |  |  |  | 2013-06-01
|  |  |  | Revised | [20 empty] | Net Technology
|  |  |  | Actual | [9 empty] | NA | NA | NA | NA | NA | NA | 2012-06-10 | 2012-06-20 | 5926.71 | $ |  |  | 2012-07-01
2.1 | 10 | 10/C2.1-D/G/NS/PFMP/13 | Goods C2.1- D | Planned |  | Wireless equipments for backup communication | Goods | Post | NS | NO | No |  |  | 2012-06-10 | NA | 2012-06-18 | 2012-07-15 | 2012-07-15 | 2012-07-20 | NA | 2012-07-28 |  | $ |  |  | 2012-08-10
|  |  |  | Revised | [9 empty] | 2013-06-02 | NA | 2013-07-02 | 2013-08-01 | 2013-08-01 | 2013-08-11 | NA | 2013-08-25 |  |  |  |  | 2013-09-24
|  |  |  | Revised2 | [9 empty] | 2014-06-02 | NA | 2014-07-02 | 2014-08-01 | 2014-08-01 | 2014-08-11 | NA | 2014-08-25 |  |  |  |  | 2014-09-24
Actual
2.2 | 11 | 11/C2.2-ApartB/G/NCB/PFMP/12 | Goods- C2.2-A Part B | Planned |  | LGMIS Computers( PCs) , UPSs, Photocopiers and Fax Machines & Projectors Stage 1 | Goods | Prior | NCB | No | No | NA | NA | 2011-01-15 | 2011-01-22 | 2011-01-27 | 2011-02-24 | 2011-02-24 | 2011-03-17 | 2011-03-24 | 2011-04-07 |  | $ |  | Smart Soft | 2012-09-04
|  |  |  | Revised1 |  |  |  | post | NCB | No | No | NA | NA | 2012-04-15 | 2012-04-22 | 2012-04-27 | 2012-05-25 | 2012-05-25 | 2012-06-15 | 2012-06-22 | 2012-07-06 |  |  |  |  | 2013-06-06
|  |  |  | Revised2 |  |  |  | post | NCB | No | No | NA | NA | 2012-10-01 | 2012-10-08 | 2012-10-13 | 2012-11-10 | 2012-11-10 | 2012-12-01 | 2012-12-08 | 2012-12-22 |  |  |  |  | 2013-11-22
|  |  |  | Actual | [11 empty] | 2012-10-22 | 2012-11-17 | 2012-11-17 | 2013-02-16 | NA | 2013-03-02 | 60800 |  |  |  | 2013-04-13
2.2 | 12 | 12/C2.2-ApartA/G/NCB/PFMP/11 | Goods- C2.2-A part A | Planned |  | LGMIS Scanners | Goods | Prior | NCB | No | No | NA | NA | 2011-01-15 | 2011-01-22 | 2011-01-27 | 2011-02-24 | 2011-02-24 | 2011-03-17 | 2011-03-24 | 2011-04-07 |  |  |  | Leaders Technology | 2011-06-06
|  |  |  | Revised |  |  |  | Prior | NCB | No | No | NA | NA | 2011-04-25 | 2011-01-31 | 2011-02-02 | 2011-03-01 | 2011-03-01 | 2011-03-20 | 2011-03-18 | 2011-03-22 |  |  |  |  | 2011-04-15
|  |  |  | Actual | [9 empty] | 2011-01-30 | 2011-02-22 | 2011-02-27 | 2011-03-29 | 2011-03-29 | 2011-04-22 | 2011-04-20 | 2011-04-25 | 32500 | $ |  |  | 2011-05-25
2.2 | 13 | 13/C2.2-B2/G/NCB/PFMP/14 | Goods- C2.2-B2 | Planned |  | LGMIS Computers( PCs) , UPSs & Projectors Stage2 + 5 laptops | Goods | post | NCB | No | No | NA | NA | 2012-01-01 | 2012-01-08 | 2012-01-13 | 2012-02-10 | 2012-02-10 | 2012-03-02 | 2012-03-09 | 2012-03-23
|  |  |  | Revised |  |  |  | post | NCB |  |  | NA | NA | 2013-07-01 | NA | 2013-07-08 | 2013-08-07 | 2013-08-07 | 2013-08-21 | NA | 2013-09-04 |  |  |  |  | 2013-10-04
|  |  |  | Revised2 |  |  |  | post | NCB | No | No | NA | NA | 2014-05-20 | NA | 2014-06-01 | 2014-06-29 | 2014-06-29 | 2014-07-20 | NA | 2014-08-03 |  |  |  |  | 2014-10-03
Actual
|  |  |  | Planned |  | Furniture for LGMIS |  | post | NS |  |  |  |  | 2014-06-01 | NA | 2014-06-13 | 2014-06-27 | 2014-06-27 | 2014-07-12 | NA | 2014-07-17 |  |  |  |  | 2014-08-17
|  | 13/C2.2-B3/G/NCB/PFMP/14 |  | Revised
Actual
2.2 | 14 | 14/C2.2-B1/G/NS/PFMP/13 | Goods- C2.2-B1 | Planned |  | LGMIS Computers( PCs) , UPSs & Scanners - Stage3 | Goods | post | NS |  |  |  |  | 2013-03-10 | NA | 2013-03-15 | 2013-03-29 | 2013-03-29 | 2013-04-12 | NA | 2013-04-26 |  |  |  |  | 2013-05-26
|  |  |  | Revised | [20 empty] | ComputeMe
|  |  |  | Actual | [14 empty] | 11-May-13
2.2 | 15 | 15/C2.2-C/GNS//PFMP/11 | Goods- C2.2-C | Planned |  | Computer Software licenses Stage 1 | Goods | Post | NS | No | No | NA | NA | 2011-03-01 | NA | 2011-03-15 | 2011-03-22 | 2011-03-22 | 2011-04-05 | NA | 2011-04-10 | 11980 | $ |  |  | 2011-06-09
Revised
|  | 15/C2.2-CA/G/NS/PFMP/11 | Lot A | Actual |  | windows server 2008 | [7 empty] | NA | NA | 2010-12-11 | 2011-01-20 | 2011-01-20 | 2011-01-30 | NA | 2011-03-30 | 2480 | $ |  | Al-Falak
|  | 15/C2.2-CB/G/NS/PFMP/11 | Lot B |  |  | Antivirus software | [7 empty] | NA | NA | 2011-03-05 | 2011-03-09 | 2011-03-09 | 2011-04-18 | NA | 2011-05-08 | 9500 | $ |  | Net technology
2.2 | 16 | 16/C2.2-DA/G/NS/PFMP/13 | Goods- C2.2-DA | Planned |  | Computer Software licenses Stage 2 | Goods | Post | NS | No | No | NA | NA | 2012-06-01 | NA | 2012-06-15 | 2012-06-22 | 2012-06-22 | 2012-07-06 | NA | 2012-07-11 |  |  |  |  | 2012-09-13
|  |  |  | Revised |  |  |  | Post | NS | No | No | NA | NA | 2013-03-15 | NA | 2013-03-29 | 2013-04-05 | 2013-04-05 | 2013-04-19 | NA | 2013-04-24 |  |  |  |  | 2013-06-23
Actual
2.2 | 17 | 17/C2.2-DB/G/NS/PFMP/14 | Goods- C2.2-DB | Planned |  | Computer Software licenses Stage 3 | Goods | Post | NS |  |  |  |  | 2014-01-01 | NA | 2014-01-15 | 2014-01-22 | 2014-01-22 | 2014-02-05 | NA | 2014-02-12 |  |  |  |  | 2014-04-13
|  |  |  | Revised |  |  |  | Post | NS |  |  |  |  | 2014-06-01 | NA | 2014-06-13 | 2014-06-27 | 2014-06-27 | 2014-07-12 | NA | 2014-07-17 |  |  |  |  | 2014-08-17
Actual
2.2 | 18 | 18/C2.2-E/G/NS/PFMP/11 | Goods- C2.2-E | Planned |  | LGMIS Awareness material to Beneficiary | Goods | Post | NS | No | No | NA | NA | 2011-01-15 | NA | 2011-01-29 | 2011-02-05 | 2011-02-05 | 2011-02-19 | NA | 2011-02-24 |  |  |  |  | 2011-03-26 |  | YR395,900
|  |  |  | Revised | [20 empty] | Al-Motafwq Printing Press
|  | 18/C2.2-E-A/G/NS/PFMP/11 | Part A | Actual | [7 empty] | NA | NA | NA | NA | 2011-03-18 | 2011-03-25 | 2011-03-25 | 2011-03-30 | NA | 2011-04-04 | 1841 | $ |  |  | 2011-04-30
|  | 18/C2.2-E-B/G/NS/PFMP/13 | Part B | Planned |  |  |  | Post | NS | No | No | NA | NA | NA | NA | 2012-06-20 | 2012-07-05 | 2012-07-06 | 2012-07-15 | NA | 2012-07-25 |  |  |  |  | 2012-08-05
|  |  |  | Revised |  |  |  | Post | NS | No | No | NA | NA | 2013-03-01 | NA | 2013-03-15 | 2013-03-22 | 2013-03-22 | 2013-03-29 | NA | 2013-04-05 |  |  |  |  | 2013-05-05
|  |  |  | Revised2 |  |  |  | Post | NS |  |  |  |  | 2014-08-01 | NA | 2014-08-15 | 2014-08-22 | 2014-08-22 | 2014-08-29 | NA | 2014-09-05 |  |  |  |  | 2014-10-05
Actual
2.2 | 19 | 19/C2.2-E-C/G/NS/PFMP/14 | Goods- | Planned |  | LGMIS Awareness material to Beneficiary-2014-2015 | Goods | Post | NS | No | No | NA | NA | 2014-01-01 | NA | 2014-01-15 | 2014-01-22 | 2014-01-22 | 2014-01-29 | NA | 2014-02-05 |  |  |  |  | 2014-03-07
|  |  | C2.2-E | Revised |  |  |  | Post | NS |  |  |  |  | 2014-12-01 | NA | 2014-12-15 | 2014-12-22 | 2014-12-22 | 2014-12-29 | NA | 2015-01-05 |  |  |  |  | 2015-02-04
|  |  | Part C | Actual
2.2 | 20 | 20/C2.2-F/G/NS/PFMP/13 | Goods- C2.2-F | Planned |  | LGMIS (Servers) | Goods | post | NS | No | No | NA | NA | 2012-01-15 | 2012-01-22 | 2012-01-27 | 2012-02-24 | 2012-02-24 | 2012-03-16 | 2012-03-23 | 2012-04-06 |  |  |  |  | 2012-05-26
|  |  |  | Revised | [7 empty] | NA | NA | 2013-03-15 | 2013-03-22 | 2013-03-27 | 2013-04-24 | 2013-04-24 | 2013-05-15 | 2013-05-22 | 2013-06-05 |  |  |  |  | 2013-07-25
|  |  |  | Revised2 |  |  |  | post | NS |  |  |  |  | 2014-05-01 | NA | 2014-05-11 | 2014-06-08 | 2014-06-08 | 2014-06-29 | 2014-07-06 | 2014-07-20 |  |  |  |  | 2014-08-30
|  |  |  | Actual | [24 empty] | to be completed
3 | 21 | 21/C3.2-A/G/NCB/PFMP/13 | Goods- C3.2-A | Planned |  | Supply of equipments to FI | Goods | post | NCB | No | No | NA | NA | 2011-01-15 | 2011-01-22 | 2011-01-27 | 2011-02-24 | 2011-02-24 | 2011-03-17 | 2011-03-24 | 2011-04-07 |  |  |  |  | 2011-10-04
|  |  |  | Revised |  |  |  | post | NCB |  |  |  |  | 2013-04-30 | 2013-05-07 | 2013-05-12 | 2013-06-09 | 2013-06-09 | 2013-06-30 | 2013-07-07 | 2013-07-21 |  |  |  |  | 2014-01-17
|  |  |  | Revised1 |  |  |  | post | NCB |  |  |  |  | 2014-05-05 | NA | 2014-05-19 | 2014-06-19 | 2014-06-19 | 2014-07-10 | NA | 2014-07-20 |  |  |  |  | 2014-11-17
Actual
3 | 22 | 22/C3.1/G/NS/PFMP/12 | Goods- C3.1 | Planned |  | Supply of equipment (laptops, software and display devices) of the HTB Committee members | Goods | post | NS | NO | No | NA | NA | 2012-07-21 | NA | 2012-07-25 | 2012-08-15 | 2012-08-15 | 2012-08-20 | NA | 2012-08-24 |  |  |  |  | 2012-09-25
Revised
|  |  |  | Actual | [9 empty] | 2012-05-15 | NA | 2012-05-15 | 2012-06-02 | 2012-06-02 | 2012-07-08 | NA | 2012-07-11 | 24885 | $ |  | AL-FALAK | 2013-01-02
3 | 23 | 23/C3.1/NCS/NS/PFMP/13 | NCS-C3.1 | Planned |  | Preparation of materials for a training course with the guidance module and tender documents (SBDs) | NCS | Post | NS | No | No | NA | NA | NA | NA | 2012-07-02 | 2012-07-15 | 2012-07-15 | 2012-07-25 | NA | 2012-08-01 |  |  |  |  | 2012-09-15
|  |  |  | Revised |  |  |  | Post | NS | [6 empty] | 2014-10-05 | 2014-10-17 | 2014-10-17 | 2014-10-24 | NA | 2014-10-28 |  |  |  |  | 2014-12-27
Actual
3 | 24 | 24/C3.3-B/G/NS/PFMP/13 | Goods-C3.3-B | Planned |  | Supply of laptops for members of the HACT | Goods | post | NS | NO | NO | NA | NA | 2011-09-16 | NA | 2011-09-20 | 2011-09-30 | 2011-09-30 | 2011-10-03 | NA | 2011-10-10 |  |  |  |  | 2011-10-25
Revised
Actual
3 | 25 | 25/C3.1/G/NCB/PFMP/13 | Goods- | Planned |  | Supply Electronic Archive to HTB Purchase of an Electronic Archive system for HTB and equipments and furniture for newly established Training Unit, which supervises the implementation of the NTP | Goods | Post | NCB |  |  |  |  | 2013-03-15 | NA | 2013-03-22 | 2013-04-21 | 2013-04-21 | 2013-05-05 | NA | 2013-05-20 |  |  |  |  | 2013-07-19
|  |  | C3.1 | Revised |  |  |  | Post | NCB |  |  |  |  | 2014-05-12 | NA | 2014-05-26 | 2014-06-26 | 2014-06-26 | 2014-07-17 | NA | 2014-07-27 |  |  |  |  | 2014-09-25
Actual
4 | 26 | 26/C4.1-A/G/NCB/PFMP/11 | Goods- C4.1-A | Planned |  | Strengthening COCA’s training department to be properly equipped for COCA staff to receive training | Goods | post | NCB | No | No | NA | NA | 2011-02-01 | 2011-02-08 | 2011-02-13 | 2011-03-13 | 2011-03-13 | 2011-04-03 | 2011-04-10 | 2011-04-24 | 33826.5 | $ |  |  | 2011-07-23
Revised
|  | 26/C4.1-A1/G/NCB/PFMP/11 | Lot A1 | Actual |  | Desktops + UPS | [7 empty] | 2011-04-10 | NA | 2011-04-13 | 2011-05-14 | 2011-05-14 | 2011-06-07 | NA | 2011-06-13 | 26870 | $ |  | Smart Soft
|  | 26/C4.1-A2/G/NCB/PFMP/11 | Lot A2 |  |  | Projectors | [7 empty] | 2013-06-30: 2011-06-07; 2013-07-21: 2011-06-13 | 2200 | $ |  | Canon
|  | 26/C4.1-A3/G/NCB/PFMP/11 | Lot A3 |  |  | Chairs & tables for computers | [7 empty] | 2013-06-30: 2011-06-07 | 4042.5 | $ |  | Y-tech
|  | 26/C4.1-A4/G/NCB/PFMP/11 | Lot A4 |  |  | switches + cabinet +batch panel | [7 empty] | 2013-06-30: 2011-06-07 | 714 | $ |  | Net technology
4 | 27 | 27/C4.1-B/G/NS/PFMP/13 | Goods- C4.1-B | Planned |  | Strengthening COCA’s training department to be properly equipped for COCA staff to receive training ( Servers) | Goods | post | NS | No | No | NA | NA | 2012-10-22 | NA | 2012-11-05 | 2012-11-15 | 2012-11-15 | 2012-11-17 |  | 2012-11-22 |  |  |  |  | 2012-11-27
|  |  |  | Revised | [9 empty] | 2013-03-15 | NA | 2013-03-22 | 2013-04-05 | 2013-04-05 | 2013-04-12 |  | 2013-05-12
Actual
[14 empty] | 2013-06-30: 2013-05-07 |  |  |  | Apple | 2013-05-14
3 | 28 | 28/C3.3/G/NCB/PFMP/11 | Goods- C3.3-A | Planned |  | Supply of equipments to HATC | Goods | post | NCB | No | No | NA | NA | 2011-01-15 | 2011-01-22 | 2011-01-27 | 2011-02-24 | 2011-02-24 | 2011-03-17 | 2011-03-24 | 2011-04-07 |  |  |  |  | 2011-10-04
[14 empty] | 2012-08-04 | NA | 2012-08-06 | 2012-09-07 | 2012-09-07 | 2012-09-23 | NA | 2012-10-01 |  |  |  |  | 2012-11-15
|  | 28/C3.3-A/G/NCB/PFMP/12 | Part A | Revised |  | Supply of equipments to HATC Administration | [7 empty] | 2012-04-30 |  | 2012-06-15 | 2012-07-25 | 2012-07-25 | 2012-07-01 |  | 2012-07-10 |  |  |  |  | 2012-10-15
|  |  |  | Actual | [9 empty] | 2012-06-15 | NA | 2012-06-23 | 2012-07-21 | 2012-07-21 | 2012-10-07 | NA | 2012-10-13 | 102074.37 | $ |  | NATCO | 2013-03-03 |  |  | Done
3 | 29 | 29/C3.3-B/G/PFMP/13 | Goods - 3.3 | Planned |  |  | Goods | post | NS |  |  |  |  | 2012-04-30 | NA | 2013-03-21 | 2013-03-28 | 2013-03-28 | 2013-04-05 | NA | 2013-04-15 |  |  |  |  | 2013-06-01 |  |  | To be completed
|  |  |  | Revised |  | Supply of equipments for complain system |  | post | NCB |  |  |  |  | 2014-06-17 |  | 2014-07-01 | 2014-07-31 | 2014-07-31 | 2014-08-17 |  | 2014-08-28 |  |  |  |  | 2014-10-12
|  |  | Part B | Actual
1 | 30 | 30/C1.1/NCS/PFMP/13 | NCS-C1.1 A | Planned |  | Producing the Citizen Budget and supporting the public access to fiscal information and support AFMIS to disclose data | NCS | Post | NS | No | No | NA | NA | 2011-01-01 | NA | 2011-01-15 | 2011-01-22 | 2011-01-22 | 2011-01-29 | NA | 2011-02-03 |  |  |  |  | 2011-03-03
|  |  |  | Revised1 | [9 empty] | 2012-05-06 | NA | 2012-05-21 | 2012-05-28 | 2012-05-28 | 2012-06-04 | NA | 2012-06-09 |  |  |  |  | 2012-07-07
|  |  |  | Revised2 |  |  |  | Post | NS | No | No | NA | NA | 2013-03-18 | NA | 2013-03-25 | 2013-04-01 | 2013-04-01 | 2013-04-08 | NA | 2013-04-13 |  |  |  |  | 2013-04-02
|  |  |  | Revised3 | [9 empty] | 2014-03-01 |  | 2014-02-12 | 2014-02-22 | 2014-02-22 | 2014-03-02 |  | 2014-03-09 |  |  |  |  | 2014-04-06
Actual
2.1 | 31 | 31/C2.1-A/NCS/PFMP/13 | NCS-C2.1 A | Planned |  | Telecommunication fees for AFMIS ( General Corporation for Telecommunication ) 2013 | NCS | Prior | DC | No | No | NA | NA | 2010-12-15 | 1900-01-06 | NA | NA | NA | 1900-01-02 | NA | 2011-01-01 |  |  |  | Yemen Net | 1901-06-29 |  | NOL WB, on August 23, 2013, to the Data Transmission Network Subscribtion Contract with Public Telecommunication Corporation for both AFMIS and LGMIS btween August 2013 and August 2014 subject to a ceiling of US$ 112,259
|  |  |  | Revised |  |  |  | Prior | DC | No | No | NA | NA | 2013-07-07: 2013-04-15; 2013-07-21: 2013-04-29 |  |  |  |  | 2013-12-31
|  |  |  | Actual | [9 empty] | 2013-07-07: 2013-08-23 |  |  |  |  | 2014-08-30 |  |  | To be cont.
2.2 | 32 | 32/C2.2-A/NCS/PFMP/13 | NCS-C2.2 A | Planned |  | Telecommunication fees for LGMIS ( General Corporation for Telecommunication ) + LGMIS SMS Notification | NCS | Prior | DC | No | No | NA | NA | 2010-12-15 | 2010-12-20 | NA | NA | NA | 2010-12-23 | NA | 2011-01-01 |  |  |  | Yemen Net | 2012-06-30
|  |  |  | Revised1 |  |  |  | Prior | DC | No | No | NA | NA | 0 | 1900-01-04 | NA | NA | NA | 1900-01-07 | NA | 2012-05-02 |  |  |  |  | 2015-05-02
|  |  |  | Revised2 |  |  |  | Prior | DC | No | No | NA | NA | 2013-07-07: 2013-11-15; 2013-07-21: 2013-11-29 |  |  |  |  | 2015-11-15
|  |  |  | Actual | [9 empty] | 2013-07-07: 2013-08-23 |  |  |  |  | 2014-08-30
2.2 | 33 | 33/C2.2-B/NCS/PFMP/13 | NCS-C2.2 B | Planned |  | (Up date ) (Maintenance) Software & Hardware ( LGMIS) . | NCS | Prior | DC | No | No | NA | NA | 2010-12-15 | 2010-12-22 | NA | NA | NA | 2010-12-27 | NA | 2011-01-01 |  |  |  |  | 2012-06-30 |  | Although NATCO was invited to sign contract, but they are not responding, it is suggested to make an open tender
|  |  |  | Revised1 |  |  |  | Prior | DC | No | No | NA | NA | 0 | 1900-01-06 | NA | NA | NA | 1900-01-11 | NA | 2012-06-17 |  |  |  |  | 2015-06-17
|  |  |  | Revised2 |  |  |  | Prior | DC | No | No | NA | NA | 2013-07-07: NA; 2013-07-21: 2013-06-17 |  |  |  |  | 2015-12-31
|  |  |  | Revised3 | [9 empty] | 2014-06-01 | 2014-06-08 | 2014-06-13 | 2014-07-13 | 2014-07-13 | 2014-08-03 |  | 2014-08-13 |  |  |  |  | 2015-12-31
Actual
2.2 | 34 | 34/C2.2-C/NCS/PFMP/11 | NCS-C2.2 C | Planned |  | SWIFT Provider - + Fees ( LGMIS) East Nets Company" For Year 2011" | NCS | Prior | DC | No | No | NA | NA | 2010-12-15 | 2010-12-22 | NA | NA | NA | 2010-12-27 | NA | 2011-01-01 | 18000 | $ |  | EastNets | 0
Revised
|  |  |  | Actual | [7 empty] | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-24 | 2011-02-23
2.2 | 35 | 35/C2.2-D/NCS/PFMP/13 | NCS-C2.2 D | Planned |  | SWIFT Provider - + Fees ( LGMIS) East Nets Company " For year 2012" | NCS | Prior | DC | No | No | NA | NA | NA | NA | NA | NA | NA | NA | 2013-03-15 | 2013-03-20 |  |  |  |  | 2015-12-30
Revised
|  |  |  | Actual | [17 empty] | 80000 | $ |  | East Nets
5 | 36 | 36/C5/NCS/PFMP/13 | NCS- PMU - OP | Planned |  | Financial Management system maintenance(CEW) | NCS | Prior | DC | No | No | NA | NA | 2011-01-09 | NA | 2011-01-14 | 2011-01-21 | 2011-01-21 | 2011-01-28 | NA | 2011-02-02 |  |  |  |  | 2012-08-01
|  |  |  | Revised1 | [7 empty] | NA | NA | 2012-05-09 | NA | 2012-05-14 | 2012-05-21 | 2012-05-21 | 2012-05-28 | NA | 2012-06-02 |  |  |  |  | 2013-11-30
|  |  |  | Revised2 | [9 empty] | 2013-02-10 |  | 2013-02-20 | 2013-03-08 | 2013-03-08 | 2013-03-16 |  | 2013-03-20
Actual | bar: 2013-05-07 to 2013-06-09
1 | 37 | 37/C1.1-B/NCS/PFMP/13 | NCS-C1.1 B | Planned |  | Enhancing MoF website to publish the GoY fiscal data (budget, final accounts, reports, requirements of OBI, and others) as part of the transparency activities | NCS | Prior | NS | No | No | 2012-11-06 | NA | 2012-12-06 | NA | 2011-01-15 | 2011-01-22 | 2011-01-22 | 2011-01-29 | NA | 2011-02-03 |  |  |  |  | 2011-03-03
|  |  |  | Revised |  |  |  | Prior | NS |  |  |  |  | 2013-04-02 | NA | 2013-04-16 | 2013-04-23 | 2013-04-23 | 2013-04-30 | NA | 2013-05-05 |  |  |  |  | 2013-06-02
|  |  |  | REvied2 |  |  |  | post | [5 empty] | 2014-05-01 | NA | 2014-05-15 | 2014-05-22 | 2014-05-22 | 2014-05-29 | NA | 2014-06-03
Actual
2.2 | 38 | 38/C2.2/G/NS/PFMP/13 | Goods- C2.2 | Planned |  | LGMIS: Furniture | Goods | Post | NS | No | No | NA | NA | 2013-05-01 | NA | 2013-05-15 | 2013-05-29 | 2013-05-29 | 2013-06-05 | NA | 2013-06-12 |  |  |  |  | 2013-07-12
Revised
|  |  |  | Actual | [7 empty] | CANCELLED
2.2 | 39 | 39/C2.3/G/NCB/PFMP/13 | Goods- C2.3 | Planned |  | Process Simplification: Equipments for the Ministry of Finance | Goods | Post | NCB | No | No | NA | NA | 2013-06-01 | NA | 2013-06-08 | 2013-07-08 | 2013-07-08 | 2013-07-22 | NA | 2013-08-05 |  |  |  |  | 1900-02-28
|  |  |  | Revised |  |  |  | Post | NCB |  |  |  |  | 2013-12-17 | NA | 2014-01-02 | 2014-02-03 | 2014-02-03 | 2014-02-25 | NA | 2014-03-09 |  |  |  |  | 2014-05-12
Actual
1 | 40 | 40/C1.1/G/NS/PFMP/13 | Goods- C1.1 | Planned |  | Equipment for budget and planning departments stage 2 | Goods | POST | NS | No | No | NA | NA | 2013-05-05 | NA | 2013-05-19 | 2013-06-09 | 2013-06-09 | 2013-06-19 | NA | 2013-07-03 |  |  |  | Horizon for Technology | 2013-09-01
Revised
|  |  |  | Actual | [9 empty] | 2013-07-21: 2012-10-07 |  |  |  |  | 2012-12-12
2.1 | 41 | 41/C2.1/G/NCB/PFMP/14 | Goods- C2.1 | Planned |  | Roll-out of AFMIS to (4th stage ) 7 governorates Turn-key vendor with assistance from PMU to: Procure hardware build infrastructure | Goods | post | NCB | No | No | NA | NA | 2014-03-25 | 2014-04-04 | 2014-04-11 | 2014-05-23 | 2014-05-23 | 2014-06-13 | 2014-06-20 | 2014-07-04 |  |  |  |  | 2015-01-03
|  |  |  | Revised | [9 empty] | 2014-05-25 | NA | 2014-06-04 | 2014-07-06 | 2014-07-06 | 2014-07-27 | NA | 2014-08-10 |  |  |  |  | 2014-12-30
Actual
2.1 | 42 | 42/C2.1/G/NCB/PFMP/15 | Goods- C2.1 | Planned |  | Roll-out of AFMIS to (5th stage ) 7 governorates Turn-key vendor with assistance from PMU to: Procure hardware build infrastructure | Goods | post | NCB | No | No | NA | NA | 2015-03-25 | 2015-04-04 | 2015-04-11 | 2015-05-23 | 2015-05-23 | 2015-06-13 | 2015-06-20 | 2015-07-04 |  |  |  |  | 2015-12-31
Revised
Actual
2.1 | 43 | 43/C2.1/G/DC/PFMP/13 | Goods- C2.1 | Planned |  | Update Antivirus software (from Jun 2013 to Jun 2014) | Goods | Prior | DC | NO | No | NA | NA | NA | NA | NA | NA | NA | NA | 2013-05-02 | 2013-05-15 |  |  |  | Net Technology | 2014-05-15
Revised
|  |  |  | Actual | [9 empty] | 2013-07-07: 21/6/2013; 2013-07-21: 20/6/2013
2.1 | 44 | 44/C2.1/G/DC/PFMP/14 | Goods- C2.1 | Planned |  | Update Antivirus software (from Jun 2014 to Jun 2015) | Goods | Prior | DC | NO | No | NA | NA | NA | NA | NA | NA | NA | NA | 2014-05-02 | 2014-05-15 |  |  |  |  | 2015-12-31
|  |  |  | Revised | [9 empty] | 2013-07-07: 2014-06-01; 2013-07-21: 2014-06-11 |  |  |  |  | 2015-06-06
Actual
2.1 | 45 | 45/C2.1/G/DC/PFMP/13 | Goods- C2.1 | Planned |  | Furniture for AFMIS | Goods | Post | NS | No | No | NA | NA | 2013-05-15 | NA | 2013-05-29 | 2013-06-12 | 2013-06-12 | 2013-06-19 | NA | 2013-06-29 |  |  |  |  | 2013-07-29
|  |  |  | Revised |  |  |  | Post | NS |  |  |  |  | 2014-01-20 |  | 2014-01-28 | 2014-02-11 | 2014-02-11 | 2014-02-18 |  | 2014-03-02 |  |  |  |  | 2014-04-02
Actual
2.1 | 46 | 46/C2.1/G/DC/PFMP/13 | Goods- C2.1 | Planned |  | Equipments for AFMIS | Goods | Post | NS | No | No | NA |  | 2013-05-20 | NA | 2013-06-03 | 2013-06-17 | 2013-06-17 | 2013-06-24 | NA | 2013-07-04 |  |  |  | شركة راديكس برايت سليوشنز | 2013-08-03
Revised
|  |  |  | Actual |  |  |  | Post | NS |  |  |  |  | 2013-10-23 |  | 2013-11-04 | 2013-11-20 | 2013-11-20 | 2013-12-02 | NA | 2013-12-04 | 29849 | $ |  |  | 2013-12-25
|  | Total |  |  |  | Estimated Cost | [15 empty] | 1175266.08
Signed Contract Value
Grand Total
Formulas:
Bid Invitation (Date) = [Preparation of Bid Document (Date)]+14
Bid Invitation (Date) = [NA]+5
Bid Closing (Date) = [Bid Invitation (Date)]+7
Bid Opening (Date) = [Bid Closing (Date)]
Contract Award Decision (Date) = [Bid Opening (Date)]+14
Contract Signed (Date) = [Contract Award Decision (Date)]+3
Completion of Contract (Date) = [Contract Signed (Date)]+14
Completion of Contract (Date) = [Contract Signed (Date), row below]+60
NA = [Preparation of Bid Document (Date)]+7

## Consultant Services
Procurement Plan for Consultant Services
COMPONENT | SL No. | Reference No. |  | SL No. | Description of Services | Review by Bank (Prior/ Post) | Type of Consultant (Firm/ Individual) | Method of Selection | Advertising for Short listing (Date) | TOR/Shortlist to be Finalized (Date) | RFP Final Draft to be forwarded to the Bank (Date) | No Objection from Bank for TOR (Date)** | No Objection from Bank for Shortlist (Date)** | No Objection from Bank for Final RFP (Date)** | RFP Issued (Date) | Proposal Submission Deadline (Date) | No Objection by the Bank to the Technical Evaluation Report (Date)** | No Objection by the Bank (Technical/ #Combined/ Draft Contract/ Final Contract) (Date)** | Contract Award Date | Contract Signed (Date) | Contract Value | Contract Currency | Contract No. | Name, City, and Country of Contractor (incl. Zip Code if US) | Contract Value | Contract Currency | Name, City, and Country of Contractor (incl. Zip Code if US) | Services Completion (Date) | Comments
1 | 1 | 1/C1.1-A/IC/PFMP/13 | Planned | CS-1.1-A | TA to establish Institutional mechanism to be as process framework link budget to the national plans preparation and to review of MTEF process | Prior | Individual | IC | 2010-12-15 | 2011-01-04 | 2011-01-11 | 2010-12-10 | 2011-01-09 | 2011-01-18 | 2011-01-25 | 2011-02-22 | 2011-03-08 | 2011-03-18 |  | 2011-03-25 | [7 empty] | 2011-05-09
|  |  | Revised1 | [5 empty] | 2012-11-15 | 2012-12-05 | 2012-12-12 | 2012-11-10 | 2012-12-10 | 2012-12-19 | 2012-12-26 | 2013-01-23 | 2013-02-06 | 2013-02-16 |  | 2013-02-23 | [7 empty] | 2013-04-27
|  |  | Revised2 | [5 empty] | 2013-06-05 | 2013-06-25 | 2013-07-02 | 2013-07-07 | 2013-06-30 | 2013-07-09 | 2013-07-16 | 2013-08-13 | 2013-08-27 | 2013-09-06 | 2013-09-13 | 2013-09-20 | [7 empty] | 2013-11-19
|  |  | Revised3 |  |  | Post | Firm | CQS | 2013-08-14 |  |  |  | 2013-11-28 |  | 2014-01-22 | 2014-02-13 |  | 5=Mar-14 | 2014-03-12 | 2014-03-19 | [7 empty] | 2014-05-18
Actual
1 | 2 | 2/C1.1-F/IC/PFMP/13 | Planned | CS-1.1-F | Local TA to compare the budgeted investment projects with the Plans | Post | Individual | IC | 2012-07-15 | 2012-08-04 |  | 2012-07-10 | [7 empty] | 2012-09-03 | [7 empty] | 2012-12-02
|  |  | Revised | [5 empty] | 2013-03-25 | 2013-04-14 | [8 empty] | 2013-04-17 | 2013-04-19 | [7 empty] | 2013-07-08
Actual
1 | 3 | 3/C1.1-B/IC/PFMP/13 | Planned | CS-1.1-B | Local TA to review the status of extra budgetary funds EBFs and special accounts, annex funds and prepare recommendation on the approach to include then in budget and eliminate the unnecessary ones | Post | Individual | IC | 2012-07-15 | 2012-08-04 |  | 2012-07-10 | [7 empty] | 2012-09-03 | [7 empty] | 2012-12-02
|  |  | Revised | [5 empty] | 2013-05-25 | 2013-06-14 |  | 2013-05-20 | [6 empty] | 2013-07-09 | 2013-07-14 | [7 empty] | 2013-10-02
|  |  | Revised2 | [5 empty] | 2014-06-01 | 2014-06-21 |  | 2014-06-28 | [6 empty] | 2014-07-16 | 2014-07-21 | [7 empty] | 2014-08-20
Actual
1 | 4 | 4/C1.2-A/IC/PFMP/12 | Planned | CS-1.2A | TA to enhance cash management system , | Prior | Individual | IC | 2011-04-15 | 2011-05-05 | NA | 2011-04-10 | 2011-05-10 | NA | NA | NA | NA | 2011-05-24 |  | 2011-05-31 | [7 empty] | 2012-02-05
|  |  | Revised1 |  |  | Post |  |  | 2012-09-15 | 2012-10-05 | NA | 2012-09-10 | 2012-10-10 | NA | NA | NA | NA | 2012-10-24 |  | 2012-10-31 | [6 empty] | Nathan Hansford | 2013-07-08
|  |  | Revised2 |  |  | Post | Individual | IC | 2012-09-15 | 2012-10-05 | 2012-10-12 | 2012-09-10 | 2012-10-10 | 2012-10-19 | 2012-10-26 | 2012-11-23 | 2012-12-07 | 2012-12-17 |  | 2012-12-24 | [7 empty] | 2013-02-27
|  |  | Actual | [5 empty] | 2012-07-21 | 2012-05-09 | NA | 2012-06-20 | [5 empty] | 2013-01-06 |  | 2012-12-08 |  |  |  |  | 142559.78 |  |  | 2013-03-01
|  |  | Actual 1 | [24 empty] | 2013-12-31
Actual2
1 | 5 | 5/C1.2-C/IC/PFMP/11 | Planned | CS-1.2-C | Translation contract | Post | Individual | IC | 2011-01-01 | 2011-01-21 | NA | NA | NA | NA | NA | NA | NA | NA |  | 2011-01-28 | [6 empty] | Ali Almalahani +Star for translation | 2012-06-11
|  |  | Revised | [5 empty] | .
|  |  | Actual | [5 empty] | 2011-05-04 | 2011-05-03 | NA | NA | NA | NA | NA | NA | NA | NA | 2011-12-07 | 2011-12-12 |  |  |  |  | 18094.12 | $ |  | 2012-01-01
1 | 6 | 6/C1.2-F/F/PFMP/12 | Planned | CS1.2-F | TA to revise the Government Accounting manual to be in line with the international Publics Accounting standards IPSAS | Post | Firm | CQS | 2011-01-01 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2011-01-01 | [6 empty] | Devpar Financial Consulting Ltd | 2011-06-30
|  |  | Revised | [5 empty] | 2012-04-01 | 2012-04-29 | 2012-05-11 | 2011-09-10 | 2012-05-06 | 2012-05-25 | 2012-05-27 | 2012-07-08 | 2012-08-07 | 2012-08-21 |  | 2012-08-28 | [7 empty] | 2013-08-28
|  |  | Actual | [5 empty] | 2012-06-15 | 2012-05-09 | NA | 2012-05-26 | NA | NA | NA | 2012-08-11 | NA | 2013-09-16 |  | 2013-10-24 |  |  |  |  | 129308.4 | $ |  | 2014-04-30
1 | 7 | 7/C1.2-G/F/PFMP/12 | Planned | CS-1.2-G | TA to revise the Publics Business Enterprises Accounting manual to be in line with the international Accounting standards IFRS | Post | Firm | QCBS | 2011-02-15 | 2011-03-15 | 2011-03-27 | 2011-02-01 | 2011-03-22 | 2011-04-10 | 2011-04-12 | 2011-05-24 | 2011-06-23 | 2011-07-07 |  | 2011-07-14 | [7 empty] | 2012-07-13
|  |  | Revised |  |  |  |  | CQS | 2012-04-01 | 2012-10-06 | 2012-11-15 |  | 2012-11-15 | 2012-11-29 | 2012-12-01 | 2012-12-15 | 2012-12-30 | 2013-01-13 |  | 2013-01-17 | [7 empty] | 2013-12-30
|  |  | Actual | [5 empty] | 2012-06-15 | 2012-10-07 |  | 2012-03-19 | NA | NA | NA |  | NA | NA
1 | 8 | 8/C1.2-H/IC/PFMP/12 | Planned | CS1.2 H | TA to evaluate the Pilot systems of CC | Post | Individual | IC | 2012-06-15 | 2012-07-15 | NA | NA | NA | NA | NA | 2012-07-24 | NA | NA | 2012-08-01 | 2012-08-08 | [7 empty] | 2012-10-23
|  |  | Revised | [7 empty] | CANCELLED & COMBINED WITH SC-1.2A
Actual
2.1 | 9 | 9/C2.1/F/PFMP/10 | Planned | CS-2.1 | Assessment and recommendation for AFMIS's Datacenter network and web enabling | Prior | Firm | QCBS | 2009-11-02 | 2009-11-17 | 2009-11-23 | 2009-11-01 | 2009-11-22 | 2009-11-25 | 2009-11-27 | 2009-12-27 | 2010-01-05 | 2010-01-07 | 2010-01-17 | 2010-01-19
|  |  | Revised1 |  |  | Prior | Firm | QCBS | 2010-06-01 | 2010-10-02 | 2010-10-02 | 40408 | 2010-10-05 | 2010-10-06 | 2010-10-08 | 2010-11-05 | 2010-11-19 | 2010-12-03 | 2010-12-10 | 2010-12-12
|  |  | Revised2 |  |  |  |  | SSS | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2012-05-02 | 2012-05-15 | 2012-05-20 |  |  |  |  | 267455.29 | $ | Keller | 2012-08-20
|  |  | Actual | [5 empty] | I June 2010 | 2010-10-03 | 2010-10-09 | 2010-08-18 | 2010-10-03 | 2010-10-10 | 2010-10-15 | 2010-11-15 | 2011-01-08 | 2011-07-18 | 2011-07-20 | 2011-08-01 |  |  |  |  | 267455.29 | $ | Keller
2.1 | 11 | 11/C2.1-A/F/PFMP/12 | Planned | CS-2.1-A | Development of MTEF and updating the budget preparation module | Post | Individual | IC | 2011-06-01 | 2011-06-21 | NA | NA | NA | NA | NA | NA | NA | NA |  | 2011-07-05 | [7 empty] | 2011-09-12 | في انتظار مخرجات المكون الاول الجزء الاول
|  |  | Revised1 |  | Updating the budget system | Prior | Firm | SSS | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2012-12-31 | NA | 2013-01-15 | [7 empty] | 2013-12-15
|  |  | Revised2 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2013-05-01 | 2013-05-15 | 2013-05-29
|  |  | Revised3 |  |  | post |  | CQS
Actual
2.1 | 12 | 12/C2.1-B/F/PFMP/12 | Planned | CS-2.1-B | Development of AFMIS web-enabled | Prior | Firm | QCBS | 2011-10-03 | 2011-10-23 | 2011-10-30 | 2011-09-28 | 2011-10-28 | 2011-11-06 | 2011-11-13 | 2011-12-11 | 2011-12-25 | 2012-01-04 | 2012-01-06 | 2012-01-11 | [7 empty] | 2012-08-02
|  |  | Revised1 | [5 empty] | 2012-10-01 | 2012-10-21 | 2012-10-28 | 2012-09-26 | 2012-10-26 | 2012-11-04 | 2012-11-11 | 2012-12-09 | 2012-12-23 | 2013-01-02 | 2012-01-07 | 2013-01-09 | [7 empty] | 2013-08-01 | تقرر تطوير النظام الى Web Enabled) بالتزامن مع انتهاء مركز البيانات
|  |  | Revised2 | [5 empty] | 2013-07-01 | 2013-07-21 | 2013-07-28 | 2013-06-26 | 2013-07-26 | 2013-08-04 | 2013-08-11 | 2013-09-08 | 2013-09-22 | 2013-10-02 | 2012-01-07 | 2013-10-09 | [7 empty] | 2014-05-01
|  |  | Revised3 | [5 empty] | 2014-04-30 | 2014-05-20 | 2014-05-27 | 2014-04-25 | 2014-05-25 | 2014-06-03 | 2014-06-10 | 2014-07-08 | 2014-07-22 | 2014-08-01 | 2014-06-07 | 2014-08-08
Actual
2.1 | 13 | 13/C2.1-C/F/PFMP/12 | Planned | CS-2.1-C | AFMIS enhancement and maintenance | Prior | Firm | QCBS | 2011-01-04 | 2011-01-24 | 2011-01-31 | 2010-12-30 | 2011-01-29 | 2011-02-07 | 2011-02-14 | 2011-03-14 | 2011-03-28 | 2011-04-07 |  | 2011-04-14 | [7 empty] | 2012-06-30
|  |  | Revised1 |  | AFMIS enhancement and maintenance FOR Two YEAR | Prior | Firm | SSS | NA | 2012-03-21 | NA | 2012-04-07 | NA | NA | NA | NA | NA | 2012-04-18 | 2012-04-19 | 2012-04-25 | [7 empty] | 2013-10-30 | يقوم بعملية الصيانة حاليا فريق الافميس في المشروع بسبب الخلاف مع الشركة
|  |  | Revised2 |  |  | Post |  | CQS | NA | 2014-05-21 | NA | 2014-06-07 | NA | NA | NA | NA | NA | 2014-06-14 | 2014-06-21 | 2014-06-28 | [7 empty] | 2015-12-20
Actual
2.1 | 14 | 14/C2.1-D/F/PFMP/13 | Planned | CS-2.1-D | Develop commitment control system in AFMIS | Prior | Firm | SS | 2013-02-11 | 2013-03-03 | 2013-03-10 | 2013-02-06 | 2013-03-08 | 2013-03-17 | 2013-03-24 | 2013-04-21 | 2013-05-05 | 2013-05-15 | 2012-01-06 | 2013-05-22 | [7 empty] | 2013-10-19
|  |  | Revised1 | [5 empty] | 2013-06-11 | 2013-07-01 | 2013-07-08 | 2013-06-06 | 2013-07-06 | 2013-07-15 | 2013-07-22 | 2013-08-19 | 2013-09-02 | 2013-09-12 | 2012-01-06 | 2013-09-19 | [8 empty] | وسيتم مراجعتها مع البنك الدولي لدمجها مع تطوير النقدية
|  |  | Revised2 |  |  | Post | Firm | CQS | 2014-07-01 | 2014-07-21 | 2014-07-28 | 2014-06-26 | 2014-07-26 | 2014-08-04 | 2014-08-11 | 2014-09-08 | 2014-09-22 | 2014-10-02 | 2012-01-06 | 2014-10-09
Actual
2.2 | 15 | 15/C2.2-A/IC/PFMP/13 | Planned | CS-2.2-A | Network Security: To assess the network security and recommend a suitable security system. | Post | Individual | IC | 2012-01-01 | 2012-01-21 | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-02-04 | [7 empty] | 2012-05-04
|  |  | Revised |  |  | Prior | Individual | IC | 2013-06-01 | 2013-06-21 | NA | NA | NA | NA | NA | NA | NA | NA | 2013-02-02 | 2013-02-04 | [7 empty] | 2013-05-05
|  |  | Actual | [5 empty] | cancelled and both were renamed in one under
2.2 | 16 | 16/C2.2-B/IC/PFMP/13 | Planned | CS-2.2-B | LGMIS: International Consultancy - Senior Advisor to help in the roll out of the system and further development | Post | Individual | IC | \ | #VALUE! | NA | NA | NA | NA | NA | NA | NA | NA |  | #VALUE! | [7 empty] | #VALUE!
|  |  | Revised |  |  | Prior | Individual | IC | 2013-06-01 | 2013-06-21 | NA | NA | NA | NA | NA | NA | NA | NA | 2012-02-02 | 2013-07-05 | [7 empty] | 2013-10-03
|  |  | Actual | [5 empty] | cancelled
2.3 | 17 | 17/C2.3-A/IC/PFMP/13 | Planned | CS-2.3-A | TA to implement the process simplification's design recommended by the consultant's study done in the process simplification phase 1 | Post | Individual | IC | 2011-02-01 | 2011-02-21 | NA | 2011-01-27 | 2011-02-26 | NA | NA | NA | NA | 2011-03-12 |  | 2011-03-19 | [7 empty] | 2011-09-15
|  |  | Revised1 |  |  | Prior | Individual | IC | 2012-09-01 | 2012-09-21 | NA | 2012-08-27 | 2012-09-26 | NA | NA | NA | NA | 2012-10-10 | 2012-10-11 | 2012-10-17 | [7 empty] | 2013-04-15
|  |  | Revised2 |  |  | Prior | Individual | IC | 2014-05-30 | 2014-06-19 | NA | 2014-05-25 | 2014-06-24 | NA | NA | NA | NA | 2014-07-08 | 2012-10-12 | 2014-07-15 | [7 empty] | 2015-01-11
Actual
2.3 | 18 | 18/C2.3-B/IC/PFMP/12 | Planned | CS-2.3-B | TA review and re-design to simplify the present work flow process of MoF with its clients and line ministries | Prior | Individual | SS | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2012-03-17 | 2012-03-28 | 2012-04-04 | [7 empty] | 2012-10-01 | Completed
Revised
|  |  | Actual | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2012-09-17 | 2012-09-17 | 2012-09-18 |  |  |  |  | 51750
3 | 19 | 19/C3.2-A/IC/PFMP/12 | Planned | CS-3.2.A | TA to assess the capacity of the Fiscal Institute to conduct the rollout training of reform | Prior | Individual | IC | 2011-01-01 | 2011-01-21 | NA | NA | NA | NA | NA | NA | NA | NA |  | 2011-02-04 | [7 empty] | 2011-08-24
|  |  | Revised1 | [5 empty] | 2012-09-11 | 2012-10-01 | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-10-15 | [7 empty] | 2012-07-19
|  |  | Revised2 | [5 empty] | 2012-03-11 | 2012-04-03 | NA | 2012-03-06 | NA | NA | 2012-04-24 | 2012-05-22 | 2012-06-05 | 2012-06-25 |  | 2013-02-12 | [7 empty] | 2013-03-22
|  |  | Actual | [16 empty] | 2012-12-04 |  |  |  |  | 18000 |  |  | 13-Mar-13
3 | 20 | 20/C3.1-A/IC/PFMP/11 | Planned | CS-3.1-A | Preparing the Training Course Materials for Guidelines and SBDs and Conducting Training of Trainers (TOT) for Guidelines | Post | Individual | IC | 2011-01-01 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2011-01-01 | [7 empty] | 2011-01-31
|  |  | Revised1 | [5 empty] | 2011-09-11 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2011-10-01 | [6 empty] | Hiaham Al Labadi | 2011-10-30
|  |  | Revised2 |  |  | Prior | Individual | IC | 2011-09-11 | 2011-10-01 | NA | 2011-09-06 | NA | NA | NA | 2012-11-19 | 2012-12-03 | 2013-02-25 |  | 2013-03-04 | [7 empty] | 2014-02-25
|  |  | Revised3 | [12 empty] | 2013-05-15 | 2013-06-05 |  | 2013-05-29 | 2013-06-05
|  | 20/C3.1-A/IC/PFMP/13 | Actual | [8 empty] | 2013-01-11 | [5 empty] | 03-Oct-13 | 2013-10-13 | 2013-12-15 |  |  |  |  | 36698.4 |  |  | 2014-03-16
3 | 21 | 21/C3.1-B/IC/PFMP/12 | Planned | CS-3.1-B | Conducting Training of Trainers (TOT) for Guidelines and SBDs | Post | Individual | IC | 2011-01-01 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2011-01-01 | [7 empty] | 2011-01-31 | Deleted
|  |  | Revised |  |  | Prior | Individual | IC | 2012-06-15 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-07-20 | [7 empty] | 2012-08-21
|  |  | Actual | [8 empty] | Cancelled
3 | 22 | 42/C3-1C/S/PFMP/12 | Planned | CS-3.1-C | Conducting Training of Trainers (TOT) for National Proc. Law and Billows | Post |  |  | 2012-09-17 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-10-22 |  |  |  | ILO |  |  |  | 2012-11-23 | Deleted
|  |  | Revised |  |  | Prior | Individual | IC |  | Cancelled
Actual
3 | 23 | 23/C3.3-D/IC/PFMP/11 | Planned | CS-3.3-D | Retreat for HATC Committee members with host a members from stockholders | Post |  |  | 2011-09-19 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2011-10-25 | [7 empty] | 2011-11-26
|  |  | Revised |  |  |  | Individual | IC | [20 empty] | Completed
|  |  | Actual | [21 empty] | 11183
3 | 24 | 24/C3.3-B/IC/PFMP/12 | Planned | SC-3.3-B | Prepare a strategy for the HATC | Post | Individual |  | 2011-09-23 | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2011-10-29 | [6 empty] | Better continuous for previous work | 2011-11-29
|  |  | Revised |  |  | Prior | Individual | SSS | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2012-05-03 |  | 2012-05-10 | [7 empty] | 2012-05-15 | Completed
|  |  | Actual | [21 empty] | 69016 |  |  | 2012-07-20
3 | 25 | 25/C3.3-A/F/PFMP/12 | Planned | CS-3.3-A | Supporting HATC in establishing a system of Registration and Follow-up of all Public Contracts and establishing a Public Complaints Management System | Post | Firm | CQS | 2011-01-15 | 2011-02-04 | 2011-02-11 | 2011-01-10 | 2011-02-09 | 2011-02-18 | 2011-02-25 | 2011-03-25 | 2011-04-08 | 2011-04-18 |  | 2011-04-25 | [7 empty] | 2012-07-08
|  |  | Revised1 | [5 empty] | 2012-09-27 | 2012-10-17 | 2012-10-24 | 2012-09-22 | 2012-10-22 | 2012-10-31 | 2012-11-07 | 2012-12-05 | 2012-12-19 | 2012-12-29 |  | 2013-01-05 | [7 empty] | 2014-03-21
|  |  | Revised2 |  |  | Prior | Firm | CQS | 2012-09-27 | 2012-10-17 | 2012-10-24 | 2012-09-22 | 2012-10-22 | 2012-10-31 | 2012-11-07 | 2012-12-05 | 2012-12-19 | 2012-12-29 |  | 2013-01-05 | [7 empty] | 2013-05-11
|  |  | Revised3 | [9 empty] | 2013-05-10 | 2013-05-17 | 2013-05-24 | 2013-06-21 | 2013-07-05 | 2013-07-15 |  | 2013-07-22
|  |  | Actual | [14 empty] | 2014-04-30
4 | 26 | 26/C4.2-A/F/PFMP/13 | Planned | CS-4.2-A | improving COCA’s audit manual and methodology and supporting its implementation consistent with International Standards on Auditing and good practices following risk-based audit methodology and using automated audit program | Post | Firm | CQS | 2011-05-01 | 2011-05-21 | 2011-05-28 | 2011-04-26 | 2011-05-26 | 2011-06-04 | 2011-06-11 | 2011-07-09 | 2011-07-23 | 2011-08-02 |  | 2011-08-09 | [7 empty] | 2012-08-08
|  |  | Revised |  |  | Prior | Firm | CQS | 2013-07-01 | 2013-07-21 | 2013-07-28 | 2013-06-26 | 2013-07-26 | 2013-08-04 | 2013-08-11 | 2013-09-08 | 2013-09-22 | 2013-10-02 |  | 2013-10-09 | [7 empty] | 2014-07-06
Actual
4 | 27 | 27/C4.3-A/IC/PFMP/12 | Planned | CS-4.3-A | COCA: Preparing and adopting a mid & long term strategic plan which includes an overall organizational strategy, capacity building strategy, etc. | Post | Individual | IC | 2011-02-01 | 2011-02-21 | NA | NA | NA | NA | NA | NA | NA | NA |  | 2011-03-07 | [7 empty] | 2011-06-05
|  |  | Revised | [5 empty] | 2012-04-01 | 2012-04-21 | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-06-10 | [6 empty] | Dr.Maqbouleh Hammoueh | 2012-09-08
|  |  | Actual | [5 empty] | 2012-03-31 | 2011-02-11 | NA | 2011-02-05 | NA | NA | NA | 11 Aug.2012 | NA | 2012-10-23 | 15-10-12 | 2012-11-02 |  |  |  |  | 39132 | $ |  | 2013-07-10
|  |  | actual1 | [16 empty] | 1-Aug-13 | [7 empty] | 31-Dec-13 | amendment no.1 to contract extended 1/8/2014-31/12/2013
|  |  | actual2 | [24 empty] | 31-Dec-14 | amendment no.2 to contract extended 1/1/2014-31/12/2014
4 | 28 | 28/C4.2-B/IC/PFMP/13 | Planned | CS-4.2-B | TA to prepare a training manual for audit procurement and deliver the course to the COCA trainers on Procurement | Post | Individual | IC | 2012-12-11 | 2012-12-31 | 2013-01-07 | 2012-12-06 | 2013-01-05 | 2013-01-14 | 2013-01-21 | 2013-02-18 | 2013-03-04 | 2013-03-14 |  | 2013-03-21 | [7 empty] | 2013-05-05
|  |  | Revised | [5 empty] | 2013-06-15 | 2013-07-05 | 2013-07-12 | 2013-06-10 | 2013-07-10 | 2013-07-19 | 2013-07-26 | 2013-08-23 | 2013-09-06 | 2013-09-16 |  | 2013-09-23
|  |  | Revised2 | [5 empty] | 2014-06-15 | 2014-07-05 | 2014-07-12 | 2014-06-10 | 2014-07-10 | 2014-07-19 | 2014-07-26 | 2014-08-23 | 2014-09-06 | 2014-09-16 |  | 2014-09-23
Actual
5 | 29 | 29/C5-OP/F/PFMP/12 | Planned | CS-OP | External Auditor | Post | Firm | LCS | 2010-11-15 | 2010-12-05 | NA | 2010-11-10 | 2010-12-10 | NA | NA | NA | NA | 2010-12-26 |  | 2011-01-01 | [7 empty] | 2012-03-16
|  |  | Revised | [5 empty] | 2012-05-15 | 2012-06-04 | NA | 2012-05-10 | 2012-06-09 | NA | NA | NA | NA | 2012-06-25 |  | 2013-02-20 | [7 empty] | 2015-12-31
Actual
5 | 30 | 30/C5-OP1/IC/PFMP/10 | Planned | CS-OP-1 | Project Executive Director | Prior | Individual | IC | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2010-12-28 |  | 2011-01-01 | [7 empty] | 2012-06-30
Revised
|  |  | Actual | [7 empty] | NA | NA | NA | NA | NA | NA | NA | 2011-02-21 |  | 2011-01-01 | [7 empty] | 2016-03-31
|  | 30/C5-OP1/IC/PFMP/14 | [6 empty] | 2014-04-01
5 | 31 | 31/C5-OP2/IC/PFMP/10 | Planned | CS-OP-2 | Technical Coordinator | Prior | Individual | IC | 2010-11-15 | 2010-12-05 | NA | 2010-11-10 | 2010-12-10 | NA | NA | NA | NA | 2010-12-26 |  | 2011-01-01 | [7 empty] | 2012-06-30
Revised
|  |  | Actual1 | [7 empty] | NA | NA | NA | NA | NA | NA | NA | 2011-02-21 |  | 2011-01-01 | [7 empty] | 2016-03-31
|  | 31/C5-OP2/IC/PFMP/14 | Actual2 | [7 empty] | NA | NA | NA | NA | NA |  |  | 2014-01-23 |  | 2014-01-01 | [7 empty] | 2014-12-31
5 | 32 | 32/C5-OP3/IC/PFMP/10 | Planned | CS-OP-3 | PFM Senior Implementation Specialist | Prior | Individual | IC | 2010-11-15 | 2010-12-05 | NA | 2010-11-10 | 2010-12-10 | NA | NA | NA | NA | 2010-12-26 |  | 2011-01-01 | [7 empty] | 2012-06-30
|  |  | Revised | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-01-01 | [7 empty] | 2012-12-31
|  |  | Actual1 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-21 |  | 2011-01-01 | [7 empty] | 2011-12-31
|  |  | Actual2 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-01-01 | [7 empty] | 2015-12-31
|  | 32/C5-OP3/IC/PFMP/13 | Actual3 | [5 empty] | 28-Oct-13 | NA | NA | NA | NA | NA | NA | NA | NA | NA
5 | 33 | 33/C5-OP4/IC/PFMP/10 | Planned | CS-OP-4 | IT Senior Implementation Specialist- AFMIS | Prior | Individual | IC | 2010-11-15 | 2010-12-05 | NA | 2010-11-10 | 2010-12-10 | NA | NA | NA | NA | 2010-12-26 |  | 2011-01-01 | [7 empty] | 2012-06-30
|  |  | Revised | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-01-01 | [7 empty] | 2012-12-31
|  |  | Actual1 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-21 |  | 2011-01-01 | [7 empty] | 2011-12-31
|  |  | Actual2 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-22 |  | 2012-01-01 | [7 empty] | 2015-12-31
|  | 33/C5-OP4/IC/PFMP/14 | Actual3 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2014-01-23 |  | 2014-01-01 | [7 empty] | 2014-12-31
5 | 34 | 8/C5-OP5/S/PFMP/10 | Planned | CS-OP-5 | IT Senior Implementation Specialist -LGMIS | Prior | Individual | IC | 2010-11-15 | 2010-12-05 | NA | 2010-11-10 | 2010-12-10 | NA | NA | NA | NA | 2010-12-26 |  | 2011-01-01 | [7 empty] | 2012-06-30
|  |  | Revised | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-01-01 | [7 empty] | 2012-12-31
|  |  | Actual1 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-21 |  | 2011-01-01 | [7 empty] | 2011-12-31
|  |  | Actual2 | [5 empty] | NA | NA | N A | NA | NA | NA | NA | NA | NA | 2011-02-22 |  | 2012-01-01 | [7 empty] | 2015-12-31
|  | 8/C5-OP5/S/PFMP/13 | Actual3 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2013-08-26 |  | 2013-10-01 | [7 empty] | 2013-12-31
|  | 8/C5-OP5/S/PFMP/14 | Actual4 | [14 empty] | 2014-01-23 |  | 2014-01-01 | [7 empty] | 2014-12-31
5 | 35 | 35/C5-OP6/IC/PFMP/10 | Planned | CS-OP-6 | Procurement Specialist | Prior | Individual | IC | 2010-11-15 | 2010-12-05 | NA | 2010-11-10 | 2010-12-10 | NA | NA | NA | NA | 2010-12-26 |  | 2011-01-01 | [7 empty] | 2012-06-30
|  |  | Revised | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-01-01 | [7 empty] | 2012-12-31
|  |  | Actual1 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-21 |  | 2011-01-01 | [7 empty] | 2011-12-31
|  |  | Actual2 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-22 |  | 2012-01-01 | [7 empty] | 2012-12-31
|  | 35/C5-OP6/IC/PFMP/13 | Actual3 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | 2013-02-04 | 2013-02-04 |  | 2013-02-04 | [7 empty] | 2016-03-31
|  | 35/C5-OP6/IC/PFMP/13 | Actual4 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | 2013-09-02 | 2013-09-02 |  | 2013-09-10 | [7 empty] | 2014-12-31
5 | 36 | 36/C5-OP7/IC/PFMP/10 | Planned | CS-OP-7 | Finance Specialist | Prior | Individual | IC | 2010-11-15 | 2010-12-05 | NA | 2010-11-10 | 2010-12-10 | NA | NA | NA | NA | 2010-12-26 |  | 2011-01-01 | [7 empty] | 2012-06-30
|  |  | Revised | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-01-01 | [7 empty] | 2012-12-31
|  |  | Actual1 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-21 |  | 2011-01-01 | [7 empty] | 2011-12-31
|  |  | Actual2 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-22 |  | 2012-01-01 | [7 empty] | 2016-03-31
|  | 36/C5-OP7/IC/PFMP/14 | Actual3 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2014-01-23 |  | 2014-01-01 | [7 empty] | 2014-12-31
5 | 37 | 37/C5-OP8/IC/PFMP/10 | Planned | CS-OP-8 | Executive Secretary | Prior | Individual | IC | 2010-11-15 | 2010-12-05 | NA | 2010-11-10 | 2010-12-10 | NA | NA | NA | NA | 2010-12-26 |  | 2011-01-01 | [7 empty] | 2012-06-30
|  |  | Revised | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-01-01 | [7 empty] | 2012-12-31
|  |  | Actual1 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-21 |  | 2011-01-01 | [7 empty] | 2011-12-31
|  |  | Actual2 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-22 |  | 2012-01-01 | [7 empty] | 2016-03-31
|  | 37/C5-OP8/IC/PFMP/14 | ctual3 | [14 empty] | 2014-01-23 |  | 2014-01-01 | [7 empty] | 2014-12-31
5 | 38 | 38/C5-OP9/IC/PFMP/10 | Planned | CS-OP-9 | M & E Specialist | Prior | Individual | IC | 2010-11-15 | 2010-12-05 | NA | 2010-11-10 | 2010-12-10 | NA | NA | NA | NA | 2010-12-26 |  | 2011-01-01 | [7 empty] | 2012-06-30
|  |  | Revised | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-01-01 | [7 empty] | 2012-12-31
|  |  | Actual1 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-21 |  | 2011-01-01 | [7 empty] | 2011-12-31
|  |  | Actual2 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-22 |  | 2012-01-01 | [7 empty] | 2015-12-31
|  | 38/C5-OP9/IC/PFMP/13 | Actual3 | [16 empty] | 2013-05-01 | [7 empty] | 2015-12-31
|  | 38/C5-OP9/IC/PFMP/14 | Actual4 | [14 empty] | 2014-01-23 |  | 2014-01-01 | [7 empty] | 2014-12-31
2.2 | 39 | 39/C2.2-LC1/IC/PFMP/10 | Planned | CS-2.2-LC1 | Senior Technical Engineer ( LGMIS) | Prior | Individual | IC | 2010-11-15 | 2010-12-05 | NA | 2010-11-10 | 2010-12-10 | NA | NA | NA | NA | 2010-12-26 |  | 2011-01-01 | [7 empty] | 2012-06-30
|  |  | Revised | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-01-01 | [7 empty] | 2012-12-31
|  |  | Actual1 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-21 |  | 2011-01-01 | [7 empty] | 2011-12-31
|  |  | Actual2 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-22 |  | 2012-01-01 | [7 empty] | 2015-12-31
|  | 39/C2.2-LC1/IC/PFMP/14 | Actual3 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2014-01-23 |  | 2014-01-01 | [7 empty] | 2014-12-31
2.2 | 40 |  | Planned | CS-2.2-LC2 | Senior Technical Specialist ( LGMIS) | Prior | Individual | IC | 2010-11-15 | 2010-12-05 | NA | 2010-11-10 | 2010-12-10 | NA | NA | NA | NA | 2010-12-26 |  | 2011-01-01 | [7 empty] | 2012-06-30
|  | 40/C2.2-LC2/IC/PFMP/10 | Revised | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-01-01 | [7 empty] | 2012-12-31
|  |  | Actual1 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-21 |  | 2011-01-01 | [7 empty] | 2011-12-31
|  |  | Actual2 | [8 empty] | NA | NA | NA | NA | NA | NA | 2011-02-22 |  | 2012-01-01 | [7 empty] | 2015-12-31
|  | 40/C2.2-LC2/IC/PFMP/13 | Actual3 | [5 empty] | 29-Sep-13 | NA | NA | NA | NA | NA | NA | NA | NA | 2014-01-23 |  | 2014-01-01 | [7 empty] | 2014-12-31
2.2 | 41 |  | Planned | CS-2.2-LC3 | Senior Technical Specialist ( LGMIS) | Prior | Individual | IC | 2010-11-15 | 2010-12-05 | NA | 2010-11-10 | 2010-12-10 | NA | NA | NA | NA | 2010-12-26 |  | 2011-01-01 | [7 empty] | 2012-06-30
|  | 41/C2.2-LC3/IC/PFMP/10 | Revised | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-01-01 | [7 empty] | 2012-12-31
|  |  | Actual1 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-21 |  | 2011-01-01 | [7 empty] | 2011-12-31
[9 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-22 |  | 2012-01-01 | [7 empty] | 2015-12-31
|  | 41/C2.2-LC3/IC/PFMP/13 | Actual2 | [5 empty] | 29-Sep-13 | NA | NA | NA | NA | NA | NA | NA | NA | 2014-01-23 |  | 2014-01-01 | [7 empty] | 2014-12-31
2.2 | 42 | 42/C2.2-LC4/IC/PFMP/10 | Planned | CS-2.2-LC4 | Administrative Assistant ( LGMIS) | Prior | Individual | IC | 2010-11-15 | 2010-12-05 | NA | 2010-11-10 | 2010-12-10 | NA | NA | NA | NA | 2010-12-26 |  | 2011-01-01 | [7 empty] | 2012-06-30
|  |  | Revised | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-01-01 | [7 empty] | 2012-12-31
|  |  | Actual1 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-21 |  | 2011-01-01 | [7 empty] | 2011-12-31
|  |  | Actual2 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-22 |  | 2012-01-01 | [7 empty] | 2012-12-31
|  | 42/C2.2-LC4/IC/PFMP/13 | Actual3 | [5 empty] | NA | NA | NA | NA | NA | MA | MA | NA | 2013-03-19 | 2013-03-19 |  | 2013-03-25 | [7 empty] | 2015-12-31
|  | 42/C2.2-LC4/IC/PFMP/14 | [15 empty] | 2014-01-23 |  | 2014-01-01 | [7 empty] | 2014-12-31
2.1 | 43 | 43/C2.1-LC1/IC/PFMP/10 | Planned | CS-2.1-LC-1 | Senior Engineer (AFMIS) | Prior | Individual | IC | 2010-11-15 | 2010-12-05 | NA | 2010-11-10 | 2010-12-10 | NA | NA | NA | NA | 2010-12-26 |  | 2011-01-01 | [7 empty] | 2012-06-30
|  |  | Revised | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-01-01 | [7 empty] | 2012-12-31
|  |  | Actual1 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-21 |  | 2011-01-01 | [7 empty] | 2011-12-31
|  |  | Actual2 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-22 |  | 2012-01-01 | [7 empty] | 2015-12-31
2.1 | 44 | 44/C2.1-LC2/IC/PFMP/10 | Planned | CS-2.1-LC-2 | Technical Specialist (AFMIS) | Prior | Individual | IC | 2010-11-15 | 2010-12-05 | NA | 2010-11-10 | 2010-12-10 | NA | NA | NA | NA | 2010-12-26 |  | 2011-01-01 | [7 empty] | 2012-06-30
|  |  | Revised | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | NA |  | 2012-01-01 | [7 empty] | 2012-12-31
|  |  | Actual1 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-21 |  | 2011-01-01 | [7 empty] | 2011-12-31
|  |  | Actual2 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2011-02-22 |  | 2012-01-01 | [7 empty] | 2015-12-31
|  | 44/C2.1-LC2/IC/PFMP/14 | Actual3 | [5 empty] | NA | NA | NA | NA | NA | NA | NA | NA | NA | 2014-01-23 |  | 2014-01-01 | [7 empty] | 2014-12-31
5 | 45 | 45/C5-OP10/IC/PFMP/10 | Planned | CS-OP-10 | PRTOJECT ACCOUNTANT | Prior | Individual | IC
Revised
|  |  | Actual | [24 empty] | 2016-03-31
|  | 45/C5-OP10/IC/PFMP/14 | Actual | [14 empty] | 2014-01-23 |  | 2014-01-01 | [7 empty] | 2014-12-31
1 | 46 | 46/C1.1-B/IC/NCS/PFMP/13 | Planned | NCS-C1.1 B | Enhancing MoF website to publish the GoY fiscal data (budget, final accounts, reports, requirements of OBI, and others) as part of the transparency activities | Prior | Firm | QCBS |  |  | 2013-04-02
Revised
|  |  | Actual | [5 empty] | 2013-02-12 | [10 empty] | 2013-07-19
2.2 | 47 | 47/C2.2/IC/PFMP/13 | Planned | CS-2.2 | LGMIS: consultant to prepare functional requirements to upgrade LGMIS to include additional features to meet the MOF needs and requirements relating to the loans and grants | Prior | Individual | IC | 2013-07-01
|  |  | Revised |  |  |  | Firm |  |  | 5-feb-14
Actual
2.1 | 48 | 48/C2.1/F/PFMP/13 | Planned | CS-2.1 | Develop Cash Management System in AFMIS | Prior | Firm | CQS | 2013-08-06 | 2013-08-26 | 2013-09-02 | 2013-08-01 | 2013-08-31 | 2013-09-09 | 2013-09-16 | 2013-10-14 | 2013-10-28 | 2013-11-07 | 2012-01-06 | 2013-11-14 | [7 empty] | 2014-06-12 | متعلق بمخرجات المكون الاول
|  |  | Revised | [5 empty] | 2014-07-01 | 2014-07-21 | 2014-07-28 | 2014-08-02 | 2014-07-26 | 2014-08-04 | 2014-08-11 | 2014-09-08 | 2014-09-22 | 2014-10-02 | 2014-10-02 | 2014-10-09
Actual
2.2 | 49 | 15/C2.2-C/IC/PFMP/14 | Planned | CS-2.2-C | Transfer system from web enabled to web based system | Prior | Firm | CQS | 2014-08-04 | 2015-01-01 | 2015-01-08 | 2014-07-30 | 2015-01-06 | 2015-01-15 | 2015-01-22 | 2015-02-19 | 2015-03-05 | 2015-03-14 | 2014-11-07 | 2015-03-21 | [7 empty] | 2015-06-12
Revised
Actual
|  | Total |  |  | Estimated Cost | [19 empty] | 456630.41
Signed Contract Value
Grand Total
Formulas:
TOR/Shortlist to be Finalized (Date) = [Advertising for Short listing (Date)]+20
No Objection from Bank for TOR (Date)** = [Advertising for Short listing (Date)]-5
No Objection from Bank for TOR (Date)** = [TOR/Shortlist to be Finalized (Date)]+7
RFP Issued (Date) = [NA]+7
Proposal Submission Deadline (Date) = [RFP Issued (Date)]+28
Contract Signed (Date) = [Contract Award Date]+7
Contract Signed (Date) = [TOR/Shortlist to be Finalized (Date)]+30
Services Completion (Date) = [Contract Signed (Date)]+45
Services Completion (Date) = [Contract Signed (Date)]+60+5
Contract Award Date = [TOR/Shortlist to be Finalized (Date)]+3
Contract Award Date = [Proposal Submission Deadline (Date)]+14
Advertising for Short listing (Date) = [No Objection from Bank for TOR (Date)**]+14
NA = [TOR/Shortlist to be Finalized (Date)]+7
NA = [NA]+7
Note on F73: المشتريات: التأكد من التنفيذ

## Capacity Building
Capacity Building Activities
SL. No. | Component | Expected Outcome/ Activity Description | Estimated Duration | Start Date | Completion Date | Comments
1 | 1.1 | Training Sessions on RMSM-X | one week | 2012-11-25 | 2012-12-01 | Done
2 | 1.1 | Workshop to discuss the Institutional Coordination Mechanism | One day | 2014-06-25 | 2014-06-25
3 | 1.1 | Rollout Training of MTEF to all Budgeting Units | 7weeks | 2013-01-28 | 2013-03-04 | shifted to additional fund PP
4 | 1.1 | Training on Budget Reform | One week | 2013-03-15 | 2013-03-22 | shifted to additional fund PP
5 | 1.1 | Study Tour to a country implemented MTBF | 10 days | 2014-02-15 | 2014-02-25 | Korea
6 | 1.2 | Study Tour to a country implemented treasury | one week | 2014-04-09 | 2014-04-16
7 | 1.2 | Workshop to Develop Treasury System TOR | 2 Days | 2014-05-04 | 2014-05-06
8 | 1.2 | Workshop to discuss the final CCS | 1 Day | 2010-10-01 | 2010-10-01 | Done in the PPA Activity
9 | 1.2 | Stakeholder workshop to discuss final treasury Implementation plan | One day | 2014-06-09 | 2014-06-10
10 | 1.2 | Training Sector Staff on Treasury Functions | 6 months | 2014-07-01 | 2014-12-28
11 | 1.2 | Stakeholder workshop to discuss the final cash management system | One day | 2014-05-16 | 2014-05-17
12 | 1.2 | Workshop in Amman for CMS | 3 days | 2011-05-01 | 2011-05-04 | Done (costs of tickets) in the PPA
13 | 1.2 | Capacity building for master trainers on cash management (10 master trainers) in 5 days | Six Days | 2014-02-15 | 2014-02-21
14 | 1.2 | Trial CM Cases Training Workshop | One day | 2014-02-23 | 2014-02-24
15 | 1.2 | CMS Training Workshop for High Officials on Data Analysis and CM Techniques | One day | 2013-07-20 | 2013-07-21 | Done
16 | 1.2 | Stakeholder workshops to discuss first draft of the Gov. Accounting Manual-IPSAS revised | One day | 2014-04-04 | 2014-04-05
17 | 1.2 | Workshop 2 to train senior officials on the Accounting Manuals | Two Days | 2014-04-25 | 2013-04-27
18 | 1.2 | Public Awareness Meeting on Government Accounting | One day | 2014-06-05 | 2014-06-06
19 | 1.2 | Capacity building for master trainers (10 master trainers) in 5 days on the Accounting manual Cash IPSAS revised | Six Days | 2014-05-04 | 2013-05-09
20 | 1.2 | Training 60 trainees on pilot CCS | 13 days | 2012-06-05 | 2012-06-19 | Done in June 2012 and Revised to Train 60 trainees only
21 | 1.2 | Training 60 trainees on pilot CMS | 14 Days | 2012-06-06 | 2012-06-20 | Done in June 2012 and Revised to Train 60 trainees only
22 | 1.2 | TOT for CCS | 5 days | 2014-03-01 | 2014-03-11
| 1.2 | Various Workshops including a Master Training of 10 local trainers | 13 days
23 | 1.2 | National Training Plan for CCS (1,100 trainees) | 300 Days | 2014-08-31 | 2015-06-27
24 | 1.2 | National Training Plan for CMS (1,100 trainees) | 300 Days
25 | 2.1 | Capacity building for the users for AFMIS for first roll-out | 30 days | 2012-01-01 | 2012-05-05 | Done
26 | 2.1 | Capacity building for the users for AFMIS for second roll-out | 70 days | 2012-12-01 | 2013-02-26 | Done
27 | 2.1 | Capacity building for the users for AFMIS for third roll-out | 100 days | 2013-05-29 08:30 | 2014-07-13 13:30
28 | 2.1 | Capacity building for AFMIS staff | 200 days | 2014-03-01 | 2015-03-01
29 | 2.1 | Capacity building for AFMIS end users ( 4th roll-out) | 70 days | 2014-10-04 08:30 | 2015-01-03 12:00
30 | 2.1 | Capacity building for AFMIS end users ( 5th roll-out) | 70 days | 2015-07-01 08:30 | 2015-09-29 12:00
31 | 2.2 | Exchange Programs/Visits Tours / LGMIS | one week | 2014-02-15 | 2014-02-22
32 | 2.2 | Computer Application Training / LGMIS | 23 days | 2014-05-01 | 2014-05-24
33 | 2.2 | Advance Technical Training Courses / LGMIS | One year | 2013-06-01 | 2014-05-27
34 | 2.2 | Present LGMIS to PMUs (approx.40 PMUs) | 11 days | 2014-11-15 | 2014-11-26
35 | 2.2 | Joint Evaluate for LGMIS with PMUs & Stakeholders / LGMIS | 96 days | 2014-02-01 | 2014-09-08
36 | 2.3 | Training for the MOF staff ( process simplification ) | 90 days | 2013-09-01 | 2013-11-30
37 | 3.1 | National training courses for tender committees (Phase one) | Three Years | 2011-05-21 | 2015-05-31
38 | 3.1 | National training courses for the technical committee (Phase one) | Three Years | 2011-09-01 | 2015-09-30
39 | 3.1 | Capacity Building for the New HTB Board members | 6 months | 2014-05-04 | 2014-11-05
| 3.1 | Training HTB technical staff
| 3.1 | training of adminstrative on managerial and admistrative aspects
40 | 3.3 | Complaint review procedures | 2 months | 2014-11-01 | 2015-03-31
41 | 3.3 | HATC Bespoke international training: General procurement policies for the Board of Directors and Technical Office | five days each group | 2014-02-10 | 2014-03-30 | two Groups with durations first 10-14 Feb and the second 17-21 Mar-14 actoal cost $ 128,617.5
42 | 4.1 | Training of trainers for COCA's selected team | one week | 2012-07-01 | 2012-07-08 | Done
43 | 4.1 | Training number of COCA staff on AFMIS modules and processes and its impact on auditing and rollout training to auditors - phase I | 18 months | 2011-07-01 | 2014-12-31 | Done in batches
44 | 4.1 | Training number of COCA staff to become trainers on IT general controls, application controls, IT processes, IT risk and security issues | 6 months | 2014-04-25 | 2014-10-30
45 | 4.1 | Training number of COCA staff on AFMIS modules (150) staff-phase II | 24 months | 2014-01-01 | 2015-12-31
46 | 4.2 | Training for COCA staff on special revenue sectors | 5 days | 2013-05-13 | 2013-05-17 | Done
47 | 4.2 | Study tour for COCA staff on consolidated final accounts |  | 2014-09-01 | 31-Dec15
48 | 4.2 | Training COCA staff on procurement | One year | 2012-07-01 | 2013-06-26 | COCA trainees took the cost with HTB training
49 | 4.2 | Training COCA Staff on Budget Preparation | one week | 2012-09-15 | 2012-09-22 | Done
50 | 4.2 | Training in PFM reforms | 24 months | 2014-01-01 | 31-Dec15 | Commitment Control Planned in August 2013
51 | 4.2 | Workshop to discuss the IT audit manual | 2 days
52 | 4.2 | Strengthening COCA's capacity to enhance its audit manual and methodology |  |  |  | Training of One COCA's staff under the USGAO International Fellowship Program
53 | 4.3 | Two workshops to discuss the COCA strategy | one day | 2012-11-26 | 2013-11-26
Total
Formulas:
Completion Date = [Start Date]+6
Completion Date = [Start Date]

## OC
Republic of Yemen, Public Financial Modernization Project –P117363, Procurement Plan
PMU Operating Cost
SL No. | Expected Outcome/ Activity Description | cost | Estimated Cost US $ | note
1 | IT and Equip Maintenance |  | 20000
2 | Travel Allowances/Per Diem |  | 100000
3 | Office Supplies |  | 15000
4 | Transportation costs and Fuels |  | 15000
5 | Help desk for MIS
6 | Financial Management system maintenance |  |  | Moved to goods
7 | Audit |  |  | Transferred to CS
8 | PEFA Assessments to Measure Project Outcome Indicator
9 | Advertisement |  | 70000
10 | Rent
| Total | 0 | 220000
0
0
0