## General information hr 7638
Procurement Plan
I. General
1. Project information:
Country: CROATIA
Borrower: PORT OF RIJEKA AUTHORITY
Project Name: RIJEKA GATEWAY PROJECT
Loan No.: 7638 - HR
2. Bank’s approval Date of the procurement Plan:
Original: 27 August 2008
Revision 1: 8 February 2013
Revision 2: 16 December 2013
Revision 3: 31 March 2014
Revision 4: 19 May 2014
3. Date of General Procurement Notice: 2 February 2010
4. Period covered by this procurement plan: June 30, 2017
1. Prior Review Threshold: Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement:
| Estimated cost | Procurement / Selection | Prior review by Bank
| (US$) | method
Civil Works
| Above 5,000,000 | ICB | All
| Below 5,000,000 | NCB | First 2 contracts and contracts above US$2,000,000
| Below 100,000 | Shopping | None
Goods
| Above 1,000,000 | ICB | All
| Below 1,000,000 | NCB | First 2 contracts and contract above US$ 500,000
| Below 100,000 | Shopping | None
III. Consulting services
1. Prior Review Threshold: Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement:
All contracts above US$ 100,000 for firms and US$50,000 for individuals are subject to Bank’s prior review.

## Consultants PRA
Procurement Plan Consultant Services -July 16, 2014
Ref. No | Contract Description |  | Review by Bank (Prior/ Post) | Proc. Method | Expected Proposal Opening Date | Contract Signing | Contract Completion | Consultant Name | Signed contract amount in Euro | Explanatory Notes
RGP/QCBS/001/2003 | Detailed engineering and project design study | Plan | Prior | QCBS | Contract finalized | 2003-03-22 | 2009-12-15 | NIPPON KOEI | 1097320
Actual
Revised
RGP/QCBS/004/2003 | Rijeka Port urban area development | Plan | Prior | QCBS | Contract finalized | 2003-02-17 | 2009-09-30 | FVR ROSTOCK | 244733
Actual
Revised
RGP/CQS 003/2002 | Environmental assessment | Plan | Prior | CQS | Contract finalized | 2002-10-15 | 2002-06-30 | URBING D.O.O. | 54419
Actual
Revised
RGP/QCBS/002/2002 | Busines plan for Luka Rijeka d.d. | Plan | Prior | QCBS | Contract finalized | 2002-09-30 | 2003-07-31 | IBM | 179292
Actual
Revised
RGP/QCBS/025/2003 | Supervision of civil works | Plan | Prior | QCBS | Contract finalized | 2005-11-24 | 2010-08-04 | Hill International S.A. | 1830551
Actual
Revised
RGP/LCS/002/2002 | Audit Services | Plan | Prior | LCS | Contract finalized | 2002-05-20 | 2003-03-31 | IrisNova d.o.o. | 25087
Actual
Revised
RGP/IC/005/2003 | Social program for luka Rijeka d.d. | Plan | Prior | IC | Contract finalized | 2002-10-02 | 2003-07-31 | JOLANTA HESS | 27112
Actual
Revised
RGP/QCBS/007/2002 | Assistance to implementation Luka Rijeka Bussines Plan | Plan | Prior | QCBS | Contract finalized | 2007-07-20 | 2011-05-10 | SA IBM | 1113553
Actual
Revised
RGP/CQS/ 018/2004 | Supervision of civil works Wiena berth | Plan | Prior | CQS | Contract finalized | 2005-06-20 | 2006-04-19 | IGH D.D. | 63176
Actual
Revised
RGP/SS/ 022/2005 | Supervision of Silo | Plan | Prior | SS | Contract canceled
Actual
Revised
RGP/SS/ 012/2004 | Preparation of Design | Plan | Prior | SS | Contract finalized | 2004-01-21 | 2004-05-10 | Aleksandar Marković | 11495
Actual
Revised
RGP/SS/ 013/2007 | Preparation of Design | Plan | Prior | SS | Contract finalized | 2004-01-21 | 2004-07-14 | Vladimir Andročec | 24605
Actual
Revised
RGP/SS/ 014/2008 | Preparation of Design | Plan | Prior | SS | Contract finalized | 2004-01-21 | 2004-05-28 | Meho S.Kovačević | 12489
Actual
Revised
RGP/SS/073/2012 | Implementation of Environmental Management System | Plan | Prior | SS | Contract finalized | 2013-01-21 | 2013-07-21 | Qualitas d.o.o. | 47962
Actual
Revised
RGP/QCBS/032/2007 | PRAGUE PIER: master plan, design | Plan | Prior | QCBS | Contract finalized | 2007-01-31 | 2011-03-30 | JV RMG Consult BV & NIPON KOEI CO. Ltd. | 382924
Actual
Revised
RGP/CQS/054/2010 | Enviromental report for Delta Area under RGP | Plan | Post | CQS | Contract finalized | 2010-04-22 | 2011-02-04 | IND EKO d.o.o. | 32780
Actual
Revised
RGP/CQS/ 059/2010 | Preparation for the Conversion of the Delta and Porto Baros Areas and Selection of a Developer | Plan | Prior | CQS | 2011-02-08 | 2011-02-10 | 2013-02-10 | RMG
|  | Actual |  |  | 2011-02-08 | 2011-02-10 |  |  | 146000
|  | Revised |  |  |  |  | 2014-06-27
RGP/QCBS/045/2008 | PPP models, BD for concess.of new CT on Zagreb pier | Plan | Prior | QCBS | 2009-06-30 | 2009-08-28 | 2012-09-30 | RMG Conslult BV |  | Termination of Contract proposed by PRA
|  | Actual |  |  | 2009-06-30 | 2009-08-28 |  |  | 473000
|  | Revised |  |  |  |  | 2014-07-21 |  | 599750
RGP/QCBS/034/2007 | Consulting Services for drawing up Main Design documentation with obtaining Construction Permit and Compilation of Tender documents for Brajdica Container terminal 2nd construction stage | Plan | Prior | QCBS | Contract finalized | 2007-07-17 | 2011-09-06 | Rijekaprojekt d.o.o. | 657852
Actual
Revised
RGP/QCBS/019/2005 | Vessel Traffic Management Information Service | Plan | Prior | QCBS | Contract finalized | 2005-08-16 | 2006-11-10 | THETIS S.p.A. | 270925
Actual
Revised
RGP/SS/021/2004 | Silo Design | Plan | Prior | SS | Contract finalized | 2004-11-22 | 2005-05-23 | Adria termo d.o.o. | 33448
Actual
Revised
RGP/CQS/007/2002 | Training for luka Rijeka d.d. | Plan | Prior | SS | Contract finalized | 2003-07-10 | 2004-02-11 | Goroslav Keller | 4911
Actual
Revised
RGP/SS/ 015/2004 | Technical Assistance- procurement expert | Plan | Prior | SS | Contract finalized | 2004-06-13 | 2005-01-19 | Asja Miličić | 4704
Actual
Revised
RGP/SS/ 016/2004 | Technical Assistance- FMS | Plan | Prior | SS | Contract finalized | 2004-06-13 | 2005-06-24 | Rita Ivančić | 7539
Actual
Revised
RGP/SS/ 023/2005 | Technical Assistance- procurement expert | Plan | Prior | SS | Contract finalized | 2005-02-01 | 2006-03-20 | Igor Guja | 21808
Actual
Revised
RGP/SS/ 030/2006 | Technical Assistance- procurement expert | Plan | Prior | SS | Contract finalized | 2006-03-01 | 2007-05-10 | Igor Guja | 11036
Actual
Revised
RGP/CQS/037/2007 | Project documentation for electronic data interchange | Plan | Prior | SS | Contract finalized | 2007-07-07 | 2010-07-28 | Prosoft d.o.o. | 55986
Actual
Revised
RGP/SS/ 026/2005 | Preparation of Traffic Circulation and parking Study on and Adjacent to Port Authority Property | Plan | Prior | CQS | Contract finalized | 2005-05-30 | 2006-07-13 | Promet milenijum d.o.o. | 31904
Actual
Revised
RGP/SS/ 038/2007 | Preparation of temporary traffic – construction solution for connecting roads of the maritime passenger terminal | Plan | Prior | SS | Contract finalized | 2007-08-29 | 2008-08-28 | Promet milenijum d.o.o. | 24813
Actual
Revised
RGP/SS/ 029/2006 | Preparation of Preliminary Design for Reconstruction of Switch Railway Station Rijeka linked to Prague Pier Infrastructure Corridor | Plan | Prior | SS | Contract finalized | 2006-03-31 | 2006-11-10 | Željezničko projektno društvo d.d | 27403
Actual
Revised
RGP/SS/ 040/2007 | Project management and technical assistance | Plan | Prior | SS | Contract finalized | 2007-09-26 | 2009-09-07 | Investinžinjering d.o.o. | 69404
Actual
Revised
RGP/SS/ 043/2008 | Geophisical investigation Zagreb Pier 2nd phase | Plan | Prior | SS | Contract finalized | 2008-04-28 | 2008-08-28 | Hydrograpic institute of Republic of Croatia | 23602
Actual
Revised
RGP/LCS/ 046/2008 | Wawe Condition Monitoring within Port of Rijeka - Zagreb Pier | Plan | Prior | LCS | Contract finalized | 2009-04-30 | 2011-09-09 | Hydrograpic institute of Republic of Croatia | 125534
Actual
Revised
RGP/QCBS/024/2005 | Technical assistance in a process of selection a Developer for Port/Urban Area Redevelopment | Plan | Prior | QCBS | Contract finalized | 2006-01-31 | 2009-03-03 | COWI AS | 403625
Actual
Revised
RGP/CQS 006/2004 | Mis Design | Plan | Post | CQS | Contract finalized | 2004-03-09 | 2005-06-09 | Infoexpert d.o.o. | 76441
Actual
Revised
RGP/LCS/ 008/2004 | Audit Services (2003,2004,2005.) | Plan | Prior | LCS | Contract finalized | 2004-02-06 | 2006-06-02 | Iris Nova d.o.o. | 71769
Actual
Revised
RGP/LCS/031/2006 | Audit Services (2006,2007,2008.) | Plan | Post | LCS | Contract finalized | 2006-06-07 | 2009-07-09 | Iris Nova d.o.o. | 71846
Actual
Revised
RGP/SS 036/2008 | Tracer Survey of Beneficiaries ot the Luka Rijeka Social Program | Plan | Prior | SS | Contract finalized | 2008-03-10 | 2008-12-16 | Agencija za poslovna istraživanja i razvojne strategije d.o.o., | 17775
Actual
Revised
RGP/CQS 051/2009 | Legal assistance in implementation of the Rijeka Gateway Project | Plan | Prior | CQS | 2009-06-19 | 2009-07-03 | 2012-06-03 | Odvjetničko društvo Vukić, Jelušić, Šulina, Stanković, Jurcan& Jabuka
|  | Actual |  |  | 2009-06-19 | 2009-07-04 |  |  | 54600
|  | Revised |  |  |  |  | 2015-07-04 |  | 84600
RGP/QCBS/047/2009 | Supervision of Four (4) Work Components of Brajdica Container Terminal Extension | Plan | Prior | QCBS | 2009-12-09 | 2010-02-11 | 2013-03-31 | Investinžinjering d.o.o. |  | Supervision extended during DNP
|  | Actual |  |  | 2009-12-09 | 2010-02-11 |  |  | 1307734
|  | Revised |  |  |  |  | 2014-10-31
RGP/SS/ 058/2010 | Designer’s Supervision on Brajdica Terminal | Plan | Prior | SS | 2010-05-21 | 2010-07-21 | 2013-06-21 | Rijekaprojekt d.o.o.
|  | Actual |  |  | 2010-05-21 | 2010-07-21 | 2013-06-21 |  | 74000
|  | Revised |  |  |  |  | 2013-06-21
RGP/SS/ 052/2010 | Audit services 2009-2012 | Plan | Prior | SS | 2009-10-02 | 2010-10-16 | 2012-05-21 | Iris Nova d.o.o. | 79138
|  | Actual |  |  | 2009-10-02 | 2010-10-16
|  | Revised |  |  |  |  | 2012-06-30
RGP/QCBS/063/2010 | Supervision of Works during Construction of the Zagreb Pier Container Terminal | Plan | Prior | QCBS | 2011-08-31 | 2012-02-20 | 2016-12-31 | JV Investinženjering d.o.o. Croatia (leading partner) and Royal Haskoning Nederland B.V. Maritime The Netherlands
|  | Actual |  |  | 2011-08-31 | 2012-02-20 |  |  | 2598950
|  | Revised |  |  |  |  | 2017-06-30
RGP/SS/073/2014 | Implementation of Environmental Management System | Plan | Prior | SS | 2012-12-12 | 2013-01-21 | 2013-07-21 | Qualitas d.o.o.
|  | Actual |  |  | 2012-12-12 | 2013-01-21 | 2013-09-30 |  | 47962
Revised
RGP/LCS/076/2012 | Audit services (2012,2013,2014) | Plan | Prior | LCS | 2012-10-15 | 2012-11-02 | 2015-05-21 | Iris Nova d.o.o.
|  | Actual |  |  | 2012-10-15 | 2013-01-11 |  |  | 53289
|  | Revised |  |  |  |  | 2015-05-21
RGP/QCBS/091/2013 | Preparation of Main Design Documentation for reconstruction of Railway Station Rijeka - Brajdica and construction of Container Terminal Brajdica Intermodal Yard | Plan | Prior | QCBS | 2014-01-27 | 2014-04-14 | 2015-02-01 | JV Željezničko projektno društvo d.d., Croatia (leading partner), Rijekaprojekt d.o.o., Croatia and IDOM Ingenieria y Consultoria S.A., Spain | 629442.19
|  | Actual |  |  | 2014-01-27 | 2014-04-23
|  | Revised |  |  |  |  | 2015-02-10
RGP/SSS/097/2014 | Supervision Services for the Buoy for prow mooring on Brajdica Container Terminal | Plan | Prior | SS | 2014-03-28 | 2014-04-14 | 2014-06-08 | Investinžinjering d.o.o. | 16000 | No objection received on 04. February 2014
|  | Actual |  |  | 2014-03-28 | 2014-04-14
|  | Revised |  |  |  |  | 2014-09-22
RGP/CQS/ 086/2013 | Environmental Impact Assessment for Reconstruction of railway stations Rijeka and Rijeka Brajdica related to construction of new (Zagreb Pier) and extension of existing (Brajdica) container terminal | Plan | Post | CQS | 2014-05-09 | 2014-05-16 | 2014-07-16 | Dvokut Ecro d.o.o. | 55855
Actual
|  | Revised |  |  | 2014-05-16 | 2014-05-30 | 2014-07-30
RGP/CQS/089/2013 | Economic and justifiability study: Efficient port system for reception of ship-generated waste and cargo residues on the area of the Port of Rijeka Authority | Plan | Post | CQS | 2014-05-02 | 2014-05-12 | 2014-09-15 | JV Oikon d.o.o .& Ind Eko d.o.o & Illyricum Consulting d.o.o | 89366
Actual
|  | Revised |  |  | 2014-05-15 | 2014-05-30 | 2014-09-28
RGP/QCBS/090/2013 | Preparation of Design Documentation for Reconstruction of Railway Station Rijeka and Construction of Intermodal Yard at Zagreb Pier Container Terminal | Plan | Prior | QCBS | 2014-04-23 | 2014-06-10 | 2016-08-10
Actual
|  | Revised |  |  | 2014-04-23 | 2014-07-25 | 2016-09-25
RGP/QCBS/072/2013 | Port of Rijeka master plan | Plan | Prior | QCBS | 2015-02-10 | 2015-04-15 | 2015-11-05 |  |  | Draft final version of TOR will be prepared by the end of October
Actual
Revised
RGP/CQS/068/2011 | Project doc's for ID cards and video CCTV | Plan | Post | CQS | 2012-04-05 | 2012-05-02 | 2012-07-30 | Aztek d.o.o
|  | Actual |  |  | 2012-04-06 | 2012-05-02
|  | Revised |  |  |  |  | 2012-09-30
RGP/CQS/064/2010 | Traffic Study with Preliminary Design for Reconstruction of Rijeka and Brajdica Marshaling Yards Related to Zagreb Pier and Brajdica Container Terminals Construction | Plan | Prior | CQS | Contract finalized | 2011-03-28 | 2012-01-27 | Željezničko projektno društvo d.d
Actual
Revised
RGP/CQS/081/2012 | Supervision of works on Rijeka Breakwater Armor Rock Recovery | Plan | Prior | CQS | 2012-06-15 | 2012-07-15 | 2012-09-30 | Marecon d.o.o.
|  | Actual |  |  | 2012-06-11 | 2012-07-02
Revised
RGP/CQS/083/2013 | Development of maritime study for Krk terminal and Raša Basin | Plan | Post | CQS | 2015-12-01 | 2016-01-20 | 2016-03-20 |  |  | The TOR following finalisation of master plan
Actual
Revised
RGP/CQS 086/2013 | Port Environmental Protection Plan (EIA) for Brajdica Marshalling Yard | Plan | Prior | SS | 2013-12-20 | 2014-01-15 | 2014-02-28 | rajko ce , dostaviti sto prije podatke za oglas do 28.010 , mora napraviti zadnji rok
Actual
Revised
RGP/LCS/093/2014 | Audit services (2015,2016,2017) | Plan | Prior | LCS | 2015-02-28 | 2015-04-15 | 2017-06-15
Actual
Revised
RGP/CQS/096/2014 | Zagreb Pier Concession Transaction Advisor | Plan | Prior | CQS | 2014-02-01 | 2014-03-15 | 2014-12-15 | to cemo vidjeti sa Wb, ostaviti kao rezerva
Actual
Revised
| Legal assistance in implementation of the Zagreb Pier Concession and the Delta &Porto Baros Concession | Plan | Prior | CQS | 2014-10-01 | 2014-11-02 | 2017-06-15
RGP/SS/094/2013 |  | Actual |  |  | 2015-06-01 | 2015-07-01 | 2015-07-05
Revised
RGP/QCBS/098/2015 | Supervision of works on Brajdica Container Terminal Extension Section C | Plan | Prior | QCBS | 2015-04-15 | 2015-06-01 | 2017-06-30
Actual
Revised
RGP/CQS/098/2015 | Technical assistance in preparation bidding documents for works and supervision on Container Terminal Brajdica Section C | Plan | Prior | CQS | 2014-11-10 | 2014-12-10 | 2015-06-01
Actual
Revised
Legend: | Contracts Completed
Contracts Awarded
Contracts Under Process
Contracts to be Procured

## Goods PRA
Procurement Plan for Goods Contracts - July 16, 2014
Ref. No | Contract Description |  | Proc. method | Dom. Pref. (yes/no) | Review by Bank (Prior/ Post) | Expected Proposal Opening Date | Contract Signing | Contract Completion | Supplier's Name | Signed contract amount in Euro | Explanatory Notes
RGP/G036/ICB/2007 | Supply, Inst.and Commissioning of VTMIS | Plan | ICB | no | prior | Contract finalized | 2007-03-23 | 2011-12-23 | Ericsson Nikola Tesla, d.d | 1539929
Actual
Revised
RGP/G010/ICB/2004 | Mobile Harbour Crane | Plan | ICB | no | prior | Contract finalized | 2004-07-27 | 2005-07-29 | Fantuzzi Regianne | 3044673
Actual
Revised
RGP/G041/ICB/2008 | Supply, Installation and Commissioning of Video Surveillance System of Port of Rijeka Authority | Plan | ICB | no | prior | Contract finalized | 2008-08-06 | 2009-03-30 | Tehnomobil d.o.o. | 307925
Actual
Revised
RGP/G05/ICB/2006 | Supply, Installation and Commissioning of Access Control System in the Area and the Jurisdiction of the Port of Rijeka Authority | Plan | ICB | no | prior | Contract finalized | 2007-01-03 | 2007-10-30 | Tehnomobil d.o.o. | 461944
Actual
Revised
RGP/G04/ICB/2007 | Supply, Installation and Commissioning of Port of Rijeka Authority Management Information System (MIS) | Plan | ICB | no | prior | Contract finalized | 2006-02-28 | 2007-12-11 | Joint venture ECS d.o.o. & Point d.o.o. & Span d.o.o | 492092
Actual
Revised
RGP/G080/NCB/2012 | ID cards & Video CCTV Brajdica New Entrance | Plan | NCB | no | prior | Contract finalized | 2013-10-01 | 2014-03-17 | JV Securus d.o.o. and Maxmar Sport d.o.o. | 396960
Actual
Revised
RGP/044/ICB/2008 | Supply, Installation and Commissioning ofSupply and Installation of the Electronic Data Interchange (EDI) | Plan | ICB | no | prior |  | 2010-06-15 | 2012-02-15 | Joint Venture Phaeros Group BVBA and Combis d.o.o. |  | Contract terminate
Actual
Revised
RGP/G079/NCB/2013 | ID cards & Video CCTV - Rijeka Basin | Plan | NCB | no | prior | 2015-10-15 | 2015-12-15 | 2016-04-02
Actual
Revised
RGP/G078/ICB/2013 | Waste collection Ship (instalation & project BD incl ) | Plan | ICB | no | prior | 2015-02-15 | 2015-03-15 | 2016-04-01
Actual
Revised
Legend: | Contracts Completed
Legend: | Contracts Completed
Contracts Awarded
Contracts Under Process
Contracts to be Procured

## Works PRA
Procurement Plan for Works Contract -July 16, 2014
Ref. No | Contract Description |  | Proc. method | Dom. Pref. (yes/no) | PreQ* | Review by Bank (Prior/ Post) | Expected Proposal Opening Date | Contract Signing | Works Completion | Physical Status | Contractor's Name | Signed contract amount in Euro | Explanatory Notes
RGP/05/06/NCB 2005 | Construction of terminal facilities | contract completed | NCB | no | no | Prior | 2005-09-21 | 2005-11-24 | 2008-12-23 | 100% | Konstruktor Inžinjering Split | 4165525
RGP/07/07/NCB 2007 | Reconstruction of the Passenger Terminal at the Rijeka Breakwater– Ferry Berth L=260m | contract completed | NCB | no | no | Post | 2007-11-16 | 2008-11-30 | 2010-02-04 | 100% | Pomgrad Inžinjering Split | 5201561
RGP/027/05 NCB 2005 | Construction of the new bridge for the vehiles at the Rijeka Brake water | contract completed | NCB | no | no | Prior | 2005-05-20 | 2005-07-06 | 2006-06-28 | 100% | Gp Krk d.d. | 754156
RGP/05/05 NCB 2006 | Demolition of warehouse structures at the area of Baross port | contract completed | NCB | no | no | Post | 2005-09-14 | 2005-11-24 | 2007-02-06 | 100% | Gp Mikić d.d. | 533312
RGP/03/01 NCB 2004 | Reconstruction of Vienna Berth | contract completed | NCB | no | no | Prior | 2004-04-27 | 2004-07-27 | 2005-11-21 | 100% | Gp Krk d.d. | 1145845
RGP 049/08/NCB/2008 | Geotechnical Soil Investigation for Zagreb Pier Stage 2 | contract completed | ICB | no | no | Prior | 2009-05-05 | 2009-07-23 | 2010-06-30 | 100% | Igeotest Marina | 1999900
RGP 060//NCB/2010 | Brajdica Container Terminal Extension Section B (Brajdica Container Terminal Gate) | Plan | NCB | no | no | Prior | 2010-10-29 | 2011-11-21 | 2012-05-15 | 100% | Viadukt d.d.
|  | Actual |  |  |  |  | 2010-10-29 | 2011-11-21 |  |  |  | 2264794.99
|  | Revised | [6 empty] | 2014-06-18
RGP 048/08/ICB/2008 | Brajdica Container Terminal Extension Section A (Pier Extension) | Plan | ICB | no | no | Prior | 2009-09-29 | 2009-12-21 | 2013-03-03 | 99% | JV Primorje, Viadukt and Gp Krk
|  | Actual |  |  |  |  | 2009-09-29 | 2009-12-21 |  |  |  | 25320876.62
|  | Revised | [6 empty] | 2014-05-20 |  |  | 26757376.62
RGP065/NCB/2011 | Connecting roads of the maritime passenger terminal | contract completed | NCB | no | no | Prior | 2011-04-08 | 2011-09-02 | 2012-03-30 | 100% | Gp Krk d.d. | 435679
RGP 050/ICB/2008 | Construction of new CT on Zagreb pier D&B | Plan | ICB | no | yes | Prior | 2010-11-12 | 2012-04-11 | 2016-10-31 | 0% | JV GRANDI LAVORI FINCOSIT - NUOVA CO.ED.MAR - MALTAURO – OSIJEK-KOTEKS
|  | Actual |  |  |  |  | 2010-11-12 | 2012-04-11 |  |  |  | 70585015.45
|  | Revised | [6 empty] | 2017-06-30
RGP 069/NCB/2012 | Rijeka Breakwater Armor Rock Recovery | Plan | NCB | no | no | Prior | 2012-06-15 | 2012-07-15 | 2012-09-30 | 0% | Sun adria d.o.o. | 447064
|  | Actual |  |  |  |  | 2012-06-11
|  | Revised | [5 empty] | 2012-06-29
RGP 070/NCB/2014 | Upgrading of Brajdica Container Terminal new berth - Buoy | Plan | NCB | no | no | Prior | 2014-02-07 | 2014-04-08 | 2014-06-08 | 80% | BSK Commerce d.o.o.
|  | Actual |  |  |  |  | 2014-02-07 | 2014-04-22 |  |  |  | 657400
|  | Revised | [6 empty] | 2014-09-22
RGP 084/NCB/2013 | Brajdica Container Terminal Extension Section D (Pier Extension) | Plan | NCB | no | no | Prior | 2013-02-01 | 2013-03-15 | 2013-12-15 | 0%
Actual
Revised
RGP 071/NCB/2014 | Upgrading of Brajdica Container Terminal new berth - Seabed Deepening | Plan | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0%
Actual
Revised
RGP 086/ICB/2015 | Brajdica Container Terminal Extension Section C - Construction of the exit gauge, expansion of the railway tunnel, execution of the contact grid and of the existing gauge deviation in the tunnel | Plan | ICB | no | no | Prior | 2015-07-01 | 2015-08-01 | 2017-04-01 | 0%
Actual
Revised
RGP099/ICB/2015 | Brajdica Container Terminal Extension Section C -Railway part of the terminal | Plan | ICB | no | no | Prior | 2015-03-15 | 2015-04-15 | 2016-01-15 | 0%
Actual
Revised
Legend: | Contracts Completed
Notice*: | Brajdica Container Terminal Extension Section C (Pier Extension) is a matter of discussion for the further project implementation and if required it will be added to the next version of the procurement plan according to the adequate procedure.
Legend: | Contracts Completed
Contracts Awarded
Contracts Under Process
Contracts to be Procured