|  |
| --- |
| **76042 v2**  **Restructuring** **Status:** **Archived** |
| **Restructuring Type:** **Level two** |
| Last modified on date : 03/26/2013 |

|  |  |
| --- | --- |
| **1. Basic Information** | |
| Project ID & Name | P082026: PY Road Maintenance |
| Country | Paraguay |
| Task Team Leader | Maria Margarita Nunez |
| Sector Manager/Director | Aurelio Menendez |
| Country Director | Penelope J. Brook |
| Original Board Approval Date | 08/24/2006 |
| Original Closing Date: | 06/30/2012 |
| Current Closing Date | 02/28/2014 |
| Proposed Closing Date [if applicable] |  |
| EA Category | B-Partial Assessment |
| Revised EA Category | B-Partial Assessment-Partial Assessment |
| EA Completion Date | 06/13/2006 |
| Revised EA Completion Date |  |

|  |  |  |
| --- | --- | --- |
| **2. Revised Financing Plan (US$m)** | | |
| **Source** | **Original** | **Revised** |
| BORR | 31.41 | 31.41 |
| IBRD | 74.00 | 74.00 |
| **Total** | 105.41 | 105.41 |

|  |  |  |
| --- | --- | --- |
| **3. Borrower** | | |
| **Organization** | **Department** | **Location** |
| Ministerio de Hacienda |  | Paraguay |

|  |  |  |
| --- | --- | --- |
| **4. Implementing Agency** | | |
| **Organization** | **Department** | **Location** |

|  |  |  |
| --- | --- | --- |
| **5. Disbursement Estimates (US$m)** | | |
| **Actual amount disbursed as of 03/28/2013** **33.52** | | |
| **Fiscal Year** | **Annual** | **Cumulative** |
| 2013 | 0.00 | 33.52 |
|  | **Total** | **33.52** |

|  |  |
| --- | --- |
| **6. Policy Exceptions and Safeguard Policies** | |
| **Does the restructured project require any exceptions to Bank policies?** | N |
|  |  |
|  |  |
| **Does the restructured projects trigger any new safeguard policies? If yes, please select from the checklist below and update ISDS accordingly before submitting the package.** | N |

|  |
| --- |
| **7a. Project Development Objectives/Outcomes**  **Original/Current Project Development Objectives/Outcomes** |
| The project's development objective is to establish a sustainable road management strategy that ensures the upgrading and maintenance of the road network through a rational and balanced use of scarce resources. |

|  |
| --- |
| **7b. Revised Project Development Objectives/Outcomes** [if applicable] |
|  |