## 20130123
PROCUREMENT PLAN
[6 empty] | 1US$ = | 6.8 RMB
CP N° |  | CONTENT | TOTAL COSTS |  | WB loan |  | Procure. Method | Review by Bank | Proposed Schedule |  |  | Contract Signing Date | Contractor's Name | Contract Price | Comments
|  |  | *106 RMB | *106 US$ | *106 US$ | % |  |  | Bid Period* | Civil works | Supply & Installation
Water Supply
01ws - ZHUJI (ZJ)
WSZJ1C | CW of WTP and intake pipe | WSZJ1C - a 40,000 m3/d Qingshan water treatment plant. | 24.29 | 3.58 | 2.41 | 68% | NCB | PRIOR | 2010/09-2010/12 | 2011/01-2012/03 |  | 20101220 | Zhejiang Hongda Construton Engineering Co.,Ltd. | 21119694.2
WSZJ2C-1 | Water distribution pipeline of Caota and main pipe of Datang Town | 20km x DN300 ~ DN800 | 52.16 | 7.6706 | 4.61 | 68% | NCB | PRIOR | 2011/10-2012/03 | 2012/04-2013/05 |  | 20120410 | Huadi Construton Co.,Ltd. | 43238635
WSZJ2C-2 | Water distribution pipeline of Wangjiajing/Paitou/Anhua and inside pipe of Datang | 23.8km x DN300 | 20.93 | 3.0779 | 1.85 | 68% | NCB | POST | 2011/10-2011/12 | 2012/02-2013/04 |  | 20120215 | Shaoxing Shuilian Constrution Engineering Co., Ltd. | 20283003
WSZJ1S | SIC of WTP | WSZJ1S - SIC of goods for 40,000 m3/d Qingshan water treatment plant. | 13.78 | 2.03 | 1.38 | 68% | NCB | PRIOR | 2011/04-2011/05 |  | 2011/06-2012/03 | 20110720 | Zhejiang Zhu'an Construton (Group) Co.,Ltd. | 11980000
Subotal |  | Total Contract Packages | 111.16 | 16.3585 | 10.25 | 68% | [7 empty] | 96621332.2
02ws - JINHUA - WUCHENG (WC)
WSWC1C | CW of WTP and intake pipe | WSWC1C - Civil works for Construction of (i) a 0.17 km x DN800 steel gravity main from Xinfan reservoir, and (ii) a 50,000 m3/d Tangxi water treatment plant. | 23.263 | 3.421 | 3.2089 | 94% | NCB | PRIOR | 2010/08-2010/09 | 2010/11-2011/12 |  | 20101027 | Zhejiang Shengyuan (Group) Co.,Ltd. | 24508108
WSWC2C | CW main distribution pipe | WSWC2C - Civil works for a 12.73 km x DN800 ~ DN900 clear water main | 26.0949 | 3.8375 | 3.5996 | 94% | NCB | PRIOR | 2010/10-2011/01 | 2011/03-2012/01 |  | 20110131 | Zhejiang Honglin Construton Co.,Ltd. | 19683279
WSWC1S | SIC of goods for water treatment plant | WSWC1S - SIC of goods for 50000m3/d water treatment plant | 13.726 | 2.0185 | 1.8934 | 94% | NCB | PRIOR | 2010/12-2011/02 |  | 2011/05-2011/12 | 20110511 | Zhejiang Installation Engineering Co.,Ltd. Of Zhongtian Constrution Group | 13236464.83
WSWC3C - NBF | constucted clear water main from Jinxi WSP to Dongmenshan | WSWC3C - NBF - 3.2 km x DN800 clear water main pipe, and a 1,500 m3 Dongmenshan high level clear water tank. | 11.5411 | 1.6972 |  |  | NBF | NA |  |  |  | 20100507 | Yiwu City Hydropower Construction Engineering Co., Ltd./Jinhua City Wucheng District Hydropower Construction and Installation Company | 12225518
WSWC4C - NBF | constructed secondary network in Jiangtang | WSWC4C - NBF - civil work for 24.38km DN110-DN315 pipes in Jiangtang town. | 10.5361 | 1.5494 |  |  | NBF | NA |  |  |  | 20080514 | Jinhua City Wucheng District Hydropower Construction and Installation Company | 6162295
WSWC5C - NBF | constructed secondary network in Tangxi | WSWC5C - NBF - civil work for 15.21km DN110-DN600 pipes in Tangxi town. | 9.0869 | 1.3363 |  |  | NBF | NA |  |  |  | 20090605 | Yongkang City Hydropower Construction and Installation Company | 7230000
Subotal |  | Total Contract Packages - NBF excluded | 63.084 | 9.2771 | 8.7019 | 94% | [7 empty] | 57427851.83
Total |  | Total Water Supply - NBF excluded | 174.244 | 25.6356 | 18.9519 | 73.93%
Wastewater
03ww - JIANDE (JD)
WWJD1C | CW of WWTP | WWJD1C - Civil works for 19,000 m3/d expansion of Chendong WWTP and 30,000 m3/d upgrading from 1B to 1A | 30.3901 | 4.4691 | 3.1016 | 70% | NCB | POST | 2013/05-2013/07 | 2013/07-2014/12
WWJD2C | CW of network in Genglou Community | WWJD2C - 13km sewerage(DN300~800) for genglou and xin'anjiang urban area . | 18.2938 | 2.6903 | 1.867 | 70% | NCB | POST | 2014/01-2014/03 | 2014/03-2014/12
WWJD3C | CW of network in Yangxi Community | WWJD3C - 4500m3/d Pumping Station (including civil work and equipment and installation),and pressure pipe of outlet. | 8.6 | 1.26 | 0.86 | 70% | NCB | PRIOR | 2011/08-2011/12 | 2012/01-2014/12 |  | 20111231 | Zhongtai Construction Group Co., Ltd. | 8403610
WWJD1S | SIC of goods in WWTP | WWJD1S -SIC of goods for 19,000 m3/d expansion of Chendong WWTP and 30,000 m3/d upgrading from 1B to 1A | 18.6095 | 2.7367 | 1.8993 | 70% | NCB | POST | 2013/05-2013/07 |  | 2013/08-2014/12
Subotal |  | Total Contract Packages | 75.8934 | 11.1561 | 7.7279 | 70% | [7 empty] | 8403610
04ww - QUZHOU - QUJIANG (QJ)
WWQJ1C | CW of WWTP |  | 30.8543 | 4.5374 | 3.3305 | 73% | NCB | PRIOR | 2011/05-2011/09 | 2011/10-2012/12 |  | 20110926 | Zhejiang Jieyu Group Co., Ltd. | 33744444
WWQJ2C | CW of network in new district expansion area | WWQJ2C - 4.1km ww pipes,1.4km storm pipes and 1.4km water supply pipes for Tongjiang / Xinan roads | 10 | 1.4706 | 1.0735 | 73% | NCB | POST | 2013/04-2013/05 | 2013/06-2013/12
WWQJ3C | CW of network in northwest area | WWQJ3C - 2.2km ww pipes and 6.3km storm pipes in Qiuzhi / Kangning / Fanggui roads | 8.32 | 1.2235 | 0.89318 | 73% | NCB | POST | 2013/09-2013/10 | 2013/11-2015/06
WWQJ4C | part 1 of Xiafei road west | WWQJ4C - 14.2km ww pipes, 8.1km storm pipes,14.4km water supply pipes and 5.6km electrical power pipes in Tongpu / Xingfeng/ Chayuan/ Roads, Zhenxinyi/ Zhenxing'er/ Zhenxingsan Roads( to the east of Bingang Road) and Dongji'er/ Dongjisan roads. | 17.45 | 2.5129 | 1.8445 | 73% | NCB | PRIOR | 2011/05-2011/08 | 2011/09-2012/12 |  | 20110818 | Zhejiang Guangsha Municipal Engineering Co., Ltd. | 17205746
WWQJ5C | part 2 of Xiafei road west | WWQJ5C - 17.8km ww pipes, 8.5km stormwater pipes,20.3km water supply pipes and 7.8km electrical power pipes ,including Meilin / Dangui / Tongjiang / Daqiao / Xianyan / Shangjin roads, Zhenxingyi / Zhenxing'er/ Zhenxingsan Roads(to the West of Bingang Roa | 27.59 | 4.0574 | 2.9619 | 73% | NCB | PRIOR | 2012/08-2012/09 | 2012/10-2014/10 |  | 20120929 | Quzhou Municipal Engineering Co., Ltd. | 25282484
WWQJ1S | SIC of goods in WWTP | WWQJ1S - SIC of goods for 20000m3/d Chengdong WWTP. | 36.8102 | 5.4133 | 3.9733 | 73% | NCB | PRIOR | 2012/09-2012/11 |  | 2012/12-2013/08 | 20121231 | Zhejiang Zhuan Construction Group Co., Ltd.. | 24984665
WWQJ6C - NBF | an underconstruction package in west xiafei road | WWQJ6C - NBF - 4.2km sewers & 3.0km stormwater pipes,including zhengxingxi/tongjiang road. | 7.7434 | 1.1387 |  |  | NBF | NA |  | 2010/03-2010/12 |  | 20100401 | Shaoxing Construction Group Co., Ltd. (tenderⅠ) /Quzhou 5th Construction Engineering Co., Ltd. (tenderⅡ) | 7740000
Subotal |  | Total Contract Packages - NBF excluded | 131.0245 | 19.2151 | 14.0769 | 73% | [7 empty] | 101217339
05WW - LANXI - YOUBU (YB)
WWYB1C | CW of WWTP and discharge pipe | WWYB1C - civil work for 5,000 m3/d WWTP | 8.4708 | 1.2457 | 0.79103 | 64% | NCB | PRIOR | 2010/07-2010/08 | 2010/09-2011/06 |  | 20100826 | Zhejiang Tianxia Construton Co.,Ltd. | 6650000
WWYB2C | CW of WW pipe in south and north part area and collector | WWYB2C - 3km WW pipes in south part of new area and 3.3km DN600 main WW pipe to WWTP & 5.8km ww in north part of new area | 8.89 | 1.3066 | 0.82969 | 64% | NCB | POST | 2013/03-2013/04 | 2013/05-2014/05
WWYB3C | CW of ancient road and CW of river rinovation | WWYB3C -1.7km ancient road renovation with associated ww/storm water pipes & 0.74km guxi river renovation | 19.4079 | 2.8541 | 1.8124 | 64% | NCB | POST | 2013/05-2013/06 | 2013/06-2013/12 | [5 empty] | 根据兰溪项目办要求，将WWYB3C和WWYB6C两个合同合并采购，合同内容不变
WWYB4C | CW of new road | WWYB4C -1.5km new road(tianfu/yongxin/yongfu)with associated sewerage & stormwater pipe | 18.8448 | 2.7713 | 1.7598 | 64% | NCB | POST | 2012/10-2012/11 | 2012/12-2013/05 |  | 20121210 | Zhejiang Zhongyi Construton Co.,Ltd. | 11963115
WWYB1S | SIC of WWTP goods | WWYB1S - SIC of goods for 5000m3/d WWTP | 9.3514 | 1.3752 | 0.87325 | 64% | NCB | PRIOR | 2010/10-2011/02 |  | 2011/05-2012/05 | 20110510 | JV Zhejiang Bohua Environmental Technology Engineering Co.,Ltd. And The 7th. Construction Engineering of Guizhou Constrution and Engineering Group | 6927742.74
Subotal |  | Total Contract Packages | 64.9649 | 9.5529 | 6.0661 | 64% | [7 empty] | 25540857.74
06ww - PAN'AN Jianshan (JS)
WWJS1C | CW and goods S&I of Jianshan project | WWJS1C - CW and goods supply and installation of 6000m3/d WWTP,3 pumpstations and networks | 43.65 | 6.4189 | 4.7179 | 76% | NCB | PRIOR | 2011/02-2011/07 | 2011/08-2012/12 |  | 20110704 | Hangzhou Equipment Installation Co., Ltd. | 30510190
Subotal |  | Total Contract Packages | 43.65 | 6.4189 | 4.7179 | 76% | [7 empty] | 30510190
07ww - PAN'AN Shenze (SZ)
WWSZ1C | CW of cuixi river enbankment | WWSZ1C - 2.3km Cuixi river embankment with associated 2*2.3km WW pipes on the two sides of Cuixi river. | 54.7939 | 8.0579 | 5.0926 | 63% | NCB | PRIOR | 2011/08-2011/12 | 2012/03-2014/09 |  | 20111206 | First Hydropower Construction Group Co., Ltd. | 52869809
WWSZ2C | CW of convey pipe | WWSZ2C - 2*5km Main sewerage conveyance piplines to Anwen existing WWTP. | 19.6044 | 2.883 | 1.8221 | 63% | NCB | POST | 2013/06-2013/08 | 2013/09-2014/12
WWSZ3C | CW of Panjin Road | WWSZ3C - 4.3km Panjin road expansion and associated WW pipes and storm drainage. | 49.8188 | 7.3263 | 4.6302 | 63% | NCB | PRIOR | 2013/06-2013/08 | 2013/09-2015/12
Subotal |  | Total Contract Packages | 124.2172 | 18.2672 | 11.5449 | 63% | [7 empty] | 52869809
08ww - PAN'AN Yunshan (YS)
WWYS1C - NBF | CW of Pumpstation and pipes along Wenxiriver | WWYS1C - one 5000m3/d pumpstation,2.75km WW convey pipe and about 3.05km pipes in central area. | 17.0253 | 2.5037 |  |  | NBF | NA | 2013/04-2013/05 | 2013/06-2013/12
WWYS2C | CW of pipes along Jinchanxi river | WWYS2C - 5.5km WW pipes along Jinchanxi river. | 15.5255 | 2.2832 | 1.4407 | 63% | NCB | PRIOR | 2013/04-2013/05 | 2013/06-2014/06
WWYS3C | CW of pipes along Zixi river | WWYS3C - 5.8km WW pipes along zixi river. | 14.9728 | 2.2019 | 1.3894 | 63% | NCB | PRIOR | 2013/04-2013/05 | 2013/06-2014/06
Subotal |  | Total Contract Packages | 47.5235 | 6.9888 | 2.8301 | 63% | [7 empty] | 0
09ww - TONGLU - JIANGNAN (JN)
WWJN1C | CW of Zhongxing road and Zhengxing road | WWJN1C - zhongxing road north extension + Zhengxing West Road + Shichang Road and WW and Stormwater Pipelines. | 15.2487 | 2.2425 | 1.4262 | 64% | NCB | PRIOR | 2010/10-2011/01 | 2011/04-2012/12 |  | 20110331 | Chun'an County Municipal Constrution Co., Ltd. | 9929719
WWJN2C | CW of Guihua and Shichang roads | WWJN2C -Guihua (Jinpu) + Shichang Road and WW and Storm water pipelines and landscape municipal facilities | 8.15 | 1.1985 | 0.76706 | 64% | NCB | POST | 2012/11-2012/12 | 2013/01-2013/11 |  |  | Haixing Construton Co.,Ltd. | 7460000
WWJN3C** | CW of Zhaishi road | WWJN3C - 1.80 km Zhaishi Road and WW and Storm water pipelines. | 22.455 | 3.3022 | 2.1002 | 64% | NCB | POST | 2014/05-2014/06 | 2014/07-2015/07 |  |  |  |  | Need to be adjusted.
WWJN4C** | CW of Pumpstations and collectors | WWJN4C - 4.1 km of sewage conveyor and 2 pumping stations. | 14.0814 | 2.0708 | 1.317 | 64% | NCB | POST | 2013/06-2013/07 | 2013/08-2013/06 |  |  |  |  | Need to be adjusted.
WWJN5C** | CW of pipes around west Zhaixi road | WWJN5C - 6.5 km Zhaixi West Road Primary and Secondary WW Sewers and Storm water pipelines. | 10.7738 | 1.5844 | 1.0077 | 64% | NCB | POST | 2014/06-2014/07 | 2014/08-2015/12 |  |  |  |  | Need to be adjusted.
WWJN6C | CW of pipes around east Zhaixi road | WWJN6C - Zhaishi East (Jintang Road, Zhaixi Road East, Zhenxingxi West and 1.05KM Sewers )Road and WW Sewers and Storm water pipelines. | 13.36 | 1.9647 | 1.2574 | 64% | NCB | POST | 2012/11-2012/12 | 2013/01-2014/04 |  |  | Futai Haixing Construton Co.,Ltd. | 15278786
Subotal |  | Total Contract Packages | 84.0688 | 12.3631 | 7.8756 | 64% | [7 empty] | 32668505
10ww - LONGYOU (LY)
WWLY1C | CW of jinqi and Weisi roads | WWLY1C - 0.461 km Jingqi Road+ 1.754 km Weisi Road and associated drinking WS, industrial WS, WW and stormwater pipelines. | 35.1319 | 5.1665 | 3.2497 | 62% | NCB | PRIOR | 2011/03-2011/06 | 2011/07-2012/12 |  | 20110811 | Zhejiang Longyou Peihua Construction Co., Ltd. | 38657056
WWLY2C | CW of Jingsan road | WWLY2C - 1.755 Km Jinsan Road and associated drinking WS, industrial WS, WW and stormwater pipelines. | 24.313 | 3.5754 | 2.249 | 62% | NCB | POST | 2011/10-2012/01 | 2012/03-2013/03 |  | 20120323 | Zhejiang Longyou Tianyuan Construction Co., Ltd. | 17790007
WWLY3C | CW of discharge pipe | WWLY3C - 1.0 km WWTP treated effluent discharge pipeline. | 6.2836 | 0.92406 | 0.58123 | 62% | NCB | PRIOR | 2010/06-2010/07 | 2010/08-2011/05 |  | 20100730 | Zhejiang Qingtian Dingsheng Constrution Engineering Co., Ltd. | 6890722
WWLY4C | CW of Weiyi and weier roads | WWLY4C - 0.921 km Weiyi Road + 0.747 km Weier Road and associated drinking WS, industrial WS, WW and stormwater pipelines. | 24.1037 | 3.5447 | 2.2296 | 62% | NCB | POST | 2012/08-2012/09 | 2012/10-2013/10 |  | 20120924 | Longyou Jixiang Construction Co., Ltd. | 20435907
WWLY5C | CW of Qiaotou to Waiyishan roads | WWLY5C - 1.16 km Qiaotou to Waiyishan Road and associated drinking WS, industrial WS, WW and stormwater pipelines. | 17.9845 | 2.6448 | 1.6636 | 62% | NCB | POST | 2013/05-2013/06 | 2013/07-2014/05
WWLY6C | CW of pipes connecting villages | WWLY6C - 1.42 km village drinking WS , 1.445 km WW and 1.465 Storm Water Pipelines. | 2.3717 | 0.34878 | 0.21938 | 62% | NCB | POST | 2013/09-2013/10 | 2013/11-2014/05
WWLY7C - NBF | CW of Jinwu and Beiyi roads | WWLY7C - NBF - 2.038 km Jinwu Road Extension + Beiyi Road and associated drinking WS, industrial WS, WW and stormwater pipelines. | 16.2645 | 2.3918 |  |  | NBF | NA | 2013/04-2013/05 | 2013/06-2014/04
WWLY8C - NBF | CW of north eastern part roads | WWLY8C - NBF - 4.995km Jinjiu Road +Jinshi Road +Jinshier Road + Weyi Road + Weier Road + Weisi Road and associated drinking WS, industrial WS, WW and stormwater pipelines. | 55.4865 | 8.1598 |  |  | NBF | NA | 2013/10-2013/11 | 2013/12-2015/12
WWLY9C - NBF | CW of south part roads | WWLY9C - NBF - 4.754 km Weisi Road + Weiliu Road + Fengjikun Road + Jinwu Road and associated drinking WS, industrial WS, WW and stormwater pipelines. | 45.1623 | 6.6415 |  |  | NBF | NA | 2014/01-2014/02 | 2014/03-2015/12
Subotal |  | Total Contract Packages - NBF excluded | 110.1886 | 16.2042 | 10.1924 | 62% | [7 empty] | 83773692
Total |  | Total Wastewater - NBF excluded | 681.5309 | 100.1663 | 65.0317 | 64.92%
Solid Waste
11sw - JIANDE (JD)
SWMC01C | CW of Qingshan landfill(includ vertical and horizontal antiseepage system) | SWMC1C - Construction of the first phase (210,000 m3 capacity) of a sanitary landfill (610,000 m3 capacity), inclusive of vertical and horizontal antiseepage system. | 54.38 | 8 | 6.13 | 77% | NCB | PRIOR | 2011/05-2011/06 | 2011/12-2012/12 |  | 20110810 | Tianjin Jinchang Environmental Protection Co., Ltd. | 54307395
SWMC01S | design and construction of leachate treatment system | SWMC2C - design,supply and installlation of leachate treatment system and provision of monitoring instruments | 21.0344 | 3.0933 | 2.3695 | 77% | NCB | POST | 2012/03-2012/04 | 2012/05-2013/01 |  | 20120601 | Shanghai Tongji Construction Technology Co. , Ltd | 15957507
SWMC02C | closure of existing dumpsites | SWMC4C - Closure of the existing 3 dumpsites | 12.017 | 1.7672 | 1.3537 | 77% | NCB | POST | 2013/06-2013/07 | 2013/08-2014/06
SWMC1G | Meicheng SW goods list 1 | SWMC1G - cars,bus and trucks | 2.1464 | 0.31564 | 0.24178 | 77% | ICB | PRIOR | 2013/07-2013/08 |  | 2013/09-2014/08
SWMC2G | Meicheng SW goods list 2 | SWMC2G - SW collection,transportation and landfill machine | 6.9757 | 1.0258 | 0.78579 | 77% | ICB | PRIOR | 2013/07-2013/08 |  | 2013/09-2014/09
Subotal |  | Total Contract Packages | 96.5535 | 14.202 | 10.8807 | 77% | [7 empty] | 70264902
Total |  | Total Solid Waste | 96.5574 | 14.1996 | 10.8758 | 77% | [7 empty] | 559298088.77
4185085.19
563483173.96