Procurement Plan dated May 28, 2013

# I. General

- Data of General Project information:

- Borrower: REPUBLIC OF POLAND

- Project Name: ODRA RIVER BASIN FLOOD PROTECTION

- Loan No.: 7436-POL, Project ID: P086768

- Coordination Agency: Project Coordination Unit Wroclaw

- Project Implementing Unit: RZGW Wroclaw, RZGW Gliwice, DZMIUW Wroclaw, IMGW, PCU and DGLP.

- Bank's approval Date of the Procurement Plan

December 16, 2006 - initial approval over Loan Agreement  Section 1.02 (n)

December 2007 – updated Procurement Plan for 2008

December 2008 – updated Procurement Plan (current version for 2009)

July 15, 2010 – updated Procurement Plan (current version for 2010-2011)

May 31, 2011 – updated Procurement Plan (current version for 2011-2012)

December  11, 2012 – updated Procurement Plan (current version for 2012-2013)

January 2, 2013 - – updated Procurement Plan (current version for 2013-2014)

Procurement Notice: 6 October 2008r., No. WB583-697/07
Period covered by this procurement plan: 2013 -2015

# II. Goods and Works and non-consulting  services.

1.	Procurement Method Threshold

|  | Procurement Method | Method Threshold | Comments |
| --- | --- | --- | --- |
| 1. | ICB and LIB (Goods) | Goods > €500,000 | per LA |
| 2. | NCB (Goods) | Goods <€500,000 | per LA |
| 3. | ICB (Works) | Works> €5,000,000 | LA provides for PQ above € 10,000,000 and ICB is a default method |
| 4. | NCB (Works) | Works< €5,000,000 | LA provides for "works estimated to cost less than €5,278,000" and it was reduced further due to EU Regulation (ref. para 3) |
| 5. | ICB (Non-Consultant Services) | TS > €5,000,000 | per LA |
| 6. | NCB (Non-Consultant Services) | TS < €5,000,000 | per LA |
| 7. | Shopping | Works< €75,000 Goods < €75,000 | per LA |
| 8. | Direct Contracting | < €600,000 | Direct contracts below EUR 6,000 will follow the Polish Procurement Law. Any DC should meet Procurement Guidelines requirements 3.6 (a) - (e) |

Prior Review Threshold
Procurement Decisions subject to Prior Review by the Bank as stated in Appendix 1 to the Guidelines for Procurement: Thresholds for applicable procurement methods (not limited to the list below) are determined by the Bank and agreed with the Borrower based on the assessment of the implementing agency’s capacity.

|  | Procurement Method | Prior Review Threshold | Comments |
| --- | --- | --- | --- |
| 1. | ICB (Goods) | Goods > €500,000 | All ICB prior review |
| 2. | NCB (Goods) | Goods <€500,000 | All NCB post review |
| 3. | ICB (Works) | Works> €5,000,000* | All ICB prior review |
| 4. | NCB (Works) | Works< €5,000,000* | All NCB post review |
| 5. | ICB (Non-Consultant Services) | TS > €5,000,000* | All ICB prior review |
| 6. | NCB (Non-Consultant Services) | TS < €5,000,000* | All NCB post review |
| 7. | Shopping | Works< €75,000 Goods < €75,000 | All Shopping post review |
| 8. | Direct Contracting | All | All DC contracts irrelevant of the value should be prior-reviewed by the Bank |

2.	Prequalification. Bidders for works, estimated to cost more then EURO10,000,000 shall be prequalified in accordance with the provisions of      paragraphs 2.9 and 2.10 of the Guidelines.

3.	Any Other Special Procurement Arrangements:

NCB-POPT	Polish procurement procedure of open tendering (POPT) according to Chapter 3, Section 1 of Polish Procurement Law or  National Competitive Bidding (NCB) for contracts up to € 5,000,000*.

ICB – POPT	for contracts more than € 5,000,000*that are to be cofinanced by EU
Cohesion Fund.  – This is the Polish procurement procedure of open tendering (POPT) according to Chapter 3, Section 1 of Polish Procurement Law, „except that the Bank’s Standard Bidding Documents for International Competitive Bidding procedures shall be used and the bidding opportunities shall be advertised in U.N. Development Business, the Europr Journal of Procurement and the Polish Bulletin of Procurement. The Bank will conduct a prior review of such contracts“ as stated in Loan Agreement Schedule 4, section II, paragraph A2.

*replace the EUR 5,278,000 threshold with the current valid threshold of EUR 5,000,000. The Regulation of the Prime Minister of 16 December 2011 on the value of contracts and design contests imposing an obligation to submit the notices to the Office for Official Publications of the European Communities.

III. Selection of Consultant

1.	Prior Review Threshold: Selection decisions subject to Prior Review by Bank as stated in Appendix l to the Guidelines Selection and Employment of Consultants:

|  | Selection Method | Prior Review Threshold | Comments |
| --- | --- | --- | --- |
| 1. | Firms QCBS, FBS, LCS | Above 150 000 EURO |  |
| 2. | Firms CQS | 150 000 EURO or more |  |
| 3. | Single Source Selection (Firms) | all | Not included in the original Loan Agreement, a one time procurment waiver to use SSS of January 13, 2009. Contract of IMGW no C2-12. |
| 4. | Individual Consultants | Above 50,000 EURO |  |
| 5 | Individual Consultants Sole - Source | all | Justification should be provided which meets the requirements of para. 5.4 of the Bank's Consultants Guidelines. |

2.	Short list comprising entirely of national consultants: Short list of consultants for services, estimated to cost less than 150 000 EURO equivalent per contract, may comprise entirely of national consultants in accordance with the provisions of paragraph 2.7 of the Consultant Guidelines.

Updated  Procurement Plan  - May 28, 2013

| Ref. No. | Contract (Description) | Category of expenditure | Number of Contracts | Procurement Method | Prequalification (Yes/No) | Review by Bank (Prior / Post) | ESTIMATED / ACTUAL DATES |  | COMMENTS |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  |  |  |  |  | TOR/ REI/ ITQ/ BD Prepare & Submission | IFB/ BD/ ITQ / REI issue Date | Bid Opening/ Proposals submission Date | Bids Evaluation Report / Technical & Financial Evaluation Report & Award Recommendation | Contract Signing Date | Contract Completion Date | PIU is responsible for the implementation of that particular contract. |  |
| ORFPP-A1-1 | Construction of Raciborz dry polder | CW | 1 | ICB | Y | Prior | November 2012 | November 2012 | February 2013 | February 2013 | June 2013 | December 2017 | PIU of RZGL GL | World Bank issued no objection for BER. Dragados S.A. Spain Signed Contract: June 18, 2013. Value of contract: 936 675 200,00 PLN |
| ORFPP-A1-2 | Modernisation of pizometer network | CW | 1 | NCB | N | Post | October 2012 | November 2012 | November 2012 | December 2012 | January 2013 | May 2013 | PIU of RZGW GL | Contract was ended. |
| ORFPP-A1-3 | Tree felling and preparation of the site within the strip of investment performance | CW | 1 | NCB | N | Post | October 2012 | November 2012 | November 2012 | December 2012 | December 2012 | May 2013 | PIU of RZGW GL | Contract was ended. |
| ORFPP-A2-1 | Roads and infrastructure for New Village: Roads sewage system, water supply | CW | 1 | NCB | N | Post | September 2013 | October 2013 | October 2013 | November 2013 | November 2013 | May 2015 | Commune of Lubomia | Technical Specifications (TS) has been developed. Commune of Lubomia is responsible for the implementation of that particular contract. |
| ORFPP-A2-2 | Energy net for New Village: Networks of electronic energy Lighting, Telecommunication Lines | CW | 1 | NCB | N | Post | September 2013 | October 2013 | October 2013 | November 2013 | November 2013 | May 2014 | Commune of Lubomia | Technical Specifications (TS) has been developed. Commune of Lubomia is responsible for the implementation of that particular contract. |
| ORFPP-A2-3 | Sewage treatment plant | CW | 1 | NCB | N | Post | August 2013 | September 2013 | September 2013 | October 2013 | October 2013 | June 2014 | Commune of Lubomia | Specifications (TS) has been developed. Commune of Lubomia is responsible for the implementation of that particular contract. |
| ORFPP-A2-4 | Construction of the municipal area Construction of a municipal building Utility buildings: Fire station, building sports, Fields park | CW | 1 | NCB | N | Post | February 2014 | March 2014 | March 2014 | April 2014 | April 2014 | May 2015 | Commune of Lubomia | Technical Specifications (TS) has been developed. Commune of Lubomia is responsible for the implementation of that particular contract. |
| ORFPP-A2-5 | Construction of the cemetery and relocation graves | CW | 1 | NCB | N | Post | May 2014 | May 2014 | June 2014 | June 2014 | July 2014 | April 2015 | Commune of Lubomia | Technical Specifications (TS) has been developed. Commune of Lubomia is responsible for the implementation of that particular contract. |
| ORFPP-A3-1 | Construction Supervision of Raciborz dry Polder | CS | 1 | QCBS | NA | Prior | October 2008 | February 2009 | April 2009 | July 2009 | November 2009 | November 2014 | PIU of RZGL GL | Contract was ended. |
| ORFPP-A3-2 | Supervision of Raciborz dry Polder | CS | 1 | QCBS |  | Prior | April 2013 | April 2013 | May 2013 | June 2013 | July 2013 | December 2017 | PIU of RZGL GL | Proposals must be submitted : 28th May 2013, time: 11.00 a.m. (Central European Time) |
| ORFPP-A3-3 | Consultant for RAP | CS | 1 | CQS |  | Prior | November 2012 | November 2012 | November 2012 | December 2012 | December 2012 | November 2014 | PIU of RZGW GL | Signed Contract |
| ORFPP-A3-4 | Consultant for environmental | CS | 1 | CQS |  | Prior | November 2012 | November 2012 | November 2012 | December 2012 | December 2012 | November 2014 | PIU of RZGW GL | Signed Contract |
| ORFPP-A3-5 | Consultant Hydraulic Specialist | CS | 1 | IC |  | Prior | November 2012 | November 2012 | November 2012 | December 2012 | December 2012 | November 2014 | PIU of RZGW GL | Signed Contract |
| ORFPP-A3-6 | Support for legal | CS | 1 | CQS |  | Prior | January 2013 | January 2013 | February 2013 | February 2013 | February 2013 | November 2014 | PIU of RZGL GL | Signed Contract |
| ORFPP-A3-7 | Design and construction supervision of the project: the construction of technical, road and municipal infrastructure within the area of New Village. | CS | 1 | LCS | NA | Prior | April 2013 | May 2013 | June 2013 | August 2013 | August 2013 | June 2016 | Commune of Lubomia | RFP sent to World Bank |
| ORFPP-A3-8 | Purchase of maps and documents | G | 8 | DC | N | Prior |  |  |  |  | November 2009 | November 2014 | PIU of RZGW GL | On-going. Maps were purchased for the amount of 74 401,91PLN : 4 = 18 850,5 Euro |
|  | OFRPP-B1 Construction of levees upstream of Wroclaw under WFS |  |  |  |  |  |  |  |  |  |  |  | PIU of DZMiUW |  |
| ORFPP- B1-1 | Modernization of Embankment in Blizanowice and Trestno | CW | 1 | ICB | Y | Prior | May 2011 | November 2011 | February 2012 | March 2012 | April 2012 | December 2013 | PIU of DZMiUW | „Energopol Szczecin S.A.” (Poland) Signed Contract: April 17, 2012. Value of contract: 14 333 662,09 PLN |
| ORFPP B1-2 | Modernization of Embankment in Kotowice and Siedlce | CW | 1 | ICB | Y | Prior | May 2012 | May 2012 | July 2012 | August 2012 | August 2012 | October 2014 | PIU of DZMiUW | “Skanska S.A.” (Poland) Signed Contract: August 31, 2012. Value of contract: 65 988 211,89 PLN |
| ORFPP- B1-3 | Construction of other levees upstream of Wroclaw | CW | 1 | ICB | Y | Prior | July 2012 | August 2012 | October 2012 | October 2012 | November 2012 | December 2014 | PIU of DZMiUW | JV “Budimex S.A. “ (Poland) Leader and Ferrovial Agroman SA (Spain) –Partner. Signed Contract November, 28, 2012. Value of contract: 39 997 177,26 PLN |
| ORFPP- B1-11 | Construction of levees downstream of Wroclaw under WFS | CW | 1 | ICB | Y | Prior | July 2012 | July 2012 | August 2012 | September 2012 | October 2012 | November 2014 | PIU of DZMiUW | “Skanska S.A.” (Poland) Signed Contract: October 26, 2012. Value of contract: 49 741 578,68PLN |
|  | OFRPP-B2 Construction of Boulevards/Retaining walls in WFS |  |  |  |  |  |  |  |  |  |  |  | PIU of RZGW WL |  |
| ORFPP- B2-2.1 | Modernization of Boulevards of the Srodmiejska Odra River | CW | 1 | ICB | Y | Prior | February 2012 | May 2012 | July 2012 | August 2012 | August 2012 | September 2014 | PIU of RZGW WL | JV "POL-AQUA S.A.” (Poland) Leader and DRAGADOS S.A. (Spain) - Partner” Signed Contract: August 31, 2012. Value of contract: 54 448 495,15 PLN |
| ORFPP-B2-3.1 | Excavation and expansion of channels in WFS | CW | 1 | ICB | Y | Prior | April 2012 | April 2012 | June 2012 | July 2012 | August 2012 | September 2014 | PIU of RZGW WL | JV „Energopol Szczecin S.A.” (Poland) Leader and Azerkorpu - Azerbejdzan - Partner Signed Contract: August 1, 2012. Value of contract: 279 085 663,48 PLN |
| ORFPP-B2-3.2 | Excavation and expansion of channels in WFS and adaptation of Rędzin barrage to pass flood water | CW | 1 | ICB | Y | Prior | April 2012 | April 2012 | June 2012 | September 2012 | October 2012 | December 2014 | PIU of RZGW WL | „Sinohydro” China Signed Contract: October 24, 2012. Value of contract: 306 085 879,72 PLN. |
| ORFPP-B2-4.2 | Other Hydraulic structures in WFS | CW | 1 | ICB | Y | Prior | July 2012 | August 2012 | August 2012 | August 2012 | September 2012 | December 2014 | PIU of RZGW WL | JV „Hydrobudowa Gdansk” (Poland) Leader and Zakladani Stavab (Czech Republic) - Partner Signed Contract: September 19, 2012. Value of contract: 36 263 989,88 PLN. |
| ORFPP-B4-2 | Design and Construction Supervision for Wroclaw Floodway System component B2 | CS | 1 | QCBS |  | Prior | November 2008 | January 2009 | April 2009 | May 2009 | October 2009 | May 2014 | PIU of RZGW WL | On-going. JV URS -lider, Halcrow Grup, BRL Ingenierie |
|  | OFRPP-B3 Flood relief through Widawa Transfer |  |  |  |  |  |  |  |  |  |  |  | PIU of DZMiUW |  |
| ORFPP-B3-1 | Flood relief through Widawa Transfer (Section Odra – Widawa Weir – to the railway bridge (Krzywoustego St.) | CW | 1 | ICB | Y | Prior | July 2013 | July 2013 | September 2013 | October 2013 | October 2013 | December 2015 | PIU of DZMiUW | World Bank issued no objection for PQD. Cost is based on the Consultant of DZMiUW estimation calculated in 2012, the estimated cost is 135,9 mln euro (1 euro = 4 pln) |
| ORFPP-B3-2 | Flood relief through Widawa Transfer (Section the Widawa River from the railway bridge (Krzywoustego St.) to estuary to the Odra River) | CW | 1 | ICB | Y | Prior | July 2013 | July 2013 | September 2013 | October 2013 | October 2013 | December 2015 | PIU of DZMiUW |  |
| ORFPP-B3-3 | Mitigation measures realization according to EMP (mowing the grass) | CW | 1 | SH | N | Post | March 2013 | March 2013 | April 2013 | May 2013 | May 2013 | September 2013 | PIU of DZMiUW | Not started |
|  | OFRPP-B4 Design, Construction supervision, Administration |  |  |  |  |  |  |  |  |  |  |  |  |  |
| ORFPP- B4-1 | Design and Construction Supervision for Wroclaw Floodway System components B1 and B3 | CS | 1 | QCBS |  | Prior | November 2008 | January 2009 | April 2009 | May 2009 | October 2009 | May 2014 | PIU of DZMiUW | On-going JV Grontmij Polska – lider, Grontmij Nederland B.V. Artelia Ville & Transport SAS, Artelia Sp. z o.o, Ekocentrum. Cost: 258 396,00 Euro and 53 602 135,20 pln ( 13 400 533,75 Euro -1 euro = 4 pln ) Total cost: 13 658 929,75 Euro |
| ORFPP-C4-1 | Monitoring and evaluation of project impact Supervision of EMP and RAP | CS | 1 | QCBS |  | Prior | November 2008 | January 2009 | April 2009 | June 2009 | April 2010 | November 2014 | PCU | Contract was ended. |
| ORFPP-C5-1 | Preparation strategy of projects for PCU | CS | 1 | IC |  | Prior | May 2013 | June 2013 | August 2013 | September 2013 | September 2013 | January 2014 | PCU | TOR under preparation |
| ORFPP- C2-1 | Preparation of the Quality Control Algorithms for Hydrological and Meteorological Measurement and Hydrological Forecasts | CS | 1 | LCS |  | Prior | May 2012 | June 2012 | October 2012 | November 2012 | December 2012 | August 2013 | PIU of IMGW | Technical Evaluation Report sent to World Bank. |
| ORFPP- C2-6 | Implementation of the IT System for Quality Control of Hydrological and Meteorological Measurements and Hydrological Forecasts, Expansion of the Client Service System (SOK) and Implementation of the Central Historical Database | G | 1 | ICB | Y | Prior | December 2010 | March 2011 | August 2011 | October 2011 | December 2011 | August 2013 | PIU of IMGW | On-going Asseco Poland. |
| ORFPP- C2-12 | C2.12 Technical Support for the Project and Strengthening of IMGW's Institutional Capacity | CS | 1 | SSS |  | Prior |  |  |  |  | October 2009 | August 2013 | PIU of IMGW | On-going ARTELIA Eau & Environnement (former Sogreah SAS) |
| ORFPP-D1 | Contract no. 1/2008 J. Zaleski Project Management. | CS | 1 | IC |  | Prior |  |  |  |  | February 2008 | November 2014 | PCU | On - going |
| ORFPP-D1 | Contract no. 2/2011 W. Krochmal PCU Director | CS | 1 | IC |  | Prior | February 2011 | April 2011 | April 2011 | May 2011 | June 2011 | November 2014 | PCU | On - going |
| ORFPP-D1 | Contract no. 2/2008 A. Tiukało | CS | 1 | IC |  | Prior |  |  |  |  | June 2008 | March 2010 | PCU | Ended |
| ORFPP-D1 | Contract no. 1/2008 A. Drożdż | CS | 1 | IC |  | Prior |  |  |  |  | June 2008 | November 2014 | PCU | On - going |
| ORFPP-D1 | Contract no. 3/2008 M. Kozłowska | CS | 1 | IC |  | Prior |  |  |  |  | June 2008 | August 2009 | PCU | Ended |
| ORFPP-D1 | Contract no. 5/2008 J. Banaszak | CS | 1 | IC |  | Prior |  |  |  |  | July 2008 | November 2014 | PCU | On - going |
| ORFPP-D1 | Contract no. 6/2008 A. Piwowarczyk | CS | 1 | IC |  | Prior |  |  |  |  | July 2008 | November 2014 | PCU | On - going |
| ORFPP-D1 | Contract no. 7/2008 W. Barczyński | CS | 1 | IC |  | Prior |  |  |  |  | July 2008 | November 2014 | PCU | On - going |
| ORFPP-D1 | Contract no. 8/2008 M. Kończak | CS | 1 | IC |  | Prior |  |  |  |  | September 2008 | September 2011 | PCU | Ended |
| ORFPP-D1 | Contract no. 4 /2011 J. Stanisławski | CS | 1 | IC |  | Prior |  |  |  |  | September 2011 | November 2014 | PCU | On - going |
| ORFPP-D1 | Contract no. 9/2008 B. Nowak | CS | 1 | IC |  | Prior |  |  |  |  | July 2008 | January 2010 | PCU | Ended |
| ORFPP-D1 | Contract no. 10/2008 H. Batko | CS | 1 | IC |  | Prior |  |  |  |  | September 2008 | November 2014 | PCU | On - going |
| ORFPP-D1 | Contract no. 11/2008 Casus Iuris - Support for legal | CS | 1 | CQS |  | Prior |  |  |  |  | November 2008 | September 2012 | PCU | Ended |
| ORFPP-D1 | Contract no. 3/2012 Casus Iuris - Support for legal | CS | 1 | CQS |  | Prior |  |  |  |  | September 2012 | November 2014 | PCU | On - going |
| ORFPP-D1 | Contract no. 1/2009 D. Kuchar Chief Accountant | CS | 1 | IC |  | Prior |  |  |  |  | August 2009 | November 2014 | PCU | On - going |
| ORFPP-D1 | Contract no. 2/2009 J. Zielińska Accounting Specjalist | CS | 1 | IC |  | Prior |  |  |  |  | August 2009 | November 2014 | PCU | On -going |
| ORFPP-D1 | Contract no. 3/2009 M. Kozłowska Administration Specialist | CS | 1 | IC |  | Prior |  |  |  |  | September 2009 | October 2011 | PCU | Ended |
| ORFPP-D1 | Contract no. 4/2009 Administration Specialist at PCU | CS | 1 | IC |  | Post |  |  |  |  | December 2009 | March 2011 | PCU | Ended |
| ORFPP-D1 | Contract no. 1/2010 B. Nowak Deputy Project Director | CS | 1 | IC |  | Prior |  |  |  |  | January 2010 | November 2014 | PCU | On - going |
| ORFPP-D1 | Contract no. 2/2010 St. Kostecki Hydraulic Specialist | CS | 1 | IC |  | Prior |  |  |  |  | April 2010 | November 2014 | PCU | On - going |
| ORFPP-D1 | Contract no. 1/2011 L. Klimek Administration Specialist at PCU | CS | 2 | IC |  | Prior | May 2011 | May 2011 | June 2011 | June 2011 | June 2011 | November 2014 | PCU | On - going |
| ORFPP-D1 | Contract no. 8/2011 I. Chlebowicz - Rega Administration Specialist | CS | 1 | IC |  | Prior | October 2011 | November 2011 | November 2011 | November 2011 | December 2011 | October 2012 | PCU | Ended |
| ORFPP-D1 | Contract no. 5/2011 M. Kozłowska Coordination Specjalist | CS | 1 | IC |  | Prior | May 2011 | May 2011 | June 2011 | June 2011 | October 2011 | November 2014 | PCU | On - going |
| ORFPP-D1 | Contract no. 2/ 2012 J. Wawrzyniak Consultant PR | CS | 1 | IC |  | Prior | May 2011 | April 2012 | May 2012 | May 2012 | July 2012 | November 2014 | PCU | On going |
| ORFPP-D1 | Interpreter services for PCU | CS | 1 | SS |  | Prior | November 2009 | January 2010 | April 2010 | June 2010 | July 2010 | November 2014 | PCU | On-going |
| ORFPP-D1 | Consultant for SMOK | CS | 1 | IC |  | Prior | May 2013 | July 2013 | October 2013 | September 2013 | September 2013 | November 2014 | PCU | TOR will be prepared |
| ORFPP-D1 | Dam Safety Panel( Panel of Experts) | CS | 2 | IC |  | Prior | May 2011 | June 2011 | July 2011 | July 2011 | August 2011 | November 2014 | PCU | On-going |
| ORFPP-D1 | D1 Short-term consultant to determine the scope of work in the building of the Office of PCU | CS | 1 | IC |  | Post | January 2010 | April 2010 | June 2010 | July 2010 | October 2011 | May 2012 | PCU | Ended |
| ORFPP-D1 | Specialist financial settlements | CS | 1 | IC |  | Prior | August 2013 | October 2013 | October 2013 | November 2013 | December 2013 | November 2014 | PCU | TOR will be prepared |
| ORFPP-D1 | Contract no 1/ 2012 A. Woźny Project Manager for A1-1 | CS | 1 | IC |  | Prior | March 2012 | April 2012 | May 2012 | May 2012 | June 2012 | November 2014 | PCU | Ended on November 2012 |
| ORFPP-D1 | Contract no 3/ 2012 A. Bombała, new Project Manager for A1-1 | CS | 1 | IC |  | Prior | September 2012 | September 2012 | October 2012 | October 2012 | November 2012 | November 2014 | PCU | Start in November 2012 |
| ORFPP-D1 | New Indywidual Consaltants | CS | 1 | IC |  | Prior | January 2013 | February 2013 | March 2013 | March 2013 | March 2013 | November 2014 | PCU | TOR will be prepared |
| ORFPP-D1 | Consultant - herpetologist and amphibian expert | CS | 1 | IC |  | Prior | November 2012 | December 2012 | January 2013 | January 2013 | February 2013 | November 2014 | PCU | World Bank issued no objection for TOR. |
| ORFPP-D1 | Consultant - bat expert | CS | 1 | IC |  | Prior | November 2012 | December 2012 | January 2013 | January 2013 | February 2013 | November 2014 | PCU | World Bank issued no objection for TOR. |
| ORFPP-D1 | Consultant - ichthyology expert | CS | 1 | IC |  | Prior | November 2012 | December 2012 | January 2013 | January 2013 | February 2013 | November 2014 | PCU | World Bank issued no objection for TOR. |
| ORFPP-D1 | Consultant - archeology expert | CS | 1 | IC |  | Prior | November 2012 | December 2012 | January 2013 | January 2013 | February 2013 | November 2014 | PCU | World Bank issued no objection for TOR. |
| ORFPP-D1 | Consultant - to operate the Project Monitoring and Information System (PMIS) | CS | 1 | IC |  | Prior | December 2012 | December 2012 | January 2013 | January 2013 | February 2013 | November 2014 | PCU | World Bank issued no objection for TOR. |
|  | Operation cost for PCU and PIU’s | OP |  |  |  | Post |  |  |  |  |  | November 2014 | PCU | On -going |

*1Euro = 4 PLN.

**The term, means expenditures approved by the Bank and incurred to finance the reasonable cost of office rent, office supplies, utilities, translation services, operation and maintenance of equipment and vehicles, and minor cost necessary for managing the Project.